MIGRATION GOVERNANCE · ROLE GUIDE # Sysadmin Guide Windows Server 2003 – 2025 · servers, files, network, protocols ● DISCOVERY — ● INSTALL & CONFIGURE — ● MIGRATION — ● DECOMMISSIONING

Role guide for sysadmins · the governance guide is the big picture; this page is what the sysadmin owns · the SQL side is in the DBA guide

Important The sysadmin owns everything around SQL Server: the server, the OS, disks, network, DNS, firewall, certificates, file shares, FTP flows and legacy protocols. The DBA owns everything inside the instance. You work together, but each side signs for its own part.

———   ◆   ———

## 1. Supported vs works but not supported

These two words tell you who carries the risk. Whether a clone is needed depends on something else: how certain the path is (when to clone).

|  | SUPPORTED | WORKS, BUT NOT SUPPORTED |
| --- | --- | --- |
| Meaning | Microsoft documents it: the OS version is in support, the upgrade path is in Microsoft's table, and the software on it is supported on that OS | It runs, and we proved it in the lab, but Microsoft doesn't document it (or flags it as incompatible) |
| Fixes and security updates | Yes | No. Out-of-support OS, or an app the OS vendor won't fix |
| Microsoft support case | Accepted | Can be refused |
| Approval | Normal gate | Normal gate. No exception, not a blocker. If the path is uncertain, it runs on a cloned VM first |
| Can it be the end state? | Yes | No. A step on the way to a newer, supported platform |
| Who carries the risk | Shared with the vendor | Us alone, which is why an uncertain path is proven on a clone first |

Important Every migration ends on a newer, supported version. An unsupported step on the way (for example 2008 R2 → 2012 R2) is allowed. Clone only when the path is uncertain: not yet done in the lab or the program, something unusual found on this server, or you're not confident. A proven path goes straight to production, with a snapshot before each step. When a clone is needed, the sysadmin clones and isolates the VM (governance §2.7).

On the sysadmin side, it typically looks like this:

- The upgrade path is supported, but what runs on it isn't. Windows 2012 R2 → 2025 is a supported OS upgrade, but setup flags SQL Server 2005 as an incompatible application (a soft block). The OS is supported; the server as a whole isn't.

- A path that Microsoft no longer documents. Windows 2008 R2 SP1 → 2012 R2 isn't in Microsoft's current upgrade table any more. It worked in our lab, but treat it as works, but not supported.

- An out-of-support OS (2003, 2008, 2008 R2, 2012 R2) without ESU gets no security updates at all. As a step on the way, it is fine; as an end state, it is not.

- Legacy protocols left on (SMBv1, TLS 1.0, NTLMv1): Windows still has the switches, but our policy is to turn them off. Leaving them on needs an exception (governance §2.6).

———   ◆   ———

## 2. Your responsibilities

A = accountable (signs for it), R = does the work, C = consulted. The full RACI with every role is in the governance guide §2.3.

| Phase | Sysadmin is A for | Sysadmin is R for | Sysadmin is C for |
| --- | --- | --- | --- |
| 1 · Discovery | Server discovery script and output; server and protocol flags | Files, shares and unused data; legacy protocols (SMBv1, FTP, TLS, NTLMv1); connection capture at OS level | SQL discovery |
| 2 · Install & configure | Target server build and hardening | Smoke test (server side) | SQL install; firewall and certificate requests (Security / Network own them) |
| 3 · Migration | OS in-place upgrade and hardening, up to the OS hand-off to the DBA. OS-level cut-over: DNS, aliases, file shares, MFT flows, scheduled tasks | Clone (if the path is uncertain); cut-over and rollback plan (server side) | Everything SQL after the OS hand-off (DBA) |
| 4 · Decommissioning | Server removal from every system | Quiet-period or scream-test monitoring; carrying out the data decision for file shares | Instance decommissioning (DBA) |

What the sysadmin signs at each gate

| Gate | Sysadmin signature covers |
| --- | --- |
| Gate 1 | Server summary reviewed; every server and protocol RED flag decided; FTP flows listed for MFT; OS path chosen (section 5) |
| Gate 2 | Server built to standard; legacy protocols off (or an exception logged); agents installed; MFT flows set up |
| Gate 3 | DNS and aliases switched; file shares and scheduled tasks moved; MFT flows tested with partners; monitoring green |
| Gate 4 | Quiet period clean; final backup kept; removed from AD, DNS, DHCP, firewall, monitoring, backup, AV, patching, CMDB |

———   ◆   ———

## 3. Hand-offs with the DBA

Three hand-off points (governance §2.2):

- After Discovery (Gate 1): OS path and SQL path agreed together.

- OS hand-off: the sysadmin finishes the OS in-place upgrade and hardening, then hands the server to the DBA. From then on, the DBA is responsible up to Gate 3.

- Before decommissioning: the DBA confirms the databases are offline and backed up; then the sysadmin removes the server.

Most delays happen between the two roles. Ask early, using this list.

| Sysadmin needs from the DBA | DBA needs from the sysadmin |
| --- | --- |
| SQL port(s) and Browser need, for the firewall rules | Target server built, with disk layout for SQL: data, log, tempdb and backup volumes, 64 KB allocation unit |
| AV exclusions for data, log and backup files and sqlservr.exe | Service accounts or gMSAs created, passwords in the vault, with instant file initialization and lock pages in memory rights |
| Backup schedule and retention for the agent | Backup agent installed; backup share reachable |
| Which apps and servers connect to SQL (from the capture), for the dependency list | Firewall rules for 1433 / named instance ports |
| Go / no-go on the SQL side before the DNS switch | DNS alias switch at the agreed time in cut-over |
| TLS level needed by SQL clients (legacy 2005 clients need TLS 1.0) | TLS certificate for SQL encryption |
| Confirmation that databases are offline before power-off | Server kept powered on during the quiet period |

———   ◆   ———

## 4. Target platform

|  | Default | Why |
| --- | --- | --- |
| OS for a new build | Windows Server 2025 (2022 if the application vendor requires it) | Longest support. 2025 supports SQL 2019, 2022 and 2025 (see the DBA matrix) |
| 1st choice: in-place upgrade | Whenever a path exists (section 5). Done by the sysadmin. On a cloned VM first only if the path is uncertain (when to clone) | Same server, name, IP and data: fewer dependencies to move. Production gets a snapshot before each hop |
| After an in-place upgrade | Harden after the last hop: SMBv1 off, TLS 1.2+ only, NTLMv1 refused, old roles and agents reviewed | An in-place upgrade keeps every old setting, including the insecure ones (governance §2.6) |
| 2nd choice: side-by-side | New server, then move apps and data. When no in-place path exists (2003), or the clone test fails | Clean build. The source stays untouched as the rollback |

Note Check the SQL version before you choose the OS. SQL 2017 isn't supported on Windows 2025, and SQL 2016 isn't supported on 2022. Agree the OS and SQL pair with the DBA at Gate 1.

———   ◆   ———

## 5. Windows in-place upgrade paths

### 5.1 Paths

| From | To (in place) | Status |
| --- | --- | --- |
| 2003 | Nothing modern | No path. Side-by-side only |
| 2008 (x64) | 2012 | Older Microsoft guidance; no longer in the current table. Not lab-tested. Try it on a clone (then 2012 → 2016 → 2025); side-by-side if it fails |
| 2008 (x86, 32-bit) | Nothing | No path: Windows 2012 and later are x64 only. Side-by-side only |
| 2008 R2 SP1 | 2012 R2 | Works, but not supported (no longer in Microsoft's current table). LAB OK |
| 2012 | 2012 R2, 2016 | Supported |
| 2012 R2 | 2016, 2019, 2025 | Supported. Not to 2022 (not supported). 2012 R2 → 2025 is LAB OK |
| 2016 | 2019, 2022, 2025 | Supported |
| 2019 | 2022, 2025 | Supported |
| 2022 | 2025 | Supported |

Source: Microsoft, Windows Server upgrade paths. Since 2025, a non-clustered server can jump up to four versions; earlier versions allow two. Rules that always apply:

- same edition or higher;

- same install language;

- x64 to x64;

- evaluation media can't upgrade a licensed server;

- disable NIC teaming first;

- each hop needs its own licence.

### 5.2 Lab-proven chain: 2008 R2 SP1 → 2012 R2 → 2025

PARTLY NOT SUPPORTED. Proven in our lab, with SQL 2005 and a live application on the server. The SQL side and its conditions are in the DBA guide §5.3.

| 2008 R2 SP1 baseline + snapshot | works, not supported ~25 min, 3 reboots → | 2012 R2 + April 2014 Update + all final updates | supported OS path ~1 h → | 2025 checks + snapshot |
| --- | --- | --- | --- | --- |

What the lab taught us. Each item stopped or broke an upgrade at least once:

| # | Lesson |
| --- | --- |
| 1 | Check the ISO first: authentic, not Evaluation (ei.cfg with Channel=eval is a blocker), same edition and language |
| 2 | 2008 R2 needs SP1 before going to 2012 R2 |
| 3 | 2008 R2 → 2012 R2 unattended: the answer file needs ImageInstall and InstallTo (the existing OS partition). Run setup on the console, because the app-compatibility page (SQL 2005) waits for Confirm |
| 4 | Before going to 2025, patch 2012 R2 fully to its last public updates (SSU KB5032308 and rollup KB5031419). With only the 2014 updates, the 2025 setup crashed (0xC190011F) |
| 5 | 2025 needs a CPU with x86-64-v2 (on a VM, set the CPU type before the upgrade) |
| 6 | Keep 40 GB+ free on C: before each hop; grow the disk if needed |
| 7 | Activation is reset after each hop. Plan KMS or MAK |
| 8 | After the 2025 upgrade, RDP didn't listen until one more restart. Check RDP explicitly |
| 9 | With pending updates, shut down from inside Windows; the hypervisor's shutdown timed out |
| 10 | Snapshot before each hop, and keep it until the app owner confirms |

Full runbook, commands and logs: legacy-migration runbook.

———   ◆   ———

## 6. Options after Discovery

Discovery ends with one of three options for each server, decided at Gate 1 (governance §1.10):

| Discovery results | → | ▸ Is the server still used? |
| --- | --- | --- |
| Is the server still used? | → | ▸ no: Retire 6.2 ▸ yes: In-place path exists? (section 5) |
| Retire 6.2 | → | end |
| In-place path exists? (section 5) | → | ▸ yes: 1st: in-place upgrade 6.1 · clone if uncertain ▸ no: 2nd: side-by-side new server |
| 1st: in-place upgrade 6.1 · clone if uncertain | → | ▸ clone test fails: 2nd: side-by-side new server |
| 2nd: side-by-side new server | → | end |

### 6.1 In-place upgrade, step by step

What it is: Windows is upgraded on the same server: same name, IP, data, shares, scheduled tasks and installed software. Nothing has to be moved, which is why it's the first choice.

Important The OS in-place upgrade is done by the sysadmin, from preparation to hardening. When the OS is done, the sysadmin hands the server over to the DBA (step 5). From the hand-off on, the DBA is responsible for the rest of the migration: SQL to a newer version, data validation and the app test, up to Gate 3.

| # | Step | Sysadmin | DBA |
| --- | --- | --- | --- |
| 1 | Prepare | Check the path (5.1), media (not Evaluation, same edition and language), licences, free disk (40 GB+), CPU (x86-64-v2 for 2025). Patch the source fully. Decide whether the path is uncertain (when to clone) | Confirm the SQL version will run on each OS hop (DBA matrix). Full backups of all databases, system databases included |
| 2 | Clone: uncertain paths only | Clone the production VM, isolate it, run every hop, timed; record the steps and problems on the server page | Quick SQL check after each hop on the clone |
| 3 | Change window on production | Snapshot before each hop. Run the hops | Final backups before the first hop |
| 4 | Harden after the last hop | SMBv1 off, TLS 1.2+ only, NTLMv1 refused, old roles and agents reviewed. Activation (KMS or MAK). RDP checked. SQL services start |  |
| 5 | OS hand-off to the DBA | Record on the server page: final OS version, hardening done, snapshots kept, anything unusual seen. Tell the DBA | Accepts the server. From here, the DBA is responsible |
| 6 | SQL to a newer version | Available for OS issues | SQL upgrade in place, or a new instance on the same server, then data validation and app test (DBA §6.1) |
| 7 | Clean up after Gate 3 | Delete the snapshots; remove Windows.old with Disk Cleanup |  |

Rollback: revert to the snapshot taken before the failed hop. If a clone was used, its timings size the change window.

Note An in-place upgrade doesn't create a new server, so there's no Phase 2 build in the usual sense. Phase 2 becomes preparing the source (step 1), and the hardening in step 6 replaces the standard build's security settings.

### 6.2 Retire: when Discovery shows the server isn't used

If nobody and nothing uses the server any more, it isn't migrated at all. It goes straight to Phase 4 on the retire-only path (governance, retire-only path).

Evidence the sysadmin brings to Gate 1:

| Check | "Not used" looks like |
| --- | --- |
| Inbound connections during the capture week | None, apart from monitoring, backup and admin tools |
| SMB sessions and open files | None on the shares |
| Interactive and service logons (Security log) | Only admins and service accounts |
| FTP logs | No transfers in the retained logs |
| Scheduled tasks | Only maintenance (cleanup, defrag, backup); no business jobs, or the jobs' output isn't used by anyone |
| IIS logs (if any) | No requests, or only health checks |
| DNS aliases pointing to it | None, or the systems that use them confirmed retired |
| Monthly or quarterly jobs | Each one checked with its owner: not needed |

Important The sysadmin brings the evidence; the app owner decides. "No connections in a week" isn't proof on its own. The app owner confirms in writing that the service is no longer needed and decides what happens to the data.

Sysadmin tasks on the retire-only path:

☐  Announce the retirement date and a contact to the users and teams found in Discovery

☐  Carry out the data decision for the file shares (archive, hand over, or delete under the retention policy), after a last full backup

☐  Scream test: stop the services or disable the NIC, so it can be undone in minutes. At least 4 weeks, including a month-end

☐  If someone is affected: re-enable, record the missed dependency, and go back to Gate 1

☐  If nobody is affected: wait for the DBA's confirmation (if SQL is on it), power off, then the removal checklist (section 7, Phase 4)

———   ◆   ———

## 7. Tasks by phase

### Phase 1 · Discovery

Details and commands: governance §1.2 – 1.5.

☐  Run the server discovery script (yours or the reference one); output in Migration/<BUNDLE>/<SERVER>/1-Discovery/

☐  Platform, identity, software, roles, services, scheduled tasks (monthly or quarterly ones listed with an owner)

☐  Network: IPs, DNS aliases, hosts entries, listening ports, connection capture for the Discovery week

☐  Certificates, backup, monitoring and AV agents

☐  Legacy protocols: SMBv1 (server, clients, as a client), TLS, NTLMv1, telnet, SNMP. All documented

☐  FTP: every flow, its partner, where the files land on the file shares, and what processes them. Listed for MFT

☐  Files and shares: sizes, data by age, open-file sessions, orphaned home folders, risky file types

☐  Server flags written to the summary file; OS path chosen with the DBA (section 4); sign the Gate 1 part

### Phase 2 · Install & configure

☐  Server from the standard build, patched, in the right OU

☐  Disk layout to standard, including the SQL volumes the DBA asked for (64 KB allocation unit)

☐  Service accounts or gMSAs; passwords in the vault; IFI and lock pages in memory rights for SQL

☐  Roles and features from Discovery (IIS, .NET 3.5, MSMQ, …)

☐  SMBv1 off, TLS 1.2+ only, NTLMv1 refused, unless an exception is logged

☐  MFT flows set up for every FTP flow found

☐  Certificates (SHA-256, 2048-bit+); firewall rules requested from Security / Network

☐  Backup, monitoring, AV/EDR (with the DBA's exclusions), patching agents

☐  Scheduled tasks prepared but disabled

☐  Service recovery actions on critical services (lab finding: they aren't set by default for old software)

### Phase 3 · Migration

☐  If the path is uncertain: clone and isolate the production VM, and rehearse the OS steps on it, timed (when to clone)

☐  OS in-place upgrade on production (snapshot per hop), hardening, then the OS hand-off to the DBA, recorded on the server page

☐  File shares: robocopy with /COPYALL, a preliminary pass days before, then a final delta during the freeze

☐  Scheduled tasks enabled on the target, disabled on the source

☐  MFT flows switched over and tested with each partner; FTP service on the old server stopped

☐  DNS and aliases switched after the DBA's go; the old name kept as a CNAME only if the app needs it

☐  Every Discovery dependency tested: scanners, MFT partners, interfaces, reports

☐  Legacy-protocol flags closed, or covered by a logged exception

☐  Monitoring green for 48 h

### Phase 4 · Decommissioning

☐  Quiet period (or scream test for a retire): connection capture still running on the old server, including a month-end

☐  File-share data decision carried out: archive, hand over or delete, signed by the data owner

☐  Wait for the DBA's confirmation that the databases are offline and backed up

☐  Server powered off, not deleted, for the agreed wait; final backup kept, with a restore test

☐  Removed from AD, DNS, DHCP, firewall, monitoring, backup, AV/EDR, patching, CMDB; licences reclaimed; service accounts disabled; certificates revoked

☐  VM deleted or hardware disposed of, disks wiped

———   ◆   ———

Sysadmin guide · part of the migration governance · lab evidence in legacy-migration