OPERATIONS HANDBOOK · SYSADMIN & DBA # Migration Governance Windows Server 2003 – 2019 · SQL Server 2000 – 2019 ● DISCOVERY — ● INSTALL & CONFIGURE — ● MIGRATION — ● DECOMMISSIONING

Living document · owner: Migration lead · review every quarter, or after every gate that found a gap in this guide

Important Three rules apply to everything below. - No gate, no next phase. A phase is complete only when its gate checklist is signed. - One accountable person per activity. Many people can do the work; one person owns the result. - Collected data is reviewed. Every output has a reviewer's name and a date.

———   ◆   ———

## 1. Purpose and scope

This guide sets out who does what, what to collect, what to decide, and when a phase is done when legacy Windows servers and SQL Server instances move to supported platforms. It builds on the discovery work and documentation teams already have, and organises them into checklists, owners and gates.

|  | In scope | Out of scope |
| --- | --- | --- |
| Platforms | Windows Server 2003, 2008, 2008 R2, 2012, 2012 R2, 2016, 2019 | Desktop and endpoint migration |
| Databases | SQL Server 2000, 2005, 2008, 2008 R2, 2012, 2014, 2016, 2017, 2019 (instances, databases, jobs, packages) | Application code changes (tracked by the app team) |
| Services | File shares, FTP, IIS, scheduled jobs, print, legacy protocols | Network redesign and firewall policy (consulted, not owned) |
| Data | Live data, unused or stale data, backups, retention | Records-management policy (owned by the data owner) |

### Support status: what to migrate first

Microsoft extended support end dates. Anything already out of support goes first, starting with the oldest.

| Windows Server | SQL Server |
| --- | --- |
| ¦ Version ¦ Extended support ended / ends ¦ ¦---¦---¦ ¦ 2003 ¦ 2015-07-14 · out ¦ ¦ 2008 / 2008 R2 ¦ 2020-01-14 · out ¦ ¦ 2012 / 2012 R2 ¦ 2023-10-10 · out ¦ ¦ 2016 ¦ 2027-01-12 · within 3 months ¦ ¦ 2019 ¦ 2029-01-09 ¦ | ¦ Version ¦ Extended support ended / ends ¦ ¦---¦---¦ ¦ 2000 ¦ 2013-04-09 · out ¦ ¦ 2005 ¦ 2016-04-12 · out ¦ ¦ 2008 / 2008 R2 ¦ 2019-07-09 · out ¦ ¦ 2012 ¦ 2022-07-12 · out ¦ ¦ 2014 ¦ 2024-07-09 · out ¦ ¦ 2016 ¦ 2026-07-14 · out ¦ ¦ 2017 ¦ 2027-10-12 ¦ ¦ 2019 ¦ 2030-01-08 ¦ |

Note Servers and instances on extended security updates (ESU) or Azure-hosted extensions still count as out of support for planning purposes.

### What this guide brings

Migrations at this scale involve many teams, many servers and a lot of collected data. This guide gives everyone the same reference points:

| Topic | What the guide provides |
| --- | --- |
| Scripts | A shared, versioned set of discovery scripts per role, which everyone can improve |
| Collected data | A short flag summary for each server, so the key findings are easy to review and act on |
| Process | Checklists with owners and exit criteria for each phase |
| Decisions | A RACI per phase and a decision log, so it's clear who decides and what was decided |
| Hand-offs | Signed gates between phases, so each team knows when it can start |

———   ◆   ———

## 2. Governance model

### 2.1 Lifecycle and gates

| 1 · Discovery know the current state | → | ▸ Gate 1 Migration lead |
| --- | --- | --- |
| Gate 1 Migration lead | → | ▸ 2 · Install & configure build the target ▸ RED flag open: 1 · Discovery know the current state (back / optional) ▸ RETIRE (no migration): 4 · Decommissioning quiet period, retire |
| 2 · Install & configure build the target | → | ▸ Gate 2 Migration lead |
| Gate 2 Migration lead | → | ▸ 3 · Migration rehearse, cut over, validate |
| 3 · Migration rehearse, cut over, validate | → | ▸ Gate 3 App owner |
| Gate 3 App owner | → | ▸ 4 · Decommissioning quiet period, retire ▸ rollback: 3 · Migration rehearse, cut over, validate (back / optional) |
| 4 · Decommissioning quiet period, retire | → | ▸ Gate 4 Migration lead |
| Gate 4 Migration lead | → | end |

Gate 1 records one disposition for each server: migrate (Phases 2 → 3 → 4), consolidate (move its workload onto an existing server, then Phases 3 → 4), or retire (straight to Phase 4, see Retire-only path).

| # | Phase | Ends when | Gate owner | Typical duration |
| --- | --- | --- | --- | --- |
| 1 | Discovery | The current state is known and reviewed, and every red flag has a decision | Migration lead | 1 week (scripted collection + 4-day capture + review) |
| 2 | Install & configure | The target is built to standard, hardened and smoke-tested | Migration lead | 1–2 weeks |
| 3 | Migration | A rehearsal is done, cut-over is complete, data is validated and the app owner has accepted | App owner | 1–3 weeks |
| 4 | Decommissioning | Quiet period with no connections, final backup taken, server removed everywhere | Migration lead | 4–8 weeks (mostly waiting) |

### 2.2 Roles

This guide is the big picture. Sysadmins and DBAs work together, but each role has its own guide, setting out what it signs for at each gate and what it needs from the other:

| Sysadmin guide Server, OS, files, network, protocols · Windows in-place paths | DBA guide Instance, databases, data · SQL × Windows matrix · migration paths |
| --- | --- |

| Role | Owns | Typical person |
| --- | --- | --- |
| Sysadmin (guide) | Everything around SQL: OS, server, files, network and security discovery; target server build; OS-level cut-over; decommissioning the server | Windows team |
| DBA (guide) | Everything inside the instance: instance and database discovery; SQL build; data migration and validation; decommissioning the instance | DBA team |

Hand-off points between sysadmin and DBA:

| Discovery sysadmin + DBA in parallel | → | Gate 1 path agreed | → | OS in-place upgrade + hardening owned by the sysadmin | → | OS hand-off sysadmin → DBA | → | SQL to a newer version + data validation owned by the DBA | → |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Gate 3 app owner | → | Decommissioning DBA: databases offline → sysadmin: removal |
| --- | --- | --- |

| Hand-off | From → to | What's handed over | From then on |
| --- | --- | --- | --- |
| 1. After Discovery (Gate 1) | Both → both | Both summaries reviewed together; OS path and SQL path agreed; who does what, and when | The sysadmin plans the OS work; the DBA plans the SQL work |
| 2. OS hand-off | Sysadmin → DBA | OS upgraded and hardened; activation, RDP, network and agents checked; SQL services start; snapshots kept | The DBA is responsible for the server's migration: SQL upgrade or new instance, data validation, app test with the app owner, up to Gate 3 |
| 3. Before decommissioning | DBA → sysadmin | Databases offline, final backups kept, instance stopped | The sysadmin powers off and removes the server |
| App owner | Dependencies, users, business windows, testing, acceptance, decisions about unused data | Business or application team |  |
| Migration lead | Plan, tracking, decision log, gate sign-off (except Gate 3), escalation | Project or team lead |  |
| Security / network | Firewall rules, exceptions for legacy protocols, certificates, risk acceptance | Security and network teams |  |

### 2.3 RACI for all phases

R does the work · A owns the result (exactly one per row) · C consulted · I informed

| Activity | Sysadmin | DBA | App owner | Migration lead | Sec / Net |
| --- | --- | --- | --- | --- | --- |
| Phase 1: Discovery |  |  |  |  |  |
| Run the server discovery script | R/A | I |  | I |  |
| Run the SQL discovery script | C | R/A |  | I |  |
| Scheduled connection capture (during the week) | R | R | I | A |  |
| Discover files, shares and unused data | R |  | C | A |  |
| Discover legacy protocols (SMBv1, FTP, TLS, NTLMv1) | R | C | I | A | C |
| Confirm the dependency list | R | R | A | C |  |
| Review output and decide on flags | R | R | C | A | C |
| Decide the disposition (migrate · consolidate · retire) | C | C | A | R | I |
| Phase 2: Install & configure |  |  |  |  |  |
| Build and harden the target OS | R/A | I |  | I | C |
| Install and configure SQL | C | R/A |  | I |  |
| Firewall rules, certificates, legacy-protocol exceptions | C | C | I | I | R/A |
| Smoke test of the target | R | R | C | A |  |
| Phase 3: Migration |  |  |  |  |  |
| Rehearsal migration (on a clone if the path is uncertain) | R | R | C | A |  |
| Cut-over and rollback plan | R | R | C | A | C |
| OS in-place upgrade and hardening, up to the OS hand-off | R/A | C | I | I | C |
| Everything SQL after the OS hand-off: SQL upgrade or new instance, data migration and validation | C | R/A | C | I |  |
| Application testing and acceptance | C | C | R/A | I |  |
| Phase 4: Decommissioning |  |  |  |  |  |
| Quiet-period monitoring | R | R | I | A |  |
| Archiving or deleting unused data | R | R | A | C |  |
| Server and instance removal from every system | R | R | I | A | C |

Note The Gate 3 sign-off belongs to the app owner, not IT. IT says the migration is technically complete; only the business can say it works.

### 2.4 Cadence

Governance uses the existing meetings; it doesn't add new ones. Each meeting has a defined migration role:

| Meeting | When | Who | Migration topics | Output |
| --- | --- | --- | --- | --- |
| Daily status | Mon–Fri, 15 min | Sysadmins, DBAs, tech lead | Per-server progress, new RED flags (owner assigned on the spot), what's ready for a gate | Updated board, flag owners |
| Tech discussion | Mon–Thu afternoon, 30 min | Sysadmins, DBAs, tech lead, app owner or security when needed | Review of Discovery summaries, technical decisions on flags, migration method, gate reviews for Gates 1, 2 and 4 | Logged decisions, signed gates |
| Sprint ceremonies | Per sprint | Agile team | Planning: which servers and phases go into the sprint. Review: gates signed during the sprint. Retro: improvements to the scripts and this guide | Sprint backlog, done items, repository changes |
| Blockers meeting | Weekly | PM, tech lead, managers (security when a risk acceptance is on the agenda) | Only flags marked BLOCKER, risk acceptances, priorities and resources | Blocker decisions in the decision log |

Tip Definition of done for a sprint item: a server's phase is done when its gate is signed. Work without a signed gate stays in progress.

|  | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Morning | Daily status | Daily status | Daily status | Daily status | Daily status |
| Afternoon | Tech discussion | Tech discussion | Tech discussion | Tech discussion |  |
| Weekly | Blockers meeting (PM · tech lead · managers) · Sprint ceremonies on the sprint calendar |  |  |  |  |

Gate 3 is signed by the app owner. Invite them to the tech discussion for that gate, or collect the sign-off in writing.

### 2.5 Decisions, exceptions and escalation

Every RED flag ends with one recorded decision: fix, accept the risk, or blocker. Decisions go in the decision log (template in the Appendix), never only in email or chat.

| RED flag found | → | ▸ Owner assigned at the daily status |
| --- | --- | --- |
| Owner assigned at the daily status | → | ▸ Can the team fix it within the plan? |
| Can the team fix it within the plan? | → | end |
| R | → | end |

### 2.6 Legacy protocols and insecure settings

Discovery documents, Migration addresses. Everything found during Discovery is recorded in the flag summary. It's fixed as part of the migration: the target is built to the current standard and doesn't carry the legacy setting over.

| Found during Discovery | Addressed during Migration |
| --- | --- |
| FTP (servers, scripts, partner and device flows) | Flow moved to the MFT (managed file transfer) platform. Files that land on old file shares move with the flow. |
| SMBv1 (server or clients) | Off on the target. Clients that only speak SMBv1 are upgraded or replaced, or moved to MFT if they only exchange files |
| TLS 1.0 / 1.1, SSL | TLS 1.2+ only on the target. Partners and clients are tested during the rehearsal |
| NTLMv1 / LM | NTLMv2 or Kerberos only. Apps and devices that need NTLMv1 are identified and upgraded |
| Anything else (telnet, SNMP v1/v2, SHA-1 certificates, clear-text credentials, …) | Documented in the summary, with a fix planned in the migration |

Warning Exceptions can happen, for example a device that can't be upgraded in time. Every exception is logged in the decision log with: - an owner; - the reason; - the compensating control, such as network isolation or a restricted firewall rule; - an end date. Security is consulted on each one. Exceptions are reviewed at the weekly blockers meeting until they're closed.

### 2.7 Supported vs works but not supported

Every path, OS and SQL combination in this program is one of two kinds, and the difference decides how it is done:

|  | SUPPORTED | WORKS, BUT NOT SUPPORTED |
| --- | --- | --- |
| What it means | Microsoft documents it: in its compatibility matrix or upgrade table | It runs, and may be proven in our lab, but Microsoft doesn't document it |
| Fixes, security updates, support case | Yes | No. The risk is ours alone |
| Approval | Normal gate | Normal gate. No exception, not a blocker. If the path is uncertain, it runs on a cloned VM first (below) |
| End state? | Yes | No. A step on the way to a newer, supported SQL version |

Important Our rule: every migration ends on a newer, supported SQL version. An unsupported step on the way is fine. A cloned VM is used only when the path is uncertain. A proven path goes straight to production, with a snapshot before each step as the rollback.

#### When to clone

| The path is… | Clone? | Examples |
| --- | --- | --- |
| Proven: already done in the lab or on an earlier server of the program, and Discovery found nothing unusual on this server | No. Snapshot before each step on production | 2008 R2 SP1 → 2012 R2 → 2025 with SQL 2005 (LAB OK); 2016 → 2025 |
| Uncertain: never done yet, in the lab or in the program | Yes | 2008 x64 → 2012 → 2016 → 2025; a new SQL instance on the same server (DBA form C) |
| Uncertain: proven, but Discovery flagged something unusual on this server | Yes | Old drivers or hardware dongles, a vendor app with no support statement, RED flags on the OS or SQL side |
| Uncertain: the sysadmin or DBA isn't confident | Yes: their call, no justification needed |  |

Once an uncertain path has worked on a clone and in production, it's proven for the next servers. Record it on the server page.

#### Clone-first procedure

| Clone the production VM | → | ▸ Isolate the clone (no production network) |
| --- | --- | --- |
| Isolate the clone (no production network) | → | ▸ Run the path on the clone, timed |
| Run the path on the clone, timed | → | ▸ Test with the app (app owner) |
| Test with the app (app owner) | → | ▸ OK? |
| OK? | → | ▸ yes: Same steps on production in the change window ▸ no: Fix the runbook, re-clone, retry |
| Same steps on production in the change window | → | end |
| Fix the runbook, re-clone, retry | → | ▸ Clone the production VM |

| # | Step | Who |
| --- | --- | --- |
| 1 | Clone the production VM (and take a snapshot or backup of production as the reference) | Sysadmin |
| 2 | Isolate the clone. It has the same name, IP and domain identity as production, so it must never reach the production network: disconnected NIC or an isolated VLAN, with the app's test client inside it | Sysadmin |
| 3 | Run the path on the clone, step by step, and time each step: OS hops (sysadmin) and the SQL move to the newer version (DBA) | Sysadmin, DBA |
| 4 | Test with the application in the isolated network: key functions, reports, interfaces | App owner, with the DBA |
| 5 | Record the steps, durations and issues on the server page; that's the runbook for production | Sysadmin, DBA |
| 6 | Production: the same steps in the change window, with a snapshot before each hop. Rollback = the snapshot, or the untouched source | Sysadmin, DBA |
| 7 | Delete the clone after Gate 3. It holds production data, so treat it like production until then | Sysadmin |

Examples for each side are in the role guides: Sysadmin §1 (OS paths, out-of-support OS, legacy protocols) and DBA §1 (SQL on an unsupported OS, the lab-proven SQL 2005 path).

———   ◆   ———

## 3. Standards

### 3.1 Scripts and repository

Bring your own script. Everyone can use the script they know, as long as it follows five rules:

- it produces the standard output (3.2, 3.3);

- it covers the Discovery checklist;

- it's read-only;

- it contains no secrets;

- it's in the team repository before it runs on production, with its version recorded in the summary.

How to work with the repository, VS Code, the develop branch and Copilot is described in Scripts & VS Code.

### 3.2 Output naming and storage

Migration/ └── <BUNDLE>/ e.g. B03-Finance └── <SERVER>/ ├── 1-Discovery/ │ ├── <SERVER>_SUMMARY_<yyyyMMdd>.csv flags only, one row per finding │ ├── <SERVER>_<area>_<yyyyMMdd>.csv e.g. APP01_services_20261022.csv │ └── <INSTANCE>_sql-<area>_<yyyyMMdd>.csv e.g. APP01-SQL2005_sql-jobs_20261022.csv ├── 2-Build/ ├── 3-Migration/ └── 4-Decommission/

Gate sign-offs, decisions and status live on the server's Loop page, not in SharePoint (section 4).

A bundle is the group of servers that are discovered and migrated together. Each server belongs to exactly one bundle. If a server moves to another bundle, its folder moves with it.

All of this lives in one SharePoint location, with no copies in personal folders or mailboxes.

### 3.3 The flag summary

Raw data is for evidence; the summary is what gets read. Every script writes one summary file in this format:

| Server | Area | Item | Flag | Detail | Owner | Decision | Decided by | Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| APP01 | Protocols | SMBv1 server enabled | AMBER | 3 scanners connect over SMBv1 | Sysadmin | Fix during migration: firmware update | J. Doe | 2026-10-30 |
| APP01 | Protocols | FTP partner flow | AMBER | Partner drops files in \\APP01\Inbound | Sysadmin | Move to MFT | J. Doe | 2026-10-30 |
| APP01 | SQL | Job owned by a person | AMBER | Nightly export owned by DOMAIN\jsmith | DBA | Fix: change to sa | A. Roy | 2026-10-30 |

### 3.4 Server page (Loop template)

Each server has one page that brings together its status, people, links (ADO, ServiceNow, SharePoint), flags, approvals and gates.

Template: SERVER-PAGE-TEMPLATE.md (view on GitHub) · SERVER-PAGE-TEMPLATE.docx (Word copy)

Loop can't import a file, but it keeps formatting when you paste. To use the template in Microsoft Loop:

- Open the Word copy, press Ctrl+A and then Ctrl+C. Copying from the rendered GitHub page also works.

- Paste it into a new Loop page. Headings, tables and lists are kept. The checkboxes (☐) arrive as text: type [] at the start of those lines to turn them into Loop checklists.

- Save the page as a template in the bundle's Loop workspace, so each server page starts from the same layout.

———   ◆   ———

## 4. Documentation path

One place for each kind of information, and links everywhere else. If the same information is written in two places, one of them is wrong.

### 4.1 The documents

| Governance guide this page · the big picture | → | ▸ Sysadmin guide what the sysadmin owns ▸ DBA guide what the DBA owns ▸ Scripts & VS Code how scripts are written and shared ▸ Server page template one Loop page per server |
| --- | --- | --- |
| Sysadmin guide what the sysadmin owns | → | ▸ Lab evidence runbook · stability tests |
| DBA guide what the DBA owns | → | ▸ Lab evidence runbook · stability tests |
| Scripts & VS Code how scripts are written and shared | → | end |
| Server page template one Loop page per server | → | end |
| Lab evidence runbook · stability tests | → | end |

| Document | What it's for | Changes when |
| --- | --- | --- |
| Governance guide (this page) | Phases, gates, roles, rules, standards | A rule changes (decided in the retro or the blockers meeting) |
| Sysadmin guide | What the sysadmin owns and signs; Windows paths; checklists | Sysadmin practice changes |
| DBA guide | What the DBA owns and signs; SQL paths and matrix; audit; checklists | DBA practice changes |
| Scripts & VS Code | Script rules, Git, VS Code, Copilot, the path to fewer scripts | Tools or the script workflow change |
| Server page template | The layout of every server's Loop page | The information we track changes |
| Lab evidence | Proof for the lab-proven paths | After each lab test |

Word copies (for reading offline, printing, or sending): all guides in one file, with a table of contents, or one file per guide in word/. The graphics are drawn natively in Word, so they can be edited there. The Markdown files stay the source. After changing a guide, regenerate the copies from the migration-governance folder:

perl tools/md2docx.pl word/Migration-Governance.docx README.md SYSADMIN.md DBA.md SCRIPTS-AND-VSCODE.md SERVER-PAGE-TEMPLATE.md perl tools/md2docx.pl word/DBA-Guide.docx DBA.md # same for each guide

### 4.2 Where to start

| You are | Read, in this order |
| --- | --- |
| Sysadmin | This page §1–2 → Sysadmin guide → Scripts & VS Code §1–4 |
| DBA | This page §1–2 → DBA guide → Scripts & VS Code §1–4 |
| App owner | This page §1, §2.2, 1.10 Disposition, Gate 3 → your server's Loop page |
| Tech lead / PM | This whole page → the server pages of the current bundle |
| Writing or changing a script | Scripts & VS Code |

### 4.3 Where each kind of information lives

| Information | Lives in | Linked from |
| --- | --- | --- |
| Rules and how-to (these guides) | Git repository | Loop workspace home page |
| Scripts | Git repository (develop; released versions on main) | Server page (script version) |
| Raw discovery output (CSV) | SharePoint Migration/<BUNDLE>/<SERVER>/1-Discovery/ | Server page |
| Flag summary (CSV) | SharePoint, same folder | Server page, flags table |
| Status, people, dependencies, flags and decisions, approvals, gate sign-offs | Loop server page (the hub for each server) | ADO story |
| Work items: stories, tasks, sprints | Azure DevOps | Server page |
| Server requests, CAB changes, decommission requests | ServiceNow | Server page |
| Clone runbook, validation evidence | SharePoint 2-Build/, 3-Migration/ | Server page |
| Decisions that apply to the whole program | Decision log page in the Loop workspace | Blockers meeting notes |

### 4.4 What gets documented, step by step

| Scripts run | → | ▸ SharePoint output + summary |
| --- | --- | --- |
| SharePoint output + summary | → | ▸ Loop server page findings, flags, decisions |
| Loop server page findings, flags, decisions | → | ▸ Gate signed on the Loop page |
| Gate signed on the Loop page | → | ▸ Next phase |
| Next phase | → | end |
| Azure DevOps story | → | ▸ links: Loop server page findings, flags, decisions (back / optional) |
| ServiceNow tickets | → | ▸ links: Loop server page findings, flags, decisions (back / optional) |

| When | Document | Where | Who |
| --- | --- | --- | --- |
| Bundle starts | Create the server page from the template, the ADO story and the SharePoint folder; link them together | Loop, ADO, SharePoint | Tech lead |
| Discovery, day 1 | Script output and flag summary | SharePoint 1-Discovery/ | Sysadmin, DBA |
| Discovery, end of week | Key findings, confirmed dependencies, monthly jobs, flags with their decisions | Server page | Sysadmin, DBA |
| Gate 1 | Disposition; Gate 1 checklist signed; decisions in the decision log | Server page | Migration lead; app owner confirms |
| Install & test (clone if uncertain) | ServiceNow server request; the clone runbook if a clone was used (steps, timings, problems); build deviations | Server page; SharePoint 2-Build/ | Sysadmin, DBA |
| Gate 2 | Gate 2 checklist signed | Server page | Migration lead |
| Migration | CAB change and approvals; rehearsal results; cut-over plan; validation evidence | ServiceNow; server page; SharePoint 3-Migration/ | Sysadmin, DBA |
| Gate 3 | App owner's acceptance, with a link to the approval record | Server page | App owner |
| Decommissioning | ServiceNow decommission request; quiet period or scream test result; removal checklist; location of the final backup | ServiceNow; server page; SharePoint 4-Decommission/ | Sysadmin, DBA |
| Gate 4 | Gate 4 checklist signed; ADO story closed | Server page; ADO | Migration lead |

### 4.5 Keeping it current

- Update the server page the same day something changes, and set its Last updated field.

- The daily status works from the server pages. There's no separate status document.

- Decisions made in the tech discussion or the blockers meeting go into the decision log during the meeting.

- Link, don't copy: the server page links to SharePoint, ADO and ServiceNow instead of repeating their content.

- These guides change in the repository, like the scripts. Improvements usually come from the sprint retro.

———   ◆   ———

| PHASE 1 Discovery | PHASE 2 Install & configure | PHASE 3 Migration | PHASE 4 Decommissioning |
| --- | --- | --- | --- |

## Phase 1 · Discovery

Goal: know everything that runs on, connects to, or depends on the server before anything is built or moved.

Discovery is scripted, so it takes one week per server or batch of servers. The scripts collect everything on day 1. A scheduled capture records connections for the rest of the week, and the review and decisions happen at the end of the week.

Discovery in one week (scripted)

| Who | Task | Mon 02 | Tue 03 | Wed 04 | Thu 05 | Fri 06 |
| --- | --- | --- | --- | --- | --- | --- |
| Sysadmin | Server, protocol and file scripts |  |  |  |  |  |
| DBA | Instance and database scripts |  |  |  |  |  |
| Capture (scheduled) | Connections and activity every 5-15 min |  |  |  |  |  |
| Review | Flag review and decisions |  |  |  |  |  |
| Review | App owner confirms dependencies |  |  |  |  |  |
| Review | Gate 1 |  |  |  |  | ◆ |

Important A one-week capture doesn't see monthly or quarterly activity. Cover that with the schedules: - Read every scheduled task and SQL Agent job schedule, and list anything that runs monthly, quarterly or yearly. Each one gets an owner to confirm what it connects to. - Ask the app owner about month-end, quarter-end and year-end processes. - The Phase 4 quiet period (2–4 weeks, with the capture still running on the old server) is the safety net for anything missed.

### 1.1 Tooling per source version

Whichever script you use, it has to run on the server's PowerShell version. The optional reference script covers every version: its core is PowerShell 2.0 compatible, and it uses the newer cmdlets only when $PSVersionTable.PSVersion.Major -ge 3.

| Source OS | PowerShell | What this means |
| --- | --- | --- |
| 2003 | None by default (2.0 only if WMF 2.0 / KB968930 was installed) | Run discovery remotely from a modern admin box over WMI/DCOM (Get-WmiObject -ComputerName), or locally with wmic, netstat, reg query, net share and schtasks. Don't install software just to discover the server. |
| 2008 | 1.0 (feature); 2.0 via WMF | PowerShell 2.0 only: no Get-CimInstance, no ConvertTo-Json, no Get-SmbShare. Use Get-WmiObject and Export-Csv. |
| 2008 R2 | 2.0 | Same as 2008. WinRM 2.0 may need its listener configured. The default execution policy is Restricted. |
| 2012 | 3.0 | CIM and the SMB cmdlets (Get-SmbServerConfiguration, Get-SmbSession, Get-SmbOpenFile) are available. Get-ScheduledTask too. |
| 2012 R2 | 4.0 (5.1 with WMF 5.1) | Same as 2012. Remoting is on by default. |
| 2016 / 2019 | 5.1 | Full cmdlets, including the SMBv1 access audit (Set-SmbServerConfiguration -AuditSmb1Access $true). |

Tip dbatools needs a modern PowerShell. Run it from an admin workstation against every instance, never on the server itself. Most read commands work from SQL 2000 to 2019, so a single DBA script can cover the whole estate.

### 1.2 Server: platform, identity and software

| Platform | Identity and access | Software and roles |
| --- | --- | --- |
| ☐ OS, edition, SP, x86/x64, install language ☐ End-of-support date ☐ Physical or virtual, host, hardware age ☐ CPU, RAM, disks, growth, page file ☐ Activation and licensing (OEM, VL, KMS) | ☐ Domain member? Domain controller? ☐ Local accounts and local Administrators ☐ Service accounts. Is the password known and in the vault? ☐ Credentials hard-coded in .ini, .config, .udl, .bat files and net use lines | ☐ Installed software (including 16-bit installers, which don't run on x64) ☐ IIS, DHCP, DNS, print, MSMQ, COM+/DCOM, WINS ☐ Non-default services and their start mode ☐ Scheduled tasks and AT jobs (2003) ☐ ODBC DSNs, 32-bit and 64-bit ☐ .NET, Java, VB6, Access runtimes ☐ Dongles, serial or USB devices, fax boards |

▾ Commands that work on PowerShell 2.0 and on 2003

# OS, including 2003 queried remotely from a modern box Get-WmiObject Win32_OperatingSystem -ComputerName SRV01 ¦ Select-Object CSName, Caption, CSDVersion, OSArchitecture, Version, OSLanguage, InstallDate # Services that run as a named account (these need a known password on the target) Get-WmiObject Win32_Service -ComputerName SRV01 ¦ Where-Object { $_.StartName -notmatch 'LocalSystem¦LocalService¦NetworkService' } ¦ Select-Object Name, DisplayName, StartName, StartMode, State ¦ Export-Csv SRV01_services-accounts_20261022.csv -NoTypeInformation # Installed software (both registry views) 'HKLM:\SOFTWARE\Microsoft\Windows\CurrentVersion\Uninstall\*', 'HKLM:\SOFTWARE\Wow6432Node\Microsoft\Windows\CurrentVersion\Uninstall\*' ¦ ForEach-Object { Get-ItemProperty $_ -ErrorAction SilentlyContinue } ¦ Where-Object { $_.DisplayName } ¦ Select-Object DisplayName, DisplayVersion, Publisher, InstallDate ¦ Export-Csv SRV01_software_20261022.csv -NoTypeInformation

:: Scheduled tasks with run-as account and command line (2003 and later) schtasks /query /v /fo csv > SRV01_tasks_20261022.csv :: 2003 only: legacy AT jobs at

### 1.3 Server: network and dependencies

☐  IPs, subnet, gateway, DNS, WINS, extra NICs and IPs, NIC teaming

☐  DNS records and aliases (CNAMEs) that point at this server

☐  hosts and lmhosts entries

☐  Listening ports mapped to processes (netstat -ano + tasklist /svc)

☐  Inbound and outbound connections over time. The script schedules a capture every 5–15 minutes for the Discovery week. Cover monthly and quarterly jobs from the task and job schedules (see the note above).

☐  Firewall rules here and upstream, plus IP allow-lists on other systems that name this server

☐  Hard-coded IPs and UNC paths in app configs

☐  Certificates: subject, SAN, expiry, issuer, exportable private key? SHA-1 or 1024-bit keys won't be accepted on modern targets.

☐  Backup agent and last good backup; monitoring and AV agents, AV exclusions

### 1.4 Server: legacy protocols and insecure settings

These are the items most likely to break during or after migration, because modern Windows disables them or doesn't install them. Discovery documents them all. They're addressed during the migration, as set out in 2.6.

| Item | How to check | Why it matters |
| --- | --- | --- |
| SMBv1 server | 2003: only speaks SMBv1. 2008 / 2008 R2: registry HKLM\SYSTEM\CurrentControlSet\Services\LanmanServer\Parameters → SMB1 (missing = enabled). 2012+: Get-SmbServerConfiguration → EnableSMB1Protocol. Enabled by default up to 2016; not installed on a clean 2019, but kept on a 2019 upgraded in place | Plan the target as if SMBv1 can't be used. |
| SMBv1 clients | 2003 / 2008: no audit. Record net session and net file during the capture. 2012 / 2012 R2: Get-SmbSession shows the Dialect (1.x = SMBv1). 2016 / 2019: enable AuditSmb1Access and read event 3000 in Microsoft-Windows-SMBServer/Audit. Then identify each client: XP, 2003, scanners and MFPs, NAS, embedded devices, old Samba | These clients can't reach a modern file server. Each needs an upgrade, firmware, or a decision. |
| SMBv1 as a client | 2008 / 2008 R2: HKLM\SYSTEM\CurrentControlSet\Services\mrxsmb10 → Start. 2012+: same, or the SMB1Protocol feature state | The app may pull files from an old NAS or device that only speaks SMBv1. |
| FTP server | IIS 6 FTP (MSFTPSVC, 2003). IIS 7.5–10 FTP (FTPSVC, 2008 R2–2019, logs in %SystemDrive%\inetpub\logs\LogFiles\FTPSVC*). FileZilla, Serv-U, WS_FTP. Check services, listeners on 21 or other ports, and site config, especially FTP roots and virtual directories that point to file shares | Clear-text passwords, anonymous access, partners or devices that drop files. For each flow, record who connects (from the logs), where the files land, and what processes them. Each flow is moved to MFT. |
| FTP clients | Scheduled tasks and scripts that call ftp.exe -s:<file>, WinSCP or curl. Read the -s: file for the host and credentials | Hidden outbound dependencies with stored passwords. Each one becomes an MFT flow. |
| TLS / SSL | HKLM\SYSTEM\CurrentControlSet\Control\SecurityProviders\SCHANNEL\Protocols. 2003: no TLS 1.1 or 1.2. 2008 R2: TLS 1.1/1.2 only if enabled. 2012–2019: TLS 1.2 is available, but TLS 1.0 and 1.1 are still on by default. Check .NET SchUseStrongCrypto too | Partners and clients that only speak SSL3 or TLS 1.0 will fail against a hardened target. |
| NTLMv1 / LM | HKLM\SYSTEM\CurrentControlSet\Control\Lsa → LmCompatibilityLevel, NoLMHash | Old apps and devices fail against hardened targets. |
| Telnet, rsh, SNMP v1/v2 | Services, listeners, SNMP community strings | Documented; replaced by SSH or SNMPv3 during the migration. |
| Other legacy items | WINS, NetBIOS name use, 8.3 short names, subst drives, mapped drives in a service context | These usually appear only after cut-over. |

▾ Commands: SMBv1, FTP, sessions

# SMBv1 server on 2008/2008 R2 (no value = enabled) Get-ItemProperty 'HKLM:\SYSTEM\CurrentControlSet\Services\LanmanServer\Parameters' ¦ Select-Object SMB1, SMB2 # SMBv1 client driver (4 = disabled) (Get-ItemProperty 'HKLM:\SYSTEM\CurrentControlSet\Services\mrxsmb10').Start # FTP services present? Get-Service MSFTPSVC, FTPSVC, 'FileZilla Server' -ErrorAction SilentlyContinue # 2012+: SMB sessions with dialect (1.x = SMBv1 client) Get-SmbSession ¦ Select-Object ClientComputerName, ClientUserName, Dialect, NumOpens # 2016 / 2019: audit SMBv1 access for the capture week, then read event 3000 Set-SmbServerConfiguration -AuditSmb1Access $true -Force Get-WinEvent -LogName 'Microsoft-Windows-SMBServer/Audit' -ErrorAction SilentlyContinue ¦ Where-Object { $_.Id -eq 3000 } ¦ Select-Object TimeCreated, Message # Scripts that drive ftp.exe with a command file (often holding a password) Get-ChildItem C:\, D:\ -Recurse -Include *.bat, *.cmd, *.vbs, *.ps1 -ErrorAction SilentlyContinue ¦ Select-String -Pattern 'ftp(\.exe)?\s.*-s:' ¦ Select-Object Path, LineNumber, Line

:: Who is connected to shares right now (schedule this during the capture period) net session >> SRV01_sessions_capture.txt net file >> SRV01_openfiles_capture.txt

### 1.5 Server: files, shares and unused data

Important Discovery only reports. The app owner or data owner decides what to archive or delete. That happens in Phase 4, never during Discovery.

☐  Every share: path, share and NTFS permissions, size, file count

☐  FTP data on file shares: inbound and outbound folders, archive folders, and the jobs that pick files up or clean them. These move with the flow to MFT, not with the file share.

☐  Data grouped by last-modified age: < 1 year · 1–3 years · 3–7 years · > 7 years

☐  Home or user folders of disabled or deleted AD accounts

☐  File types that carry risk or hide dependencies:

| Type | Why |
| --- | --- |
| .mdb .accdb | Access databases, often with linked tables pointing to SQL or ODBC DSNs |
| .xls* | External data connections to SQL or ODBC |
| .pst .ost | Mail archives; owner and retention questions |
| .bak .trn .mdf .ldf | Stray SQL files outside the instance |
| .bat .cmd .vbs .ps1 | Scripts with paths, servers and credentials |
| .iso .vhd installers | Large files, rarely needed |

☐  Duplicate and very large files

☐  Open files and sessions during the capture, to see which shares are actually used

☐  Data on local drives that isn't in any share (app data, exports, logs)

☐  Retention or legal holds. Ask the data owner; old doesn't automatically mean deletable.

Caution Don't use LastAccessTime. On 2008 to 2016 it isn't updated by default, and on 2019 it's "system managed", which depends on volume size (fsutil behavior query disablelastaccess). On 2003 it is updated, but antivirus and backup scans touch it too. Use LastWriteTime, together with the session and open-file capture.

▾ Command: data by age, PowerShell 2.0 compatible

$root = 'D:\Shares' $now = Get-Date Get-ChildItem $root -Recurse -ErrorAction SilentlyContinue ¦ Where-Object { -not $_.PSIsContainer } ¦ ForEach-Object { $age = ($now - $_.LastWriteTime).Days / 365 $bucket = if ($age -lt 1) {'<1y'} elseif ($age -lt 3) {'1-3y'} elseif ($age -lt 7) {'3-7y'} else {'>7y'} New-Object PSObject -Property @{ Bucket = $bucket; Bytes = $_.Length; Ext = $_.Extension.ToLower() } } ¦ Group-Object Bucket ¦ Select-Object Name, Count, @{n='GB'; e={ [math]::Round(($_.Group ¦ Measure-Object Bytes -Sum).Sum / 1GB, 2) }} ¦ Export-Csv SRV01_file-age_20261022.csv -NoTypeInformation

### 1.6 SQL: instance

| Version and support | Security | Features in use |
| --- | --- | --- |
| ☐ Version, edition, SP/CU, x86/x64 ☐ Instance name, port (static or dynamic), Browser ☐ Server collation, and databases with a different collation ☐ Service accounts, SPNs, delegation ☐ Memory, MAXDOP, non-default sp_configure settings, trace flags ☐ Startup parameters and tempdb layout | ☐ Logins (SQL and Windows), server roles, sa state ☐ SQL logins with weak or blank passwords (SQL 2000 has no password policy) ☐ Orphaned users per database ☐ TDE, certificates, master keys, credentials, proxies. Are the keys backed up? ☐ Forced encryption and its certificate | ☐ Agent jobs: owner, schedule, steps, what they touch outside SQL ☐ Operators, alerts, Database Mail, SQL Mail (removed after 2008 R2) ☐ Maintenance plans (2000/2005 plans don't migrate) ☐ DTS packages (2000). Not supported on 2012+, so they need a rewrite to SSIS ☐ SSIS, SSRS reports and subscriptions, SSAS ☐ Linked servers, OPENROWSET / OPENQUERY ☐ Replication, log shipping, mirroring, clustering, Always On AGs (2012+) ☐ CLR, extended procedures, xp_cmdshell ☐ Cross-database and cross-server names ☐ 2016–2019 features removed or deprecated in 2022: Stretch Database, R/Python ML Services (not installed by setup), PolyBase Hadoop, Distributed Replay ☐ Query Store, Master Data Services, Data Quality Services, Power BI Report Server |

Which restore paths work. Plan the number of hops now:

| SQL 2000 compat 80 | → | ▸ restore: Hop instance SQL 2008 R2 |
| --- | --- | --- |
| Hop instance SQL 2008 R2 | → | ▸ restore: SQL 2022 / 2025 |
| SQL 2022 / 2025 | → | end |
| SQL 2005 compat 90 | → | ▸ restore (auto compat 100): SQL 2022 / 2025 |
| SQL 2008 – 2019 | → | ▸ restore, log shipping or in-place upgrade: SQL 2022 / 2025 |

Only SQL 2000 needs an intermediate hop. Databases from SQL 2005 (compatibility level 90) and later restore directly on SQL 2022 and 2025; 2005 databases are raised to level 100 automatically (Microsoft, Supported version and edition upgrades for 2022 and 2025). Per-version paths, in-place upgrade limits and the SQL × Windows matrix are in the DBA guide.

Warning A restore upgrades the database to the target version, one way. A backup taken on the target can't be restored on the source. The rollback is always the untouched source, never a backup from the new server.

### 1.7 SQL: databases

☐  Name, size (data and log), growth, file locations, owner

☐  Compatibility level, recovery model

☐  Page verify: SQL 2000 databases are often TORN_PAGE_DETECTION or NONE. Plan CHECKSUM after migration.

☐  Last good DBCC CHECKDB. Run one before migration so you know whether corruption was already there.

☐  Backups: target, frequency, last good one, and the RPO/RTO agreed with the app owner

☐  Is it used? See 1.8

☐  Applications and connection strings that use it, from the capture, not from memory

### 1.8 SQL: activity and auditing per version

Old versions can't tell you who uses a database the way newer ones can. SQL Server Audit doesn't exist before 2008, it's Enterprise-only on 2008 / 2008 R2, and database-level audit reaches every edition only from 2016 SP1. Use what each version offers, schedule the capture for the Discovery week, and read the Agent job schedules to cover monthly activity.

| Version | Who connects | Is the database used | Who changes what |
| --- | --- | --- | --- |
| SQL 2000 | Snapshot master..sysprocesses every 5–15 min | No usage DMVs. Use a light server-side trace (login, batch completed, filtered) | Server-side trace. C2 audit mode only as a last resort: it's heavy and stops the instance if the disk fills |
| SQL 2005 | Snapshot sys.dm_exec_sessions + sys.dm_exec_connections (client IP) | sys.dm_db_index_usage_stats. It resets on restart: check uptime via tempdb create_date | Default trace (rolls over fast: 5 × 20 MB), DDL triggers, logon triggers (SP2+) |
| SQL 2008 / R2 | Same as 2005 | Same, plus sys.dm_os_sys_info.sqlserver_start_time | SQL Server Audit on Enterprise; otherwise the 2005 methods |
| SQL 2012 / 2014 | sys.dm_exec_sessions now has database_id | Same as 2008 | Server-level audit on every edition; database-level audit on Enterprise only. Extended Events |
| SQL 2016 – 2019 | Same as 2012 | Same, plus Query Store (per-database query history, if enabled) | Server- and database-level audit on every edition (2016 SP1+). Extended Events |

▾ T-SQL: connection snapshots and usage, per version

-- SQL 2000: who is connected (schedule every 5–15 min, insert into a capture table) SELECT GETDATE() AS captured_at, spid, RTRIM(hostname) AS host, RTRIM(program_name) AS program, RTRIM(loginame) AS login, DB_NAME(dbid) AS db FROM master..sysprocesses WHERE spid > 50;

-- SQL 2005 / 2008: who is connected, with client IP SELECT GETDATE() AS captured_at, c.client_net_address, s.host_name, s.program_name, s.login_name, DB_NAME(p.dbid) AS db FROM sys.dm_exec_sessions AS s JOIN sys.dm_exec_connections AS c ON c.session_id = s.session_id JOIN sys.sysprocesses AS p ON p.spid = s.session_id WHERE s.is_user_process = 1;

-- SQL 2012 – 2019: who is connected, with client IP and current database SELECT GETDATE() AS captured_at, c.client_net_address, s.host_name, s.program_name, s.login_name, DB_NAME(s.database_id) AS db FROM sys.dm_exec_sessions AS s JOIN sys.dm_exec_connections AS c ON c.session_id = s.session_id WHERE s.is_user_process = 1;

-- SQL 2005 – 2019: last read and write per database since the service started -- (on 2008+ you can also use sys.dm_os_sys_info.sqlserver_start_time) SELECT create_date AS sql_started FROM sys.databases WHERE name = 'tempdb'; SELECT DB_NAME(database_id) AS db, MAX(last_user_seek) AS last_seek, MAX(last_user_scan) AS last_scan, MAX(last_user_lookup) AS last_lookup, MAX(last_user_update) AS last_update FROM sys.dm_db_index_usage_stats GROUP BY database_id;

-- All versions: jobs owned by a person, orphaned users SELECT j.name, SUSER_SNAME(j.owner_sid) AS owner FROM msdb.dbo.sysjobs AS j; EXEC sp_change_users_login 'Report'; -- run in each user database -- All versions: jobs that run monthly or less often (the week's capture won't see them) -- freq_type 16 = monthly, 32 = monthly relative SELECT j.name, s.name AS schedule, s.freq_type, s.freq_interval, s.active_start_time FROM msdb.dbo.sysjobs AS j JOIN msdb.dbo.sysjobschedules AS js ON js.job_id = j.job_id JOIN msdb.dbo.sysschedules AS s ON s.schedule_id = js.schedule_id WHERE s.freq_type IN (16, 32);

☐  Turn on login auditing ("both failed and successful logins") for the capture week. It writes to the errorlog, so check the errorlog size and recycle schedule. Audit options for each version, including versions without SQL Server Audit: DBA guide §7.

☐  A database with no reads or writes during the capture, no monthly job touching it, and a long uptime behind the usage stats is a candidate for archiving. The app owner decides.

☐  Hand the compiled host · app · login · database list to the app owner to confirm.

### 1.9 Red and amber flags

| RED: blocks migration until decided | AMBER: needs a plan |
| --- | --- |
| - Unsupported source → target path (e.g. SQL 2000 → 2019 direct) - DTS packages, 16-bit apps, hardware dongles - SMBv1 or NTLMv1 client that can't be upgraded (needs an exception) - Clear-text credentials in scripts - TDE or encryption keys not backed up - No backup, or last good backup older than 7 days - Unknown inbound connections after the capture | - FTP flow to move to MFT - SMBv1, TLS 1.0/1.1 or NTLMv1 in use (fixed during the migration) - Certificate expiring within 90 days - Job or database owned by a personal account - Data older than 7 years with no owner - Service account password unknown - No CHECKSUM page verify, no recent CHECKDB - Dynamic SQL port, hard-coded IPs - Database with no activity during the capture |

### 1.10 Disposition: migrate, consolidate or retire

Discovery often shows that a server, or some of its databases and shares, no longer needs to move. Decide this before building anything.

| Disposition | Typical evidence from Discovery | Next phase |
| --- | --- | --- |
| Migrate | Active users and connections, the app is still needed | Phase 2 |
| Consolidate | Light workload that fits on an existing supported server or instance | Phase 3 (target already exists) |
| Retire | No meaningful connections, no scheduled jobs that matter, the app is replaced or no longer used | Phase 4, retire-only path |

A server can also be split: for example, migrate two databases and retire the rest. Record each part's disposition in the decision log.

What each role does for each option, including the evidence that a server or database isn't used and the in-place upgrade step by step: Sysadmin guide §6 · DBA guide §6.

Important Retire is a business decision. The app owner is accountable, and has to confirm in writing that the service is no longer needed and what happens to its data. The sysadmin and DBA provide the evidence.

### Gate 1 · Discovery complete

☐  Server and SQL scripts ran from the approved repository version (version recorded in the summary)

☐  Capture ran for the Discovery week, and every monthly, quarterly or yearly task or job has an owner who confirmed what it connects to

☐  Output is in Migration/<BUNDLE>/<SERVER>/1-Discovery/ with standard names

☐  Summary reviewed by the sysadmin ______ and the DBA ______ on ______

☐  Every RED flag has an owner and a logged decision

☐  App owner has confirmed the dependencies and the unused-data candidates

☐  Disposition recorded for the server (and for each database or share, if split): migrate · consolidate · retire

☐  If migrating: target platform and path chosen (OS and SQL versions, number of hops, in-place or side-by-side)

☐  If retiring: app owner's written confirmation that the service is no longer needed, plus a decision on the data

☐  Migration lead sign-off: ______ on ______

———   ◆   ———

| PHASE 1 Discovery | PHASE 2 Install & configure | PHASE 3 Migration | PHASE 4 Decommissioning |
| --- | --- | --- | --- |

## Phase 2 · Install & configure

Goal: a target that is built to standard, hardened, and ready, with every prerequisite that Discovery found already in place.

| Sysadmin: server | DBA: SQL |
| --- | --- |
| ☐ Built from the standard image or build, on a supported OS ☐ Patched, and joined to the correct OU (GPOs applied) ☐ Disk layout to standard (OS · apps · data · logs · tempdb · backups) ☐ Service accounts created, or gMSAs where the app supports them; passwords in the vault ☐ Roles and features from Discovery installed (IIS, .NET 3.5, MSMQ, …) ☐ SMBv1 off, TLS 1.2+ only, NTLMv1 refused. Exceptions only as logged in the decision log ☐ MFT flows set up for every FTP flow found in Discovery (accounts, folders, partner keys or certificates) ☐ Certificates issued (SHA-256, 2048-bit+), private keys exportable per policy ☐ Backup, monitoring, AV (with exclusions) and logging agents installed ☐ Scheduled tasks prepared but disabled | ☐ Supported version and edition, latest CU ☐ Collation matches the source (or a documented change) ☐ Service accounts, SPNs, static port, firewall rule ☐ Memory, MAXDOP, cost threshold, tempdb files to standard ☐ Backups, integrity checks and index maintenance jobs (standard solution, not legacy maintenance plans) ☐ Database Mail, operators and alerts configured ☐ Logins scripted from the source (SIDs and hashes kept) but not yet enabled for apps ☐ SSIS / SSRS installed if Discovery found them; DTS rewrite tracked ☐ Linked servers recreated with non-personal credentials ☐ Auditing enabled with SQL Server Audit (server level on all editions from 2012; database level from 2016 SP1). Standard setup: DBA guide §7 |

### Gate 2 · Target ready

☐  Build checklist complete, with deviations recorded in the decision log

☐  Security / network: firewall rules, certificates and exceptions done and signed

☐  Backup of the empty target tested (restore proven)

☐  Monitoring is green

☐  Smoke test passed (app installs and starts, connects to an empty or test database)

☐  Migration lead sign-off: ______ on ______

———   ◆   ———

| PHASE 1 Discovery | PHASE 2 Install & configure | PHASE 3 Migration | PHASE 4 Decommissioning |
| --- | --- | --- | --- |

## Phase 3 · Migration

Goal: data, apps and dependencies move once, in a rehearsed and timed window, with a rollback that has been tested.

### 3.1 Choose the method

In-place upgrade first, whenever a path exists. Side-by-side second. A path that's uncertain runs on a cloned VM first (when to clone). The sysadmin does the OS in-place upgrade; the DBA takes over at the OS hand-off (2.2).

| In-place path exists? (OS and SQL) | → | ▸ yes: Path uncertain? ▸ no: 2nd choice Side-by-side |
| --- | --- | --- |
| Path uncertain? | → | ▸ no (proven): 1st choice In-place on production snapshot per step + hardening ▸ yes: Run it on a cloned VM |
| 1st choice In-place on production snapshot per step + hardening | → | end |
| Run it on a cloned VM | → | ▸ Clone test passes? |
| Clone test passes? | → | ▸ yes: 1st choice In-place on production snapshot per step + hardening ▸ no, can't be fixed: 2nd choice Side-by-side |
| 2nd choice Side-by-side | → | end |

| Order | Method | When to use | Watch out for |
| --- | --- | --- | --- |
| 1 | In-place OS upgrade | Whenever a path exists. 2008 R2 SP1 → 2012 R2 → 2025: works, not supported, LAB OK. 2012 R2 → 2016, 2019 or 2025 (not 2022). 2016, 2019 → 2022 or 2025 (Sysadmin guide §5) | Each hop needs a licence and a snapshot. It keeps old settings, so harden after the last hop: SMBv1 off, TLS 1.2+, NTLMv1 refused (2.6) |
| 1 | In-place SQL upgrade | Whenever a supported path exists: to 2022 from 2012 SP4, 2014 SP3, 2016 SP3, 2017, 2019; to 2025 from 2014 SP3 onwards. The OS must support the target SQL (DBA guide §5) | Rollback = the VM snapshot taken just before |
| 2 | Side-by-side (new server, move app and data) | No in-place path (2003, SQL 2000, an OS and SQL pair that can't be reached), or the clone test failed | DNS and aliases, IP allow-lists, hard-coded names |

Moving the data in a side-by-side, or into a new SQL instance:

| Method | When to use | Watch out for |
| --- | --- | --- |
| Backup / restore (SQL) | Most databases; downtime equals the restore time | Restore-version hops (see 1.6); orphaned users |
| Log shipping or differential catch-up (SQL) | Large databases with a short window | The target must be able to restore the source version |
| Detach / attach | Rarely; when backup and restore is too slow | No rollback once upgraded; keep a copy |
| Robocopy (files) | File shares | /COPYALL, a preliminary pass plus a final delta, long paths |

### 3.2 Runbook

| Rehearsal (timed; on a clone if uncertain) | → | ▸ Cut-over plan + rollback plan approved |
| --- | --- | --- |
| Cut-over plan + rollback plan approved | → | ▸ Freeze and final backup |
| Freeze and final backup | → | ▸ Move data and apps |
| Move data and apps | → | ▸ Switch DNS, aliases, jobs |
| Switch DNS, aliases, jobs | → | ▸ Validate (IT, then app owner) |
| Validate (IT, then app owner) | → | ▸ fails: Rollback (source is still intact) ▸ passes: Gate 3 |
| Rollback (source is still intact) | → | end |
| Gate 3 | → | end |

☐  Rehearsal, timed: on a cloned VM if the path is uncertain (when to clone), otherwise a dry run of the steps on a test server. The real window = rehearsal time + 50%.

☐  Rollback plan with a clear point of no return and who calls it

☐  Users and app owner notified; change ticket approved

☐  Source set to read-only (or services stopped) before the final copy, so no writes are lost

☐  Logins fixed (orphaned users), jobs enabled, linked servers tested

☐  Compatibility level raised after validation, not during cut-over

☐  CHECKSUM page verify set; DBCC CHECKDB on the target

☐  Row counts and checksums compared for key tables

☐  DNS and aliases switched; old name kept as a CNAME if the app needs it

☐  Every dependency from Discovery tested: scanners, MFT flows and partners, reports, interfaces

☐  Every legacy-protocol flag from Discovery is closed, or covered by a logged exception with an end date

☐  FTP service on the old server stopped once its flows run on MFT

### Gate 3 · Accepted

☐  Validation evidence stored in 3-Migration/

☐  All Discovery dependencies tested and marked OK

☐  First backup on the target, and a restore tested

☐  Monitoring green for 48 h

☐  App owner acceptance: ______ on ______

———   ◆   ———

| PHASE 1 Discovery | PHASE 2 Install & configure | PHASE 3 Migration | PHASE 4 Decommissioning |
| --- | --- | --- | --- |

## Phase 4 · Decommissioning

Goal: the old server is retired cleanly and reversibly until the wait period ends, and leaves nothing behind in any system.

| Quiet period 2–4 weeks monitor connections | → | Power off (don't delete) 2–4 weeks | → | Final backup kept per retention | → | Remove from every system | → | Gate 4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

☐  Quiet period: keep the connection capture running on the old server, and make sure it covers a month-end. It's the safety net for the one-week Discovery: any hit is a missed dependency, so fix it before you continue.

☐  Unused-data decisions from Discovery carried out: archive, move or delete, signed by the data owner

☐  SQL: databases set offline first, then a final backup; logins disabled

☐  Server powered off, not deleted, for the agreed wait

☐  Final full backup (server + databases) kept per retention policy, with a restore test

### Retire-only path

Use this path for a server whose disposition at Gate 1 was retire. There is no new server and no Gate 3, so nothing has been tested in practice yet. The scream test takes the place of that validation.

| Gate 1 disposition: RETIRE | → | ▸ Announce date + contact |
| --- | --- | --- |
| Announce date + contact | → | ▸ Data decision carried out (archive or hand over) |
| Data decision carried out (archive or hand over) | → | ▸ Scream test disable, don't delete covers a month-end |
| Scream test disable, don't delete covers a month-end | → | ▸ Anyone affected? |
| Anyone affected? | → | ▸ yes: Re-enable, back to Gate 1 (new disposition) ▸ no: Power off, final backup, removal checklist |
| Re-enable, back to Gate 1 (new disposition) | → | end |
| Power off, final backup, removal checklist | → | ▸ Gate 4 |
| Gate 4 | → | end |

☐  Announce the retirement date and a contact to users and dependent teams (as found in Discovery)

☐  Data: what the app owner decided is carried out first: archived to the agreed location, handed over, or deleted under the retention policy. A last full backup is taken before anything is deleted.

☐  SQL: each database is set offline, not dropped, so it can come back in minutes

☐  Scream test: disable the service in a way that can be undone in minutes (stop the services, disable the NIC, or shut down the VM). Keep it disabled for at least 4 weeks, including a month-end, with the change ticket and contact visible.

☐  If someone is affected: re-enable the server, record the missed dependency, and go back to Gate 1 with a new disposition

☐  If nobody is affected: continue with the final backup and the removal checklist below

Removal checklist:

| ☐ Active Directory computer object ☐ DNS A, PTR and CNAME records ☐ DHCP reservations ☐ Firewall rules and allow-lists | ☐ Monitoring ☐ Backup jobs ☐ Antivirus / EDR console ☐ Patch management (WSUS, SCCM) | ☐ CMDB / inventory ☐ Licences reclaimed (OS, SQL, CALs) ☐ Service accounts disabled, then deleted ☐ Certificates revoked |
| --- | --- | --- |

### Gate 4 · Retired

☐  No connections seen during the quiet period, or no one affected during the scream test (retire-only path)

☐  Retire-only: data decision carried out and confirmed by the app owner

☐  Final backup kept, with the restore test recorded

☐  Removal checklist complete

☐  VM or hardware deleted or disposed of per policy (disks wiped)

☐  Migration lead sign-off: ______ on ______

———   ◆   ———

## Appendix

### A. Decision log template

| ID | Date | Server | Flag / topic | Decision (fix · accept · blocker) | Rationale | Owner | End date (for an accept) | Signed by |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D-001 |  |  |  |  |  |  |  |  |

### B. Gate sign-off template (on the server's Loop page)

SERVER: APP01 PHASE: 1 - Discovery GATE OWNER: <name> [x] Scripts from approved version .......... v1.4 (commit 3f2a91c) [x] Capture period ......................... 2026-11-02 -> 2026-11-06 [x] Monthly/quarterly jobs confirmed ....... 4 tasks, 2 Agent jobs - owners listed [x] Summary reviewed ....................... sysadmin <name> / DBA <name> - 2026-11-05 [x] RED flags decided ...................... D-014, D-015, D-016 [x] Dependencies confirmed by app owner .... <name> - 2026-11-06 SIGNED: <name> DATE: 2026-11-06

### C. Glossary

| Term | Meaning |
| --- | --- |
| Gate | A signed checkpoint between two phases |
| RACI | Responsible, Accountable, Consulted, Informed |
| Capture | Recording connections or activity at regular intervals (every 5–15 min for the Discovery week), not a single snapshot |
| Flag | A finding that needs a decision (RED) or a plan (AMBER) |
| Quiet period | Time after cut-over when the old server stays up and is watched for missed dependencies |
| Hop | An intermediate version needed because the source can't go straight to the target |
| MFT | Managed file transfer: the central platform that replaces FTP flows, with secure protocols, logging and alerting |
| Bundle | A group of servers discovered and migrated together; the top folder level in the migration storage |
| Disposition | The Gate 1 decision for a server or part of one: migrate, consolidate or retire |
| Scream test | Disabling a server that's being retired, in a way that can be quickly undone, to find out whether anyone still depends on it |

———   ◆   ———

Migration governance · maintained by the Migration lead · change this guide through a reviewed change in the repository, like the scripts