MIGRATION GOVERNANCE · GLOBAL DOCUMENT # Migration Governance Governance guide · Sysadmin guide · DBA guide · Scripts & VS Code · Server page template ● Discovery — ● Install & configure — ● Migration — ● Decommissioning

Contents

Right-click here and choose Update Field to build the table of contents.

Exported 2026-10-23 from the migration-governance folder of the repository. The repository is the source; this file is a snapshot.

OPERATIONS HANDBOOK · SYSADMIN & DBA # Migration Governance Windows Server 2003 – 2019 · SQL Server 2000 – 2019 ● DISCOVERY — ● INSTALL & CONFIGURE — ● MIGRATION — ● DECOMMISSIONING

Living document · owner: Migration lead · review every quarter, or after every gate that found a gap in this guide

Important Three rules apply to everything below. - No gate, no next phase. A phase is complete only when its gate checklist is signed. - One accountable person per activity. Many people can do the work; one person owns the result. - Collected data is reviewed. Every output has a reviewer's name and a date.

———   ◆   ———

## 1. Purpose and scope

This guide sets out who does what, what to collect, what to decide, and when a phase is done when legacy Windows servers and SQL Server instances move to supported platforms. It builds on the discovery work and documentation teams already have, and organises them into checklists, owners and gates.

|  | In scope | Out of scope |
| --- | --- | --- |
| Platforms | Windows Server 2003, 2008, 2008 R2, 2012, 2012 R2, 2016, 2019 | Desktop and endpoint migration |
| Databases | SQL Server 2000, 2005, 2008, 2008 R2, 2012, 2014, 2016, 2017, 2019 (instances, databases, jobs, packages) | Application code changes (tracked by the app team) |
| Services | File shares, FTP, IIS, scheduled jobs, print, legacy protocols | Network redesign and firewall policy (consulted, not owned) |
| Data | Live data, unused or stale data, backups, retention | Records-management policy (owned by the data owner) |

### Support status: what to migrate first

Microsoft extended support end dates. Anything already out of support goes first, starting with the oldest.

| Windows Server | SQL Server |
| --- | --- |
| ¦ Version ¦ Extended support ended / ends ¦ ¦---¦---¦ ¦ 2003 ¦ 2015-07-14 · out ¦ ¦ 2008 / 2008 R2 ¦ 2020-01-14 · out ¦ ¦ 2012 / 2012 R2 ¦ 2023-10-10 · out ¦ ¦ 2016 ¦ 2027-01-12 · within 3 months ¦ ¦ 2019 ¦ 2029-01-09 ¦ | ¦ Version ¦ Extended support ended / ends ¦ ¦---¦---¦ ¦ 2000 ¦ 2013-04-09 · out ¦ ¦ 2005 ¦ 2016-04-12 · out ¦ ¦ 2008 / 2008 R2 ¦ 2019-07-09 · out ¦ ¦ 2012 ¦ 2022-07-12 · out ¦ ¦ 2014 ¦ 2024-07-09 · out ¦ ¦ 2016 ¦ 2026-07-14 · out ¦ ¦ 2017 ¦ 2027-10-12 ¦ ¦ 2019 ¦ 2030-01-08 ¦ |

Note Servers and instances on extended security updates (ESU) or Azure-hosted extensions still count as out of support for planning purposes.

### What this guide brings

Migrations at this scale involve many teams, many servers and a lot of collected data. This guide gives everyone the same reference points:

| Topic | What the guide provides |
| --- | --- |
| Scripts | A shared, versioned set of discovery scripts per role, which everyone can improve |
| Collected data | A short flag summary for each server, so the key findings are easy to review and act on |
| Process | Checklists with owners and exit criteria for each phase |
| Decisions | A RACI per phase and a decision log, so it's clear who decides and what was decided |
| Hand-offs | Signed gates between phases, so each team knows when it can start |

———   ◆   ———

## 2. Governance model

### 2.1 Lifecycle and gates

| 1 · Discovery know the current state | → | ▸ Gate 1 Migration lead |
| --- | --- | --- |
| Gate 1 Migration lead | → | ▸ 2 · Install & configure build the target ▸ RED flag open: 1 · Discovery know the current state (back / optional) ▸ RETIRE (no migration): 4 · Decommissioning quiet period, retire |
| 2 · Install & configure build the target | → | ▸ Gate 2 Migration lead |
| Gate 2 Migration lead | → | ▸ 3 · Migration rehearse, cut over, validate |
| 3 · Migration rehearse, cut over, validate | → | ▸ Gate 3 App owner |
| Gate 3 App owner | → | ▸ 4 · Decommissioning quiet period, retire ▸ rollback: 3 · Migration rehearse, cut over, validate (back / optional) |
| 4 · Decommissioning quiet period, retire | → | ▸ Gate 4 Migration lead |
| Gate 4 Migration lead | → | end |

Gate 1 records one disposition for each server: migrate (Phases 2 → 3 → 4), consolidate (move its workload onto an existing server, then Phases 3 → 4), or retire (straight to Phase 4, see Retire-only path).

| # | Phase | Ends when | Gate owner | Typical duration |
| --- | --- | --- | --- | --- |
| 1 | Discovery | The current state is known and reviewed, and every red flag has a decision | Migration lead | 1 week (scripted collection + 4-day capture + review) |
| 2 | Install & configure | The target is built to standard, hardened and smoke-tested | Migration lead | 1–2 weeks |
| 3 | Migration | A rehearsal is done, cut-over is complete, data is validated and the app owner has accepted | App owner | 1–3 weeks |
| 4 | Decommissioning | Quiet period with no connections, final backup taken, server removed everywhere | Migration lead | 4–8 weeks (mostly waiting) |

### 2.2 Roles

This guide is the big picture. Sysadmins and DBAs work together, but each role has its own guide, setting out what it signs for at each gate and what it needs from the other:

| Sysadmin guide Server, OS, files, network, protocols · Windows in-place paths | DBA guide Instance, databases, data · SQL × Windows matrix · migration paths |
| --- | --- |

| Role | Owns | Typical person |
| --- | --- | --- |
| Sysadmin (guide) | Everything around SQL: OS, server, files, network and security discovery; target server build; OS-level cut-over; decommissioning the server | Windows team |
| DBA (guide) | Everything inside the instance: instance and database discovery; SQL build; data migration and validation; decommissioning the instance | DBA team |

Hand-off points between sysadmin and DBA:

| Discovery sysadmin + DBA in parallel | → | Gate 1 path agreed | → | OS in-place upgrade + hardening owned by the sysadmin | → | OS hand-off sysadmin → DBA | → | SQL to a newer version + data validation owned by the DBA | → |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Gate 3 app owner | → | Decommissioning DBA: databases offline → sysadmin: removal |
| --- | --- | --- |

| Hand-off | From → to | What's handed over | From then on |
| --- | --- | --- | --- |
| 1. After Discovery (Gate 1) | Both → both | Both summaries reviewed together; OS path and SQL path agreed; who does what, and when | The sysadmin plans the OS work; the DBA plans the SQL work |
| 2. OS hand-off | Sysadmin → DBA | OS upgraded and hardened; activation, RDP, network and agents checked; SQL services start; snapshots kept | The DBA is responsible for the server's migration: SQL upgrade or new instance, data validation, app test with the app owner, up to Gate 3 |
| 3. Before decommissioning | DBA → sysadmin | Databases offline, final backups kept, instance stopped | The sysadmin powers off and removes the server |
| App owner | Dependencies, users, business windows, testing, acceptance, decisions about unused data | Business or application team |  |
| Migration lead | Plan, tracking, decision log, gate sign-off (except Gate 3), escalation | Project or team lead |  |
| Security / network | Firewall rules, exceptions for legacy protocols, certificates, risk acceptance | Security and network teams |  |

### 2.3 RACI for all phases

R does the work · A owns the result (exactly one per row) · C consulted · I informed

| Activity | Sysadmin | DBA | App owner | Migration lead | Sec / Net |
| --- | --- | --- | --- | --- | --- |
| Phase 1: Discovery |  |  |  |  |  |
| Run the server discovery script | R/A | I |  | I |  |
| Run the SQL discovery script | C | R/A |  | I |  |
| Scheduled connection capture (during the week) | R | R | I | A |  |
| Discover files, shares and unused data | R |  | C | A |  |
| Discover legacy protocols (SMBv1, FTP, TLS, NTLMv1) | R | C | I | A | C |
| Confirm the dependency list | R | R | A | C |  |
| Review output and decide on flags | R | R | C | A | C |
| Decide the disposition (migrate · consolidate · retire) | C | C | A | R | I |
| Phase 2: Install & configure |  |  |  |  |  |
| Build and harden the target OS | R/A | I |  | I | C |
| Install and configure SQL | C | R/A |  | I |  |
| Firewall rules, certificates, legacy-protocol exceptions | C | C | I | I | R/A |
| Smoke test of the target | R | R | C | A |  |
| Phase 3: Migration |  |  |  |  |  |
| Rehearsal migration (on a clone if the path is uncertain) | R | R | C | A |  |
| Cut-over and rollback plan | R | R | C | A | C |
| OS in-place upgrade and hardening, up to the OS hand-off | R/A | C | I | I | C |
| Everything SQL after the OS hand-off: SQL upgrade or new instance, data migration and validation | C | R/A | C | I |  |
| Application testing and acceptance | C | C | R/A | I |  |
| Phase 4: Decommissioning |  |  |  |  |  |
| Quiet-period monitoring | R | R | I | A |  |
| Archiving or deleting unused data | R | R | A | C |  |
| Server and instance removal from every system | R | R | I | A | C |

Note The Gate 3 sign-off belongs to the app owner, not IT. IT says the migration is technically complete; only the business can say it works.

### 2.4 Cadence

Governance uses the existing meetings; it doesn't add new ones. Each meeting has a defined migration role:

| Meeting | When | Who | Migration topics | Output |
| --- | --- | --- | --- | --- |
| Daily status | Mon–Fri, 15 min | Sysadmins, DBAs, tech lead | Per-server progress, new RED flags (owner assigned on the spot), what's ready for a gate | Updated board, flag owners |
| Tech discussion | Mon–Thu afternoon, 30 min | Sysadmins, DBAs, tech lead, app owner or security when needed | Review of Discovery summaries, technical decisions on flags, migration method, gate reviews for Gates 1, 2 and 4 | Logged decisions, signed gates |
| Sprint ceremonies | Per sprint | Agile team | Planning: which servers and phases go into the sprint. Review: gates signed during the sprint. Retro: improvements to the scripts and this guide | Sprint backlog, done items, repository changes |
| Blockers meeting | Weekly | PM, tech lead, managers (security when a risk acceptance is on the agenda) | Only flags marked BLOCKER, risk acceptances, priorities and resources | Blocker decisions in the decision log |

Tip Definition of done for a sprint item: a server's phase is done when its gate is signed. Work without a signed gate stays in progress.

|  | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Morning | Daily status | Daily status | Daily status | Daily status | Daily status |
| Afternoon | Tech discussion | Tech discussion | Tech discussion | Tech discussion |  |
| Weekly | Blockers meeting (PM · tech lead · managers) · Sprint ceremonies on the sprint calendar |  |  |  |  |

Gate 3 is signed by the app owner. Invite them to the tech discussion for that gate, or collect the sign-off in writing.

### 2.5 Decisions, exceptions and escalation

Every RED flag ends with one recorded decision: fix, accept the risk, or blocker. Decisions go in the decision log (template in the Appendix), never only in email or chat.

| RED flag found | → | ▸ Owner assigned at the daily status |
| --- | --- | --- |
| Owner assigned at the daily status | → | ▸ Can the team fix it within the plan? |
| Can the team fix it within the plan? | → | end |
| R | → | end |

### 2.6 Legacy protocols and insecure settings

Discovery documents, Migration addresses. Everything found during Discovery is recorded in the flag summary. It's fixed as part of the migration: the target is built to the current standard and doesn't carry the legacy setting over.

| Found during Discovery | Addressed during Migration |
| --- | --- |
| FTP (servers, scripts, partner and device flows) | Flow moved to the MFT (managed file transfer) platform. Files that land on old file shares move with the flow. |
| SMBv1 (server or clients) | Off on the target. Clients that only speak SMBv1 are upgraded or replaced, or moved to MFT if they only exchange files |
| TLS 1.0 / 1.1, SSL | TLS 1.2+ only on the target. Partners and clients are tested during the rehearsal |
| NTLMv1 / LM | NTLMv2 or Kerberos only. Apps and devices that need NTLMv1 are identified and upgraded |
| Anything else (telnet, SNMP v1/v2, SHA-1 certificates, clear-text credentials, …) | Documented in the summary, with a fix planned in the migration |

Warning Exceptions can happen, for example a device that can't be upgraded in time. Every exception is logged in the decision log with: - an owner; - the reason; - the compensating control, such as network isolation or a restricted firewall rule; - an end date. Security is consulted on each one. Exceptions are reviewed at the weekly blockers meeting until they're closed.

### 2.7 Supported vs works but not supported

Every path, OS and SQL combination in this program is one of two kinds, and the difference decides how it is done:

|  | SUPPORTED | WORKS, BUT NOT SUPPORTED |
| --- | --- | --- |
| What it means | Microsoft documents it: in its compatibility matrix or upgrade table | It runs, and may be proven in our lab, but Microsoft doesn't document it |
| Fixes, security updates, support case | Yes | No. The risk is ours alone |
| Approval | Normal gate | Normal gate. No exception, not a blocker. If the path is uncertain, it runs on a cloned VM first (below) |
| End state? | Yes | No. A step on the way to a newer, supported SQL version |

Important Our rule: every migration ends on a newer, supported SQL version. An unsupported step on the way is fine. A cloned VM is used only when the path is uncertain. A proven path goes straight to production, with a snapshot before each step as the rollback.

#### When to clone

| The path is… | Clone? | Examples |
| --- | --- | --- |
| Proven: already done in the lab or on an earlier server of the program, and Discovery found nothing unusual on this server | No. Snapshot before each step on production | 2008 R2 SP1 → 2012 R2 → 2025 with SQL 2005 (LAB OK); 2016 → 2025 |
| Uncertain: never done yet, in the lab or in the program | Yes | 2008 x64 → 2012 → 2016 → 2025; a new SQL instance on the same server (DBA form C) |
| Uncertain: proven, but Discovery flagged something unusual on this server | Yes | Old drivers or hardware dongles, a vendor app with no support statement, RED flags on the OS or SQL side |
| Uncertain: the sysadmin or DBA isn't confident | Yes: their call, no justification needed |  |

Once an uncertain path has worked on a clone and in production, it's proven for the next servers. Record it on the server page.

#### Clone-first procedure

| Clone the production VM | → | ▸ Isolate the clone (no production network) |
| --- | --- | --- |
| Isolate the clone (no production network) | → | ▸ Run the path on the clone, timed |
| Run the path on the clone, timed | → | ▸ Test with the app (app owner) |
| Test with the app (app owner) | → | ▸ OK? |
| OK? | → | ▸ yes: Same steps on production in the change window ▸ no: Fix the runbook, re-clone, retry |
| Same steps on production in the change window | → | end |
| Fix the runbook, re-clone, retry | → | ▸ Clone the production VM |

| # | Step | Who |
| --- | --- | --- |
| 1 | Clone the production VM (and take a snapshot or backup of production as the reference) | Sysadmin |
| 2 | Isolate the clone. It has the same name, IP and domain identity as production, so it must never reach the production network: disconnected NIC or an isolated VLAN, with the app's test client inside it | Sysadmin |
| 3 | Run the path on the clone, step by step, and time each step: OS hops (sysadmin) and the SQL move to the newer version (DBA) | Sysadmin, DBA |
| 4 | Test with the application in the isolated network: key functions, reports, interfaces | App owner, with the DBA |
| 5 | Record the steps, durations and issues on the server page; that's the runbook for production | Sysadmin, DBA |
| 6 | Production: the same steps in the change window, with a snapshot before each hop. Rollback = the snapshot, or the untouched source | Sysadmin, DBA |
| 7 | Delete the clone after Gate 3. It holds production data, so treat it like production until then | Sysadmin |

Examples for each side are in the role guides: Sysadmin §1 (OS paths, out-of-support OS, legacy protocols) and DBA §1 (SQL on an unsupported OS, the lab-proven SQL 2005 path).

———   ◆   ———

## 3. Standards

### 3.1 Scripts and repository

Bring your own script. Everyone can use the script they know, as long as it follows five rules:

- it produces the standard output (3.2, 3.3);

- it covers the Discovery checklist;

- it's read-only;

- it contains no secrets;

- it's in the team repository before it runs on production, with its version recorded in the summary.

How to work with the repository, VS Code, the develop branch and Copilot is described in Scripts & VS Code.

### 3.2 Output naming and storage

Migration/ └── <BUNDLE>/ e.g. B03-Finance └── <SERVER>/ ├── 1-Discovery/ │ ├── <SERVER>_SUMMARY_<yyyyMMdd>.csv flags only, one row per finding │ ├── <SERVER>_<area>_<yyyyMMdd>.csv e.g. APP01_services_20261022.csv │ └── <INSTANCE>_sql-<area>_<yyyyMMdd>.csv e.g. APP01-SQL2005_sql-jobs_20261022.csv ├── 2-Build/ ├── 3-Migration/ └── 4-Decommission/

Gate sign-offs, decisions and status live on the server's Loop page, not in SharePoint (section 4).

A bundle is the group of servers that are discovered and migrated together. Each server belongs to exactly one bundle. If a server moves to another bundle, its folder moves with it.

All of this lives in one SharePoint location, with no copies in personal folders or mailboxes.

### 3.3 The flag summary

Raw data is for evidence; the summary is what gets read. Every script writes one summary file in this format:

| Server | Area | Item | Flag | Detail | Owner | Decision | Decided by | Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| APP01 | Protocols | SMBv1 server enabled | AMBER | 3 scanners connect over SMBv1 | Sysadmin | Fix during migration: firmware update | J. Doe | 2026-10-30 |
| APP01 | Protocols | FTP partner flow | AMBER | Partner drops files in \\APP01\Inbound | Sysadmin | Move to MFT | J. Doe | 2026-10-30 |
| APP01 | SQL | Job owned by a person | AMBER | Nightly export owned by DOMAIN\jsmith | DBA | Fix: change to sa | A. Roy | 2026-10-30 |

### 3.4 Server page (Loop template)

Each server has one page that brings together its status, people, links (ADO, ServiceNow, SharePoint), flags, approvals and gates.

Template: SERVER-PAGE-TEMPLATE.md (view on GitHub) · SERVER-PAGE-TEMPLATE.docx (Word copy)

Loop can't import a file, and it only keeps basic formatting when you paste: headings, bold, lists, checklists and plain tables. Colours, shading and fonts are lost. To use the template in Microsoft Loop:

- Open SERVER-PAGE-TEMPLATE.md on GitHub, so it shows rendered, then select the page and copy it.

- Paste it into a new Loop page. Don't paste from the Word copy: Word's clipboard format makes Loop lose the lists and headings. Check that the checklists came through; if not, type [] at the start of those lines.

- Save the page as a template in the bundle's Loop workspace, so each server page starts from the same layout.

Note The guides don't go into Loop. Their layout (colours, diagrams, matrix) can't exist there. The Loop workspace home page links to them on GitHub, or to the Word copies in word/ (4.3).

———   ◆   ———

## 4. Documentation path

One place for each kind of information, and links everywhere else. If the same information is written in two places, one of them is wrong.

### 4.1 The documents

| Governance guide this page · the big picture | → | ▸ Sysadmin guide what the sysadmin owns ▸ DBA guide what the DBA owns ▸ Scripts & VS Code how scripts are written and shared ▸ Server page template one Loop page per server |
| --- | --- | --- |
| Sysadmin guide what the sysadmin owns | → | ▸ Lab evidence runbook · stability tests |
| DBA guide what the DBA owns | → | ▸ Lab evidence runbook · stability tests |
| Scripts & VS Code how scripts are written and shared | → | end |
| Server page template one Loop page per server | → | end |
| Lab evidence runbook · stability tests | → | end |

| Document | What it's for | Changes when |
| --- | --- | --- |
| Governance guide (this page) | Phases, gates, roles, rules, standards | A rule changes (decided in the retro or the blockers meeting) |
| Sysadmin guide | What the sysadmin owns and signs; Windows paths; checklists | Sysadmin practice changes |
| DBA guide | What the DBA owns and signs; SQL paths and matrix; audit; checklists | DBA practice changes |
| Scripts & VS Code | Script rules, Git, VS Code, Copilot, the path to fewer scripts | Tools or the script workflow change |
| Server page template | The layout of every server's Loop page | The information we track changes |
| Lab evidence | Proof for the lab-proven paths | After each lab test |

Word copies (for reading offline, printing, or sending): the global document with all guides in one file, Migration-Governance-Global.docx, with a table of contents, or one file per guide in word/. The graphics are drawn natively in Word, so they can be edited there. The Markdown files stay the source. After changing a guide, regenerate the copies from the migration-governance folder:

perl tools/md2docx.pl word/Migration-Governance-Global.docx README.md SYSADMIN.md DBA.md SCRIPTS-AND-VSCODE.md SERVER-PAGE-TEMPLATE.md perl tools/md2docx.pl word/DBA-Guide.docx DBA.md # same for each guide

### 4.2 Where to start

| You are | Read, in this order |
| --- | --- |
| Sysadmin | This page §1–2 → Sysadmin guide → Scripts & VS Code §1–4 |
| DBA | This page §1–2 → DBA guide → Scripts & VS Code §1–4 |
| App owner | This page §1, §2.2, 1.10 Disposition, Gate 3 → your server's Loop page |
| Tech lead / PM | This whole page → the server pages of the current bundle |
| Writing or changing a script | Scripts & VS Code |

### 4.3 Where each kind of information lives

| Information | Lives in | Linked from |
| --- | --- | --- |
| Rules and how-to (these guides) | Git repository | Loop workspace home page |
| Scripts | Git repository (develop; released versions on main) | Server page (script version) |
| Raw discovery output (CSV) | SharePoint Migration/<BUNDLE>/<SERVER>/1-Discovery/ | Server page |
| Flag summary (CSV) | SharePoint, same folder | Server page, flags table |
| Status, people, dependencies, flags and decisions, approvals, gate sign-offs | Loop server page (the hub for each server) | ADO story |
| Work items: stories, tasks, sprints | Azure DevOps | Server page |
| Server requests, CAB changes, decommission requests | ServiceNow | Server page |
| Clone runbook, validation evidence | SharePoint 2-Build/, 3-Migration/ | Server page |
| Decisions that apply to the whole program | Decision log page in the Loop workspace | Blockers meeting notes |

### 4.4 What gets documented, step by step

| Scripts run | → | ▸ SharePoint output + summary |
| --- | --- | --- |
| SharePoint output + summary | → | ▸ Loop server page findings, flags, decisions |
| Loop server page findings, flags, decisions | → | ▸ Gate signed on the Loop page |
| Gate signed on the Loop page | → | ▸ Next phase |
| Next phase | → | end |
| Azure DevOps story | → | ▸ links: Loop server page findings, flags, decisions (back / optional) |
| ServiceNow tickets | → | ▸ links: Loop server page findings, flags, decisions (back / optional) |

| When | Document | Where | Who |
| --- | --- | --- | --- |
| Bundle starts | Create the server page from the template, the ADO story and the SharePoint folder; link them together | Loop, ADO, SharePoint | Tech lead |
| Discovery, day 1 | Script output and flag summary | SharePoint 1-Discovery/ | Sysadmin, DBA |
| Discovery, end of week | Key findings, confirmed dependencies, monthly jobs, flags with their decisions | Server page | Sysadmin, DBA |
| Gate 1 | Disposition; Gate 1 checklist signed; decisions in the decision log | Server page | Migration lead; app owner confirms |
| Install & test (clone if uncertain) | ServiceNow server request; the clone runbook if a clone was used (steps, timings, problems); build deviations | Server page; SharePoint 2-Build/ | Sysadmin, DBA |
| Gate 2 | Gate 2 checklist signed | Server page | Migration lead |
| Migration | CAB change and approvals; rehearsal results; cut-over plan; validation evidence | ServiceNow; server page; SharePoint 3-Migration/ | Sysadmin, DBA |
| Gate 3 | App owner's acceptance, with a link to the approval record | Server page | App owner |
| Decommissioning | ServiceNow decommission request; quiet period or scream test result; removal checklist; location of the final backup | ServiceNow; server page; SharePoint 4-Decommission/ | Sysadmin, DBA |
| Gate 4 | Gate 4 checklist signed; ADO story closed | Server page; ADO | Migration lead |

### 4.5 Keeping it current

- Update the server page the same day something changes, and set its Last updated field.

- The daily status works from the server pages. There's no separate status document.

- Decisions made in the tech discussion or the blockers meeting go into the decision log during the meeting.

- Link, don't copy: the server page links to SharePoint, ADO and ServiceNow instead of repeating their content.

- These guides change in the repository, like the scripts. Improvements usually come from the sprint retro.

———   ◆   ———

| PHASE 1 Discovery | PHASE 2 Install & configure | PHASE 3 Migration | PHASE 4 Decommissioning |
| --- | --- | --- | --- |

## Phase 1 · Discovery

Goal: know everything that runs on, connects to, or depends on the server before anything is built or moved.

Discovery is scripted, so it takes one week per server or batch of servers. The scripts collect everything on day 1. A scheduled capture records connections for the rest of the week, and the review and decisions happen at the end of the week.

Discovery in one week (scripted)

| Who | Task | Mon 02 | Tue 03 | Wed 04 | Thu 05 | Fri 06 |
| --- | --- | --- | --- | --- | --- | --- |
| Sysadmin | Server, protocol and file scripts |  |  |  |  |  |
| DBA | Instance and database scripts |  |  |  |  |  |
| Capture (scheduled) | Connections and activity every 5-15 min |  |  |  |  |  |
| Review | Flag review and decisions |  |  |  |  |  |
| Review | App owner confirms dependencies |  |  |  |  |  |
| Review | Gate 1 |  |  |  |  | ◆ |

Important A one-week capture doesn't see monthly or quarterly activity. Cover that with the schedules: - Read every scheduled task and SQL Agent job schedule, and list anything that runs monthly, quarterly or yearly. Each one gets an owner to confirm what it connects to. - Ask the app owner about month-end, quarter-end and year-end processes. - The Phase 4 quiet period (2–4 weeks, with the capture still running on the old server) is the safety net for anything missed.

### 1.1 Tooling per source version

Whichever script you use, it has to run on the server's PowerShell version. The optional reference script covers every version: its core is PowerShell 2.0 compatible, and it uses the newer cmdlets only when $PSVersionTable.PSVersion.Major -ge 3.

| Source OS | PowerShell | What this means |
| --- | --- | --- |
| 2003 | None by default (2.0 only if WMF 2.0 / KB968930 was installed) | Run discovery remotely from a modern admin box over WMI/DCOM (Get-WmiObject -ComputerName), or locally with wmic, netstat, reg query, net share and schtasks. Don't install software just to discover the server. |
| 2008 | 1.0 (feature); 2.0 via WMF | PowerShell 2.0 only: no Get-CimInstance, no ConvertTo-Json, no Get-SmbShare. Use Get-WmiObject and Export-Csv. |
| 2008 R2 | 2.0 | Same as 2008. WinRM 2.0 may need its listener configured. The default execution policy is Restricted. |
| 2012 | 3.0 | CIM and the SMB cmdlets (Get-SmbServerConfiguration, Get-SmbSession, Get-SmbOpenFile) are available. Get-ScheduledTask too. |
| 2012 R2 | 4.0 (5.1 with WMF 5.1) | Same as 2012. Remoting is on by default. |
| 2016 / 2019 | 5.1 | Full cmdlets, including the SMBv1 access audit (Set-SmbServerConfiguration -AuditSmb1Access $true). |

Tip dbatools needs a modern PowerShell. Run it from an admin workstation against every instance, never on the server itself. Most read commands work from SQL 2000 to 2019, so a single DBA script can cover the whole estate.

### 1.2 Server: platform, identity and software

| Platform | Identity and access | Software and roles |
| --- | --- | --- |
| ☐ OS, edition, SP, x86/x64, install language ☐ End-of-support date ☐ Physical or virtual, host, hardware age ☐ CPU, RAM, disks, growth, page file ☐ Activation and licensing (OEM, VL, KMS) | ☐ Domain member? Domain controller? ☐ Local accounts and local Administrators ☐ Service accounts. Is the password known and in the vault? ☐ Credentials hard-coded in .ini, .config, .udl, .bat files and net use lines | ☐ Installed software (including 16-bit installers, which don't run on x64) ☐ IIS, DHCP, DNS, print, MSMQ, COM+/DCOM, WINS ☐ Non-default services and their start mode ☐ Scheduled tasks and AT jobs (2003) ☐ ODBC DSNs, 32-bit and 64-bit ☐ .NET, Java, VB6, Access runtimes ☐ Dongles, serial or USB devices, fax boards |

▾ Commands that work on PowerShell 2.0 and on 2003

# OS, including 2003 queried remotely from a modern box Get-WmiObject Win32_OperatingSystem -ComputerName SRV01 ¦ Select-Object CSName, Caption, CSDVersion, OSArchitecture, Version, OSLanguage, InstallDate # Services that run as a named account (these need a known password on the target) Get-WmiObject Win32_Service -ComputerName SRV01 ¦ Where-Object { $_.StartName -notmatch 'LocalSystem¦LocalService¦NetworkService' } ¦ Select-Object Name, DisplayName, StartName, StartMode, State ¦ Export-Csv SRV01_services-accounts_20261022.csv -NoTypeInformation # Installed software (both registry views) 'HKLM:\SOFTWARE\Microsoft\Windows\CurrentVersion\Uninstall\*', 'HKLM:\SOFTWARE\Wow6432Node\Microsoft\Windows\CurrentVersion\Uninstall\*' ¦ ForEach-Object { Get-ItemProperty $_ -ErrorAction SilentlyContinue } ¦ Where-Object { $_.DisplayName } ¦ Select-Object DisplayName, DisplayVersion, Publisher, InstallDate ¦ Export-Csv SRV01_software_20261022.csv -NoTypeInformation

:: Scheduled tasks with run-as account and command line (2003 and later) schtasks /query /v /fo csv > SRV01_tasks_20261022.csv :: 2003 only: legacy AT jobs at

### 1.3 Server: network and dependencies

☐  IPs, subnet, gateway, DNS, WINS, extra NICs and IPs, NIC teaming

☐  DNS records and aliases (CNAMEs) that point at this server

☐  hosts and lmhosts entries

☐  Listening ports mapped to processes (netstat -ano + tasklist /svc)

☐  Inbound and outbound connections over time. The script schedules a capture every 5–15 minutes for the Discovery week. Cover monthly and quarterly jobs from the task and job schedules (see the note above).

☐  Firewall rules here and upstream, plus IP allow-lists on other systems that name this server

☐  Hard-coded IPs and UNC paths in app configs

☐  Certificates: subject, SAN, expiry, issuer, exportable private key? SHA-1 or 1024-bit keys won't be accepted on modern targets.

☐  Backup agent and last good backup; monitoring and AV agents, AV exclusions

### 1.4 Server: legacy protocols and insecure settings

These are the items most likely to break during or after migration, because modern Windows disables them or doesn't install them. Discovery documents them all. They're addressed during the migration, as set out in 2.6.

| Item | How to check | Why it matters |
| --- | --- | --- |
| SMBv1 server | 2003: only speaks SMBv1. 2008 / 2008 R2: registry HKLM\SYSTEM\CurrentControlSet\Services\LanmanServer\Parameters → SMB1 (missing = enabled). 2012+: Get-SmbServerConfiguration → EnableSMB1Protocol. Enabled by default up to 2016; not installed on a clean 2019, but kept on a 2019 upgraded in place | Plan the target as if SMBv1 can't be used. |
| SMBv1 clients | 2003 / 2008: no audit. Record net session and net file during the capture. 2012 / 2012 R2: Get-SmbSession shows the Dialect (1.x = SMBv1). 2016 / 2019: enable AuditSmb1Access and read event 3000 in Microsoft-Windows-SMBServer/Audit. Then identify each client: XP, 2003, scanners and MFPs, NAS, embedded devices, old Samba | These clients can't reach a modern file server. Each needs an upgrade, firmware, or a decision. |
| SMBv1 as a client | 2008 / 2008 R2: HKLM\SYSTEM\CurrentControlSet\Services\mrxsmb10 → Start. 2012+: same, or the SMB1Protocol feature state | The app may pull files from an old NAS or device that only speaks SMBv1. |
| FTP server | IIS 6 FTP (MSFTPSVC, 2003). IIS 7.5–10 FTP (FTPSVC, 2008 R2–2019, logs in %SystemDrive%\inetpub\logs\LogFiles\FTPSVC*). FileZilla, Serv-U, WS_FTP. Check services, listeners on 21 or other ports, and site config, especially FTP roots and virtual directories that point to file shares | Clear-text passwords, anonymous access, partners or devices that drop files. For each flow, record who connects (from the logs), where the files land, and what processes them. Each flow is moved to MFT. |
| FTP clients | Scheduled tasks and scripts that call ftp.exe -s:<file>, WinSCP or curl. Read the -s: file for the host and credentials | Hidden outbound dependencies with stored passwords. Each one becomes an MFT flow. |
| TLS / SSL | HKLM\SYSTEM\CurrentControlSet\Control\SecurityProviders\SCHANNEL\Protocols. 2003: no TLS 1.1 or 1.2. 2008 R2: TLS 1.1/1.2 only if enabled. 2012–2019: TLS 1.2 is available, but TLS 1.0 and 1.1 are still on by default. Check .NET SchUseStrongCrypto too | Partners and clients that only speak SSL3 or TLS 1.0 will fail against a hardened target. |
| NTLMv1 / LM | HKLM\SYSTEM\CurrentControlSet\Control\Lsa → LmCompatibilityLevel, NoLMHash | Old apps and devices fail against hardened targets. |
| Telnet, rsh, SNMP v1/v2 | Services, listeners, SNMP community strings | Documented; replaced by SSH or SNMPv3 during the migration. |
| Other legacy items | WINS, NetBIOS name use, 8.3 short names, subst drives, mapped drives in a service context | These usually appear only after cut-over. |

▾ Commands: SMBv1, FTP, sessions

# SMBv1 server on 2008/2008 R2 (no value = enabled) Get-ItemProperty 'HKLM:\SYSTEM\CurrentControlSet\Services\LanmanServer\Parameters' ¦ Select-Object SMB1, SMB2 # SMBv1 client driver (4 = disabled) (Get-ItemProperty 'HKLM:\SYSTEM\CurrentControlSet\Services\mrxsmb10').Start # FTP services present? Get-Service MSFTPSVC, FTPSVC, 'FileZilla Server' -ErrorAction SilentlyContinue # 2012+: SMB sessions with dialect (1.x = SMBv1 client) Get-SmbSession ¦ Select-Object ClientComputerName, ClientUserName, Dialect, NumOpens # 2016 / 2019: audit SMBv1 access for the capture week, then read event 3000 Set-SmbServerConfiguration -AuditSmb1Access $true -Force Get-WinEvent -LogName 'Microsoft-Windows-SMBServer/Audit' -ErrorAction SilentlyContinue ¦ Where-Object { $_.Id -eq 3000 } ¦ Select-Object TimeCreated, Message # Scripts that drive ftp.exe with a command file (often holding a password) Get-ChildItem C:\, D:\ -Recurse -Include *.bat, *.cmd, *.vbs, *.ps1 -ErrorAction SilentlyContinue ¦ Select-String -Pattern 'ftp(\.exe)?\s.*-s:' ¦ Select-Object Path, LineNumber, Line

:: Who is connected to shares right now (schedule this during the capture period) net session >> SRV01_sessions_capture.txt net file >> SRV01_openfiles_capture.txt

### 1.5 Server: files, shares and unused data

Important Discovery only reports. The app owner or data owner decides what to archive or delete. That happens in Phase 4, never during Discovery.

☐  Every share: path, share and NTFS permissions, size, file count

☐  FTP data on file shares: inbound and outbound folders, archive folders, and the jobs that pick files up or clean them. These move with the flow to MFT, not with the file share.

☐  Data grouped by last-modified age: < 1 year · 1–3 years · 3–7 years · > 7 years

☐  Home or user folders of disabled or deleted AD accounts

☐  File types that carry risk or hide dependencies:

| Type | Why |
| --- | --- |
| .mdb .accdb | Access databases, often with linked tables pointing to SQL or ODBC DSNs |
| .xls* | External data connections to SQL or ODBC |
| .pst .ost | Mail archives; owner and retention questions |
| .bak .trn .mdf .ldf | Stray SQL files outside the instance |
| .bat .cmd .vbs .ps1 | Scripts with paths, servers and credentials |
| .iso .vhd installers | Large files, rarely needed |

☐  Duplicate and very large files

☐  Open files and sessions during the capture, to see which shares are actually used

☐  Data on local drives that isn't in any share (app data, exports, logs)

☐  Retention or legal holds. Ask the data owner; old doesn't automatically mean deletable.

Caution Don't use LastAccessTime. On 2008 to 2016 it isn't updated by default, and on 2019 it's "system managed", which depends on volume size (fsutil behavior query disablelastaccess). On 2003 it is updated, but antivirus and backup scans touch it too. Use LastWriteTime, together with the session and open-file capture.

▾ Command: data by age, PowerShell 2.0 compatible

$root = 'D:\Shares' $now = Get-Date Get-ChildItem $root -Recurse -ErrorAction SilentlyContinue ¦ Where-Object { -not $_.PSIsContainer } ¦ ForEach-Object { $age = ($now - $_.LastWriteTime).Days / 365 $bucket = if ($age -lt 1) {'<1y'} elseif ($age -lt 3) {'1-3y'} elseif ($age -lt 7) {'3-7y'} else {'>7y'} New-Object PSObject -Property @{ Bucket = $bucket; Bytes = $_.Length; Ext = $_.Extension.ToLower() } } ¦ Group-Object Bucket ¦ Select-Object Name, Count, @{n='GB'; e={ [math]::Round(($_.Group ¦ Measure-Object Bytes -Sum).Sum / 1GB, 2) }} ¦ Export-Csv SRV01_file-age_20261022.csv -NoTypeInformation

### 1.6 SQL: instance

| Version and support | Security | Features in use |
| --- | --- | --- |
| ☐ Version, edition, SP/CU, x86/x64 ☐ Instance name, port (static or dynamic), Browser ☐ Server collation, and databases with a different collation ☐ Service accounts, SPNs, delegation ☐ Memory, MAXDOP, non-default sp_configure settings, trace flags ☐ Startup parameters and tempdb layout | ☐ Logins (SQL and Windows), server roles, sa state ☐ SQL logins with weak or blank passwords (SQL 2000 has no password policy) ☐ Orphaned users per database ☐ TDE, certificates, master keys, credentials, proxies. Are the keys backed up? ☐ Forced encryption and its certificate | ☐ Agent jobs: owner, schedule, steps, what they touch outside SQL ☐ Operators, alerts, Database Mail, SQL Mail (removed after 2008 R2) ☐ Maintenance plans (2000/2005 plans don't migrate) ☐ DTS packages (2000). Not supported on 2012+, so they need a rewrite to SSIS ☐ SSIS, SSRS reports and subscriptions, SSAS ☐ Linked servers, OPENROWSET / OPENQUERY ☐ Replication, log shipping, mirroring, clustering, Always On AGs (2012+) ☐ CLR, extended procedures, xp_cmdshell ☐ Cross-database and cross-server names ☐ 2016–2019 features removed or deprecated in 2022: Stretch Database, R/Python ML Services (not installed by setup), PolyBase Hadoop, Distributed Replay ☐ Query Store, Master Data Services, Data Quality Services, Power BI Report Server |

Which restore paths work. Plan the number of hops now:

| SQL 2000 compat 80 | → | ▸ restore: Hop instance SQL 2008 R2 |
| --- | --- | --- |
| Hop instance SQL 2008 R2 | → | ▸ restore: SQL 2022 / 2025 |
| SQL 2022 / 2025 | → | end |
| SQL 2005 compat 90 | → | ▸ restore (auto compat 100): SQL 2022 / 2025 |
| SQL 2008 – 2019 | → | ▸ restore, log shipping or in-place upgrade: SQL 2022 / 2025 |

Only SQL 2000 needs an intermediate hop. Databases from SQL 2005 (compatibility level 90) and later restore directly on SQL 2022 and 2025; 2005 databases are raised to level 100 automatically (Microsoft, Supported version and edition upgrades for 2022 and 2025). Per-version paths, in-place upgrade limits and the SQL × Windows matrix are in the DBA guide.

Warning A restore upgrades the database to the target version, one way. A backup taken on the target can't be restored on the source. The rollback is always the untouched source, never a backup from the new server.

### 1.7 SQL: databases

☐  Name, size (data and log), growth, file locations, owner

☐  Compatibility level, recovery model

☐  Page verify: SQL 2000 databases are often TORN_PAGE_DETECTION or NONE. Plan CHECKSUM after migration.

☐  Last good DBCC CHECKDB. Run one before migration so you know whether corruption was already there.

☐  Backups: target, frequency, last good one, and the RPO/RTO agreed with the app owner

☐  Is it used? See 1.8

☐  Applications and connection strings that use it, from the capture, not from memory

### 1.8 SQL: activity and auditing per version

Old versions can't tell you who uses a database the way newer ones can. SQL Server Audit doesn't exist before 2008, it's Enterprise-only on 2008 / 2008 R2, and database-level audit reaches every edition only from 2016 SP1. Use what each version offers, schedule the capture for the Discovery week, and read the Agent job schedules to cover monthly activity.

| Version | Who connects | Is the database used | Who changes what |
| --- | --- | --- | --- |
| SQL 2000 | Snapshot master..sysprocesses every 5–15 min | No usage DMVs. Use a light server-side trace (login, batch completed, filtered) | Server-side trace. C2 audit mode only as a last resort: it's heavy and stops the instance if the disk fills |
| SQL 2005 | Snapshot sys.dm_exec_sessions + sys.dm_exec_connections (client IP) | sys.dm_db_index_usage_stats. It resets on restart: check uptime via tempdb create_date | Default trace (rolls over fast: 5 × 20 MB), DDL triggers, logon triggers (SP2+) |
| SQL 2008 / R2 | Same as 2005 | Same, plus sys.dm_os_sys_info.sqlserver_start_time | SQL Server Audit on Enterprise; otherwise the 2005 methods |
| SQL 2012 / 2014 | sys.dm_exec_sessions now has database_id | Same as 2008 | Server-level audit on every edition; database-level audit on Enterprise only. Extended Events |
| SQL 2016 – 2019 | Same as 2012 | Same, plus Query Store (per-database query history, if enabled) | Server- and database-level audit on every edition (2016 SP1+). Extended Events |

▾ T-SQL: connection snapshots and usage, per version

-- SQL 2000: who is connected (schedule every 5–15 min, insert into a capture table) SELECT GETDATE() AS captured_at, spid, RTRIM(hostname) AS host, RTRIM(program_name) AS program, RTRIM(loginame) AS login, DB_NAME(dbid) AS db FROM master..sysprocesses WHERE spid > 50;

-- SQL 2005 / 2008: who is connected, with client IP SELECT GETDATE() AS captured_at, c.client_net_address, s.host_name, s.program_name, s.login_name, DB_NAME(p.dbid) AS db FROM sys.dm_exec_sessions AS s JOIN sys.dm_exec_connections AS c ON c.session_id = s.session_id JOIN sys.sysprocesses AS p ON p.spid = s.session_id WHERE s.is_user_process = 1;

-- SQL 2012 – 2019: who is connected, with client IP and current database SELECT GETDATE() AS captured_at, c.client_net_address, s.host_name, s.program_name, s.login_name, DB_NAME(s.database_id) AS db FROM sys.dm_exec_sessions AS s JOIN sys.dm_exec_connections AS c ON c.session_id = s.session_id WHERE s.is_user_process = 1;

-- SQL 2005 – 2019: last read and write per database since the service started -- (on 2008+ you can also use sys.dm_os_sys_info.sqlserver_start_time) SELECT create_date AS sql_started FROM sys.databases WHERE name = 'tempdb'; SELECT DB_NAME(database_id) AS db, MAX(last_user_seek) AS last_seek, MAX(last_user_scan) AS last_scan, MAX(last_user_lookup) AS last_lookup, MAX(last_user_update) AS last_update FROM sys.dm_db_index_usage_stats GROUP BY database_id;

-- All versions: jobs owned by a person, orphaned users SELECT j.name, SUSER_SNAME(j.owner_sid) AS owner FROM msdb.dbo.sysjobs AS j; EXEC sp_change_users_login 'Report'; -- run in each user database -- All versions: jobs that run monthly or less often (the week's capture won't see them) -- freq_type 16 = monthly, 32 = monthly relative SELECT j.name, s.name AS schedule, s.freq_type, s.freq_interval, s.active_start_time FROM msdb.dbo.sysjobs AS j JOIN msdb.dbo.sysjobschedules AS js ON js.job_id = j.job_id JOIN msdb.dbo.sysschedules AS s ON s.schedule_id = js.schedule_id WHERE s.freq_type IN (16, 32);

☐  Turn on login auditing ("both failed and successful logins") for the capture week. It writes to the errorlog, so check the errorlog size and recycle schedule. Audit options for each version, including versions without SQL Server Audit: DBA guide §7.

☐  A database with no reads or writes during the capture, no monthly job touching it, and a long uptime behind the usage stats is a candidate for archiving. The app owner decides.

☐  Hand the compiled host · app · login · database list to the app owner to confirm.

### 1.9 Red and amber flags

| RED: blocks migration until decided | AMBER: needs a plan |
| --- | --- |
| - Unsupported source → target path (e.g. SQL 2000 → 2019 direct) - DTS packages, 16-bit apps, hardware dongles - SMBv1 or NTLMv1 client that can't be upgraded (needs an exception) - Clear-text credentials in scripts - TDE or encryption keys not backed up - No backup, or last good backup older than 7 days - Unknown inbound connections after the capture | - FTP flow to move to MFT - SMBv1, TLS 1.0/1.1 or NTLMv1 in use (fixed during the migration) - Certificate expiring within 90 days - Job or database owned by a personal account - Data older than 7 years with no owner - Service account password unknown - No CHECKSUM page verify, no recent CHECKDB - Dynamic SQL port, hard-coded IPs - Database with no activity during the capture |

### 1.10 Disposition: migrate, consolidate or retire

Discovery often shows that a server, or some of its databases and shares, no longer needs to move. Decide this before building anything.

| Disposition | Typical evidence from Discovery | Next phase |
| --- | --- | --- |
| Migrate | Active users and connections, the app is still needed | Phase 2 |
| Consolidate | Light workload that fits on an existing supported server or instance | Phase 3 (target already exists) |
| Retire | No meaningful connections, no scheduled jobs that matter, the app is replaced or no longer used | Phase 4, retire-only path |

A server can also be split: for example, migrate two databases and retire the rest. Record each part's disposition in the decision log.

What each role does for each option, including the evidence that a server or database isn't used and the in-place upgrade step by step: Sysadmin guide §6 · DBA guide §6.

Important Retire is a business decision. The app owner is accountable, and has to confirm in writing that the service is no longer needed and what happens to its data. The sysadmin and DBA provide the evidence.

### Gate 1 · Discovery complete

☐  Server and SQL scripts ran from the approved repository version (version recorded in the summary)

☐  Capture ran for the Discovery week, and every monthly, quarterly or yearly task or job has an owner who confirmed what it connects to

☐  Output is in Migration/<BUNDLE>/<SERVER>/1-Discovery/ with standard names

☐  Summary reviewed by the sysadmin ______ and the DBA ______ on ______

☐  Every RED flag has an owner and a logged decision

☐  App owner has confirmed the dependencies and the unused-data candidates

☐  Disposition recorded for the server (and for each database or share, if split): migrate · consolidate · retire

☐  If migrating: target platform and path chosen (OS and SQL versions, number of hops, in-place or side-by-side)

☐  If retiring: app owner's written confirmation that the service is no longer needed, plus a decision on the data

☐  Migration lead sign-off: ______ on ______

———   ◆   ———

| PHASE 1 Discovery | PHASE 2 Install & configure | PHASE 3 Migration | PHASE 4 Decommissioning |
| --- | --- | --- | --- |

## Phase 2 · Install & configure

Goal: a target that is built to standard, hardened, and ready, with every prerequisite that Discovery found already in place.

| Sysadmin: server | DBA: SQL |
| --- | --- |
| ☐ Built from the standard image or build, on a supported OS ☐ Patched, and joined to the correct OU (GPOs applied) ☐ Disk layout to standard (OS · apps · data · logs · tempdb · backups) ☐ Service accounts created, or gMSAs where the app supports them; passwords in the vault ☐ Roles and features from Discovery installed (IIS, .NET 3.5, MSMQ, …) ☐ SMBv1 off, TLS 1.2+ only, NTLMv1 refused. Exceptions only as logged in the decision log ☐ MFT flows set up for every FTP flow found in Discovery (accounts, folders, partner keys or certificates) ☐ Certificates issued (SHA-256, 2048-bit+), private keys exportable per policy ☐ Backup, monitoring, AV (with exclusions) and logging agents installed ☐ Scheduled tasks prepared but disabled | ☐ Supported version and edition, latest CU ☐ Collation matches the source (or a documented change) ☐ Service accounts, SPNs, static port, firewall rule ☐ Memory, MAXDOP, cost threshold, tempdb files to standard ☐ Backups, integrity checks and index maintenance jobs (standard solution, not legacy maintenance plans) ☐ Database Mail, operators and alerts configured ☐ Logins scripted from the source (SIDs and hashes kept) but not yet enabled for apps ☐ SSIS / SSRS installed if Discovery found them; DTS rewrite tracked ☐ Linked servers recreated with non-personal credentials ☐ Auditing enabled with SQL Server Audit (server level on all editions from 2012; database level from 2016 SP1). Standard setup: DBA guide §7 |

### Gate 2 · Target ready

☐  Build checklist complete, with deviations recorded in the decision log

☐  Security / network: firewall rules, certificates and exceptions done and signed

☐  Backup of the empty target tested (restore proven)

☐  Monitoring is green

☐  Smoke test passed (app installs and starts, connects to an empty or test database)

☐  Migration lead sign-off: ______ on ______

———   ◆   ———

| PHASE 1 Discovery | PHASE 2 Install & configure | PHASE 3 Migration | PHASE 4 Decommissioning |
| --- | --- | --- | --- |

## Phase 3 · Migration

Goal: data, apps and dependencies move once, in a rehearsed and timed window, with a rollback that has been tested.

### 3.1 Choose the method

In-place upgrade first, whenever a path exists. Side-by-side second. A path that's uncertain runs on a cloned VM first (when to clone). The sysadmin does the OS in-place upgrade; the DBA takes over at the OS hand-off (2.2).

| In-place path exists? (OS and SQL) | → | ▸ yes: Path uncertain? ▸ no: 2nd choice Side-by-side |
| --- | --- | --- |
| Path uncertain? | → | ▸ no (proven): 1st choice In-place on production snapshot per step + hardening ▸ yes: Run it on a cloned VM |
| 1st choice In-place on production snapshot per step + hardening | → | end |
| Run it on a cloned VM | → | ▸ Clone test passes? |
| Clone test passes? | → | ▸ yes: 1st choice In-place on production snapshot per step + hardening ▸ no, can't be fixed: 2nd choice Side-by-side |
| 2nd choice Side-by-side | → | end |

| Order | Method | When to use | Watch out for |
| --- | --- | --- | --- |
| 1 | In-place OS upgrade | Whenever a path exists. 2008 R2 SP1 → 2012 R2 → 2025: works, not supported, LAB OK. 2012 R2 → 2016, 2019 or 2025 (not 2022). 2016, 2019 → 2022 or 2025 (Sysadmin guide §5) | Each hop needs a licence and a snapshot. It keeps old settings, so harden after the last hop: SMBv1 off, TLS 1.2+, NTLMv1 refused (2.6) |
| 1 | In-place SQL upgrade | Whenever a supported path exists: to 2022 from 2012 SP4, 2014 SP3, 2016 SP3, 2017, 2019; to 2025 from 2014 SP3 onwards. The OS must support the target SQL (DBA guide §5) | Rollback = the VM snapshot taken just before |
| 2 | Side-by-side (new server, move app and data) | No in-place path (2003, SQL 2000, an OS and SQL pair that can't be reached), or the clone test failed | DNS and aliases, IP allow-lists, hard-coded names |

Moving the data in a side-by-side, or into a new SQL instance:

| Method | When to use | Watch out for |
| --- | --- | --- |
| Backup / restore (SQL) | Most databases; downtime equals the restore time | Restore-version hops (see 1.6); orphaned users |
| Log shipping or differential catch-up (SQL) | Large databases with a short window | The target must be able to restore the source version |
| Detach / attach | Rarely; when backup and restore is too slow | No rollback once upgraded; keep a copy |
| Robocopy (files) | File shares | /COPYALL, a preliminary pass plus a final delta, long paths |

### 3.2 Runbook

| Rehearsal (timed; on a clone if uncertain) | → | ▸ Cut-over plan + rollback plan approved |
| --- | --- | --- |
| Cut-over plan + rollback plan approved | → | ▸ Freeze and final backup |
| Freeze and final backup | → | ▸ Move data and apps |
| Move data and apps | → | ▸ Switch DNS, aliases, jobs |
| Switch DNS, aliases, jobs | → | ▸ Validate (IT, then app owner) |
| Validate (IT, then app owner) | → | ▸ fails: Rollback (source is still intact) ▸ passes: Gate 3 |
| Rollback (source is still intact) | → | end |
| Gate 3 | → | end |

☐  Rehearsal, timed: on a cloned VM if the path is uncertain (when to clone), otherwise a dry run of the steps on a test server. The real window = rehearsal time + 50%.

☐  Rollback plan with a clear point of no return and who calls it

☐  Users and app owner notified; change ticket approved

☐  Source set to read-only (or services stopped) before the final copy, so no writes are lost

☐  Logins fixed (orphaned users), jobs enabled, linked servers tested

☐  Compatibility level raised after validation, not during cut-over

☐  CHECKSUM page verify set; DBCC CHECKDB on the target

☐  Row counts and checksums compared for key tables

☐  DNS and aliases switched; old name kept as a CNAME if the app needs it

☐  Every dependency from Discovery tested: scanners, MFT flows and partners, reports, interfaces

☐  Every legacy-protocol flag from Discovery is closed, or covered by a logged exception with an end date

☐  FTP service on the old server stopped once its flows run on MFT

### Gate 3 · Accepted

☐  Validation evidence stored in 3-Migration/

☐  All Discovery dependencies tested and marked OK

☐  First backup on the target, and a restore tested

☐  Monitoring green for 48 h

☐  App owner acceptance: ______ on ______

———   ◆   ———

| PHASE 1 Discovery | PHASE 2 Install & configure | PHASE 3 Migration | PHASE 4 Decommissioning |
| --- | --- | --- | --- |

## Phase 4 · Decommissioning

Goal: the old server is retired cleanly and reversibly until the wait period ends, and leaves nothing behind in any system.

| Quiet period 2–4 weeks monitor connections | → | Power off (don't delete) 2–4 weeks | → | Final backup kept per retention | → | Remove from every system | → | Gate 4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

☐  Quiet period: keep the connection capture running on the old server, and make sure it covers a month-end. It's the safety net for the one-week Discovery: any hit is a missed dependency, so fix it before you continue.

☐  Unused-data decisions from Discovery carried out: archive, move or delete, signed by the data owner

☐  SQL: databases set offline first, then a final backup; logins disabled

☐  Server powered off, not deleted, for the agreed wait

☐  Final full backup (server + databases) kept per retention policy, with a restore test

### Retire-only path

Use this path for a server whose disposition at Gate 1 was retire. There is no new server and no Gate 3, so nothing has been tested in practice yet. The scream test takes the place of that validation.

| Gate 1 disposition: RETIRE | → | ▸ Announce date + contact |
| --- | --- | --- |
| Announce date + contact | → | ▸ Data decision carried out (archive or hand over) |
| Data decision carried out (archive or hand over) | → | ▸ Scream test disable, don't delete covers a month-end |
| Scream test disable, don't delete covers a month-end | → | ▸ Anyone affected? |
| Anyone affected? | → | ▸ yes: Re-enable, back to Gate 1 (new disposition) ▸ no: Power off, final backup, removal checklist |
| Re-enable, back to Gate 1 (new disposition) | → | end |
| Power off, final backup, removal checklist | → | ▸ Gate 4 |
| Gate 4 | → | end |

☐  Announce the retirement date and a contact to users and dependent teams (as found in Discovery)

☐  Data: what the app owner decided is carried out first: archived to the agreed location, handed over, or deleted under the retention policy. A last full backup is taken before anything is deleted.

☐  SQL: each database is set offline, not dropped, so it can come back in minutes

☐  Scream test: disable the service in a way that can be undone in minutes (stop the services, disable the NIC, or shut down the VM). Keep it disabled for at least 4 weeks, including a month-end, with the change ticket and contact visible.

☐  If someone is affected: re-enable the server, record the missed dependency, and go back to Gate 1 with a new disposition

☐  If nobody is affected: continue with the final backup and the removal checklist below

Removal checklist:

| ☐ Active Directory computer object ☐ DNS A, PTR and CNAME records ☐ DHCP reservations ☐ Firewall rules and allow-lists | ☐ Monitoring ☐ Backup jobs ☐ Antivirus / EDR console ☐ Patch management (WSUS, SCCM) | ☐ CMDB / inventory ☐ Licences reclaimed (OS, SQL, CALs) ☐ Service accounts disabled, then deleted ☐ Certificates revoked |
| --- | --- | --- |

### Gate 4 · Retired

☐  No connections seen during the quiet period, or no one affected during the scream test (retire-only path)

☐  Retire-only: data decision carried out and confirmed by the app owner

☐  Final backup kept, with the restore test recorded

☐  Removal checklist complete

☐  VM or hardware deleted or disposed of per policy (disks wiped)

☐  Migration lead sign-off: ______ on ______

———   ◆   ———

## Appendix

### A. Decision log template

| ID | Date | Server | Flag / topic | Decision (fix · accept · blocker) | Rationale | Owner | End date (for an accept) | Signed by |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D-001 |  |  |  |  |  |  |  |  |

### B. Gate sign-off template (on the server's Loop page)

SERVER: APP01 PHASE: 1 - Discovery GATE OWNER: <name> [x] Scripts from approved version .......... v1.4 (commit 3f2a91c) [x] Capture period ......................... 2026-11-02 -> 2026-11-06 [x] Monthly/quarterly jobs confirmed ....... 4 tasks, 2 Agent jobs - owners listed [x] Summary reviewed ....................... sysadmin <name> / DBA <name> - 2026-11-05 [x] RED flags decided ...................... D-014, D-015, D-016 [x] Dependencies confirmed by app owner .... <name> - 2026-11-06 SIGNED: <name> DATE: 2026-11-06

### C. Glossary

| Term | Meaning |
| --- | --- |
| Gate | A signed checkpoint between two phases |
| RACI | Responsible, Accountable, Consulted, Informed |
| Capture | Recording connections or activity at regular intervals (every 5–15 min for the Discovery week), not a single snapshot |
| Flag | A finding that needs a decision (RED) or a plan (AMBER) |
| Quiet period | Time after cut-over when the old server stays up and is watched for missed dependencies |
| Hop | An intermediate version needed because the source can't go straight to the target |
| MFT | Managed file transfer: the central platform that replaces FTP flows, with secure protocols, logging and alerting |
| Bundle | A group of servers discovered and migrated together; the top folder level in the migration storage |
| Disposition | The Gate 1 decision for a server or part of one: migrate, consolidate or retire |
| Scream test | Disabling a server that's being retired, in a way that can be quickly undone, to find out whether anyone still depends on it |

———   ◆   ———

Migration governance · maintained by the Migration lead · change this guide through a reviewed change in the repository, like the scripts

MIGRATION GOVERNANCE · ROLE GUIDE # Sysadmin Guide Windows Server 2003 – 2025 · servers, files, network, protocols ● DISCOVERY — ● INSTALL & CONFIGURE — ● MIGRATION — ● DECOMMISSIONING

Role guide for sysadmins · the governance guide is the big picture; this page is what the sysadmin owns · the SQL side is in the DBA guide

Important The sysadmin owns everything around SQL Server: the server, the OS, disks, network, DNS, firewall, certificates, file shares, FTP flows and legacy protocols. The DBA owns everything inside the instance. You work together, but each side signs for its own part.

———   ◆   ———

## 1. Supported vs works but not supported

These two words tell you who carries the risk. Whether a clone is needed depends on something else: how certain the path is (when to clone).

|  | SUPPORTED | WORKS, BUT NOT SUPPORTED |
| --- | --- | --- |
| Meaning | Microsoft documents it: the OS version is in support, the upgrade path is in Microsoft's table, and the software on it is supported on that OS | It runs, and we proved it in the lab, but Microsoft doesn't document it (or flags it as incompatible) |
| Fixes and security updates | Yes | No. Out-of-support OS, or an app the OS vendor won't fix |
| Microsoft support case | Accepted | Can be refused |
| Approval | Normal gate | Normal gate. No exception, not a blocker. If the path is uncertain, it runs on a cloned VM first |
| Can it be the end state? | Yes | No. A step on the way to a newer, supported platform |
| Who carries the risk | Shared with the vendor | Us alone, which is why an uncertain path is proven on a clone first |

Important Every migration ends on a newer, supported version. An unsupported step on the way (for example 2008 R2 → 2012 R2) is allowed. Clone only when the path is uncertain: not yet done in the lab or the program, something unusual found on this server, or you're not confident. A proven path goes straight to production, with a snapshot before each step. When a clone is needed, the sysadmin clones and isolates the VM (governance §2.7).

On the sysadmin side, it typically looks like this:

- The upgrade path is supported, but what runs on it isn't. Windows 2012 R2 → 2025 is a supported OS upgrade, but setup flags SQL Server 2005 as an incompatible application (a soft block). The OS is supported; the server as a whole isn't.

- A path that Microsoft no longer documents. Windows 2008 R2 SP1 → 2012 R2 isn't in Microsoft's current upgrade table any more. It worked in our lab, but treat it as works, but not supported.

- An out-of-support OS (2003, 2008, 2008 R2, 2012 R2) without ESU gets no security updates at all. As a step on the way, it is fine; as an end state, it is not.

- Legacy protocols left on (SMBv1, TLS 1.0, NTLMv1): Windows still has the switches, but our policy is to turn them off. Leaving them on needs an exception (governance §2.6).

———   ◆   ———

## 2. Your responsibilities

A = accountable (signs for it), R = does the work, C = consulted. The full RACI with every role is in the governance guide §2.3.

| Phase | Sysadmin is A for | Sysadmin is R for | Sysadmin is C for |
| --- | --- | --- | --- |
| 1 · Discovery | Server discovery script and output; server and protocol flags | Files, shares and unused data; legacy protocols (SMBv1, FTP, TLS, NTLMv1); connection capture at OS level | SQL discovery |
| 2 · Install & configure | Target server build and hardening | Smoke test (server side) | SQL install; firewall and certificate requests (Security / Network own them) |
| 3 · Migration | OS in-place upgrade and hardening, up to the OS hand-off to the DBA. OS-level cut-over: DNS, aliases, file shares, MFT flows, scheduled tasks | Clone (if the path is uncertain); cut-over and rollback plan (server side) | Everything SQL after the OS hand-off (DBA) |
| 4 · Decommissioning | Server removal from every system | Quiet-period or scream-test monitoring; carrying out the data decision for file shares | Instance decommissioning (DBA) |

What the sysadmin signs at each gate

| Gate | Sysadmin signature covers |
| --- | --- |
| Gate 1 | Server summary reviewed; every server and protocol RED flag decided; FTP flows listed for MFT; OS path chosen (section 5) |
| Gate 2 | Server built to standard; legacy protocols off (or an exception logged); agents installed; MFT flows set up |
| Gate 3 | DNS and aliases switched; file shares and scheduled tasks moved; MFT flows tested with partners; monitoring green |
| Gate 4 | Quiet period clean; final backup kept; removed from AD, DNS, DHCP, firewall, monitoring, backup, AV, patching, CMDB |

———   ◆   ———

## 3. Hand-offs with the DBA

Three hand-off points (governance §2.2):

- After Discovery (Gate 1): OS path and SQL path agreed together.

- OS hand-off: the sysadmin finishes the OS in-place upgrade and hardening, then hands the server to the DBA. From then on, the DBA is responsible up to Gate 3.

- Before decommissioning: the DBA confirms the databases are offline and backed up; then the sysadmin removes the server.

Most delays happen between the two roles. Ask early, using this list.

| Sysadmin needs from the DBA | DBA needs from the sysadmin |
| --- | --- |
| SQL port(s) and Browser need, for the firewall rules | Target server built, with disk layout for SQL: data, log, tempdb and backup volumes, 64 KB allocation unit |
| AV exclusions for data, log and backup files and sqlservr.exe | Service accounts or gMSAs created, passwords in the vault, with instant file initialization and lock pages in memory rights |
| Backup schedule and retention for the agent | Backup agent installed; backup share reachable |
| Which apps and servers connect to SQL (from the capture), for the dependency list | Firewall rules for 1433 / named instance ports |
| Go / no-go on the SQL side before the DNS switch | DNS alias switch at the agreed time in cut-over |
| TLS level needed by SQL clients (legacy 2005 clients need TLS 1.0) | TLS certificate for SQL encryption |
| Confirmation that databases are offline before power-off | Server kept powered on during the quiet period |

———   ◆   ———

## 4. Target platform

|  | Default | Why |
| --- | --- | --- |
| OS for a new build | Windows Server 2025 (2022 if the application vendor requires it) | Longest support. 2025 supports SQL 2019, 2022 and 2025 (see the DBA matrix) |
| 1st choice: in-place upgrade | Whenever a path exists (section 5). Done by the sysadmin. On a cloned VM first only if the path is uncertain (when to clone) | Same server, name, IP and data: fewer dependencies to move. Production gets a snapshot before each hop |
| After an in-place upgrade | Harden after the last hop: SMBv1 off, TLS 1.2+ only, NTLMv1 refused, old roles and agents reviewed | An in-place upgrade keeps every old setting, including the insecure ones (governance §2.6) |
| 2nd choice: side-by-side | New server, then move apps and data. When no in-place path exists (2003), or the clone test fails | Clean build. The source stays untouched as the rollback |

Note Check the SQL version before you choose the OS. SQL 2017 isn't supported on Windows 2025, and SQL 2016 isn't supported on 2022. Agree the OS and SQL pair with the DBA at Gate 1.

———   ◆   ———

## 5. Windows in-place upgrade paths

### 5.1 Paths

| From | To (in place) | Status |
| --- | --- | --- |
| 2003 | Nothing modern | No path. Side-by-side only |
| 2008 (x64) | 2012 | Older Microsoft guidance; no longer in the current table. Not lab-tested. Try it on a clone (then 2012 → 2016 → 2025); side-by-side if it fails |
| 2008 (x86, 32-bit) | Nothing | No path: Windows 2012 and later are x64 only. Side-by-side only |
| 2008 R2 SP1 | 2012 R2 | Works, but not supported (no longer in Microsoft's current table). LAB OK |
| 2012 | 2012 R2, 2016 | Supported |
| 2012 R2 | 2016, 2019, 2025 | Supported. Not to 2022 (not supported). 2012 R2 → 2025 is LAB OK |
| 2016 | 2019, 2022, 2025 | Supported |
| 2019 | 2022, 2025 | Supported |
| 2022 | 2025 | Supported |

Source: Microsoft, Windows Server upgrade paths. Since 2025, a non-clustered server can jump up to four versions; earlier versions allow two. Rules that always apply:

- same edition or higher;

- same install language;

- x64 to x64;

- evaluation media can't upgrade a licensed server;

- disable NIC teaming first;

- each hop needs its own licence.

### 5.2 Lab-proven chain: 2008 R2 SP1 → 2012 R2 → 2025

PARTLY NOT SUPPORTED. Proven in our lab, with SQL 2005 and a live application on the server. The SQL side and its conditions are in the DBA guide §5.3.

| 2008 R2 SP1 baseline + snapshot | works, not supported ~25 min, 3 reboots → | 2012 R2 + April 2014 Update + all final updates | supported OS path ~1 h → | 2025 checks + snapshot |
| --- | --- | --- | --- | --- |

What the lab taught us. Each item stopped or broke an upgrade at least once:

| # | Lesson |
| --- | --- |
| 1 | Check the ISO first: authentic, not Evaluation (ei.cfg with Channel=eval is a blocker), same edition and language |
| 2 | 2008 R2 needs SP1 before going to 2012 R2 |
| 3 | 2008 R2 → 2012 R2 unattended: the answer file needs ImageInstall and InstallTo (the existing OS partition). Run setup on the console, because the app-compatibility page (SQL 2005) waits for Confirm |
| 4 | Before going to 2025, patch 2012 R2 fully to its last public updates (SSU KB5032308 and rollup KB5031419). With only the 2014 updates, the 2025 setup crashed (0xC190011F) |
| 5 | 2025 needs a CPU with x86-64-v2 (on a VM, set the CPU type before the upgrade) |
| 6 | Keep 40 GB+ free on C: before each hop; grow the disk if needed |
| 7 | Activation is reset after each hop. Plan KMS or MAK |
| 8 | After the 2025 upgrade, RDP didn't listen until one more restart. Check RDP explicitly |
| 9 | With pending updates, shut down from inside Windows; the hypervisor's shutdown timed out |
| 10 | Snapshot before each hop, and keep it until the app owner confirms |

Full runbook, commands and logs: legacy-migration runbook.

———   ◆   ———

## 6. Options after Discovery

Discovery ends with one of three options for each server, decided at Gate 1 (governance §1.10):

| Discovery results | → | ▸ Is the server still used? |
| --- | --- | --- |
| Is the server still used? | → | ▸ no: Retire 6.2 ▸ yes: In-place path exists? (section 5) |
| Retire 6.2 | → | end |
| In-place path exists? (section 5) | → | ▸ yes: 1st: in-place upgrade 6.1 · clone if uncertain ▸ no: 2nd: side-by-side new server |
| 1st: in-place upgrade 6.1 · clone if uncertain | → | ▸ clone test fails: 2nd: side-by-side new server |
| 2nd: side-by-side new server | → | end |

### 6.1 In-place upgrade, step by step

What it is: Windows is upgraded on the same server: same name, IP, data, shares, scheduled tasks and installed software. Nothing has to be moved, which is why it's the first choice.

Important The OS in-place upgrade is done by the sysadmin, from preparation to hardening. When the OS is done, the sysadmin hands the server over to the DBA (step 5). From the hand-off on, the DBA is responsible for the rest of the migration: SQL to a newer version, data validation and the app test, up to Gate 3.

| # | Step | Sysadmin | DBA |
| --- | --- | --- | --- |
| 1 | Prepare | Check the path (5.1), media (not Evaluation, same edition and language), licences, free disk (40 GB+), CPU (x86-64-v2 for 2025). Patch the source fully. Decide whether the path is uncertain (when to clone) | Confirm the SQL version will run on each OS hop (DBA matrix). Full backups of all databases, system databases included |
| 2 | Clone: uncertain paths only | Clone the production VM, isolate it, run every hop, timed; record the steps and problems on the server page | Quick SQL check after each hop on the clone |
| 3 | Change window on production | Snapshot before each hop. Run the hops | Final backups before the first hop |
| 4 | Harden after the last hop | SMBv1 off, TLS 1.2+ only, NTLMv1 refused, old roles and agents reviewed. Activation (KMS or MAK). RDP checked. SQL services start |  |
| 5 | OS hand-off to the DBA | Record on the server page: final OS version, hardening done, snapshots kept, anything unusual seen. Tell the DBA | Accepts the server. From here, the DBA is responsible |
| 6 | SQL to a newer version | Available for OS issues | SQL upgrade in place, or a new instance on the same server, then data validation and app test (DBA §6.1) |
| 7 | Clean up after Gate 3 | Delete the snapshots; remove Windows.old with Disk Cleanup |  |

Rollback: revert to the snapshot taken before the failed hop. If a clone was used, its timings size the change window.

Note An in-place upgrade doesn't create a new server, so there's no Phase 2 build in the usual sense. Phase 2 becomes preparing the source (step 1), and the hardening in step 6 replaces the standard build's security settings.

### 6.2 Retire: when Discovery shows the server isn't used

If nobody and nothing uses the server any more, it isn't migrated at all. It goes straight to Phase 4 on the retire-only path (governance, retire-only path).

Evidence the sysadmin brings to Gate 1:

| Check | "Not used" looks like |
| --- | --- |
| Inbound connections during the capture week | None, apart from monitoring, backup and admin tools |
| SMB sessions and open files | None on the shares |
| Interactive and service logons (Security log) | Only admins and service accounts |
| FTP logs | No transfers in the retained logs |
| Scheduled tasks | Only maintenance (cleanup, defrag, backup); no business jobs, or the jobs' output isn't used by anyone |
| IIS logs (if any) | No requests, or only health checks |
| DNS aliases pointing to it | None, or the systems that use them confirmed retired |
| Monthly or quarterly jobs | Each one checked with its owner: not needed |

Important The sysadmin brings the evidence; the app owner decides. "No connections in a week" isn't proof on its own. The app owner confirms in writing that the service is no longer needed and decides what happens to the data.

Sysadmin tasks on the retire-only path:

☐  Announce the retirement date and a contact to the users and teams found in Discovery

☐  Carry out the data decision for the file shares (archive, hand over, or delete under the retention policy), after a last full backup

☐  Scream test: stop the services or disable the NIC, so it can be undone in minutes. At least 4 weeks, including a month-end

☐  If someone is affected: re-enable, record the missed dependency, and go back to Gate 1

☐  If nobody is affected: wait for the DBA's confirmation (if SQL is on it), power off, then the removal checklist (section 7, Phase 4)

———   ◆   ———

## 7. Tasks by phase

### Phase 1 · Discovery

Details and commands: governance §1.2 – 1.5.

☐  Run the server discovery script (yours or the reference one); output in Migration/<BUNDLE>/<SERVER>/1-Discovery/

☐  Platform, identity, software, roles, services, scheduled tasks (monthly or quarterly ones listed with an owner)

☐  Network: IPs, DNS aliases, hosts entries, listening ports, connection capture for the Discovery week

☐  Certificates, backup, monitoring and AV agents

☐  Legacy protocols: SMBv1 (server, clients, as a client), TLS, NTLMv1, telnet, SNMP. All documented

☐  FTP: every flow, its partner, where the files land on the file shares, and what processes them. Listed for MFT

☐  Files and shares: sizes, data by age, open-file sessions, orphaned home folders, risky file types

☐  Server flags written to the summary file; OS path chosen with the DBA (section 4); sign the Gate 1 part

### Phase 2 · Install & configure

☐  Server from the standard build, patched, in the right OU

☐  Disk layout to standard, including the SQL volumes the DBA asked for (64 KB allocation unit)

☐  Service accounts or gMSAs; passwords in the vault; IFI and lock pages in memory rights for SQL

☐  Roles and features from Discovery (IIS, .NET 3.5, MSMQ, …)

☐  SMBv1 off, TLS 1.2+ only, NTLMv1 refused, unless an exception is logged

☐  MFT flows set up for every FTP flow found

☐  Certificates (SHA-256, 2048-bit+); firewall rules requested from Security / Network

☐  Backup, monitoring, AV/EDR (with the DBA's exclusions), patching agents

☐  Scheduled tasks prepared but disabled

☐  Service recovery actions on critical services (lab finding: they aren't set by default for old software)

### Phase 3 · Migration

☐  If the path is uncertain: clone and isolate the production VM, and rehearse the OS steps on it, timed (when to clone)

☐  OS in-place upgrade on production (snapshot per hop), hardening, then the OS hand-off to the DBA, recorded on the server page

☐  File shares: robocopy with /COPYALL, a preliminary pass days before, then a final delta during the freeze

☐  Scheduled tasks enabled on the target, disabled on the source

☐  MFT flows switched over and tested with each partner; FTP service on the old server stopped

☐  DNS and aliases switched after the DBA's go; the old name kept as a CNAME only if the app needs it

☐  Every Discovery dependency tested: scanners, MFT partners, interfaces, reports

☐  Legacy-protocol flags closed, or covered by a logged exception

☐  Monitoring green for 48 h

### Phase 4 · Decommissioning

☐  Quiet period (or scream test for a retire): connection capture still running on the old server, including a month-end

☐  File-share data decision carried out: archive, hand over or delete, signed by the data owner

☐  Wait for the DBA's confirmation that the databases are offline and backed up

☐  Server powered off, not deleted, for the agreed wait; final backup kept, with a restore test

☐  Removed from AD, DNS, DHCP, firewall, monitoring, backup, AV/EDR, patching, CMDB; licences reclaimed; service accounts disabled; certificates revoked

☐  VM deleted or hardware disposed of, disks wiped

———   ◆   ———

Sysadmin guide · part of the migration governance · lab evidence in legacy-migration

MIGRATION GOVERNANCE · ROLE GUIDE # DBA Guide SQL Server 2000 – 2025 · instances, databases, migration paths ● DISCOVERY — ● INSTALL & CONFIGURE — ● MIGRATION — ● DECOMMISSIONING

Role guide for DBAs · the governance guide is the big picture; this page is what the DBA owns · the sysadmin side is in the Sysadmin guide

Important The DBA owns everything inside the SQL Server instance: engine, databases, logins, jobs, packages, and the data's integrity before and after the move. The sysadmin owns everything around it: the server, the OS, disks, network, files and protocols. You work together, but each side signs for its own part.

———   ◆   ———

## 1. Supported vs works but not supported

These two words tell you who carries the risk. Whether a clone is needed depends on something else: how certain the path is (when to clone).

|  | SUPPORTED | WORKS, BUT NOT SUPPORTED |
| --- | --- | --- |
| Meaning | Microsoft lists the combination. SQL version, service pack and Windows version are in Microsoft's compatibility matrix | It runs, and we proved it in the lab, but Microsoft doesn't list it (or lists it as "not supported") |
| Fixes and security updates | Yes. Bugs and vulnerabilities in this combination get fixed | No. If it breaks because of the combination, nobody fixes it |
| Microsoft support case | Accepted | Can be refused. The first answer is "move to a supported configuration" |
| Approval | Normal gate | Normal gate. No exception, not a blocker. If the path is uncertain, it runs on a cloned VM first |
| Can it be the end state? | Yes | No. A step on the way to a newer, supported SQL version |
| Who carries the risk | Shared with the vendor | Us alone, which is why an uncertain path is proven on a clone first |

Important Every migration ends on a newer, supported SQL version. An unsupported step on the way is allowed. Clone only when the path is uncertain: not yet done in the lab or the program, something unusual found on this server, or you're not confident. A proven path goes straight to production, with a snapshot before each step (governance §2.7).

On the DBA side, it typically looks like this:

- SQL 2005 still running on Windows Server 2012 R2 or 2025. Our lab ran it there after in-place OS upgrades, with a clean DBCC CHECKDB, crash recovery and fault injection passed. But the engine is out of support, the combination is unsupported, and SQL 2005 only does TLS 1.0 at login. Clients need a TLS 1.0 exception too (governance §2.6).

- SQL 2005 on Windows Server 2008 (not R2). The combination was supported (SQL 2005 SP2 or later), but both products are out of support: SQL 2005 since 2016, Windows 2008 since 2020. There are no fixes for either, so it's in the same risk position as an unsupported combination. TLS 1.0 at login applies here too. The way out:

  - Data: the databases restore directly on SQL 2022 or 2025, which is supported (5.1).

  - OS in place, if the server is x64: 2008 → 2012 → 2016 → 2025, with SQL 2005 kept running (form A, 6.1). Not tested in our lab: the lab chain started from 2008 R2. Clone first.

  - If the server is 32-bit (x86): there's no in-place path, because Windows 2012 and later are x64 only. Side-by-side.

- SQL 2016 on Windows Server 2022, or SQL 2017 on Windows Server 2025. It installs and runs, but Microsoft lists both as "not supported". Pick SQL 2019 or later for those OS versions.

- A restore from SQL 2005 to SQL 2022 or 2025 is supported. The database is raised to compatibility level 100 automatically. This is the supported way off SQL 2005; no extra hop is needed.

———   ◆   ———

## 2. Your responsibilities

A = accountable (signs for it), R = does the work, C = consulted. The full RACI with every role is in the governance guide §2.3.

| Phase | DBA is A for | DBA is R for | DBA is C for |
| --- | --- | --- | --- |
| 1 · Discovery | SQL discovery script and output; SQL flags | Connection and activity capture inside SQL; dependency list (SQL side) | Server discovery; legacy protocols (TLS for SQL clients) |
| 2 · Install & configure | SQL install and configuration on the target | Smoke test (SQL side) | Server build (disk layout, service accounts) |
| 3 · Migration | Everything SQL after the OS hand-off: SQL upgrade or new instance, data migration and validation, app test with the app owner, up to Gate 3 | Rehearsal (on a clone if uncertain); cut-over and rollback plan (SQL side) | The OS in-place upgrade (done by the sysadmin); DNS / alias switch timing |
| 4 · Decommissioning | Instance decommissioning: databases offline, final backups, logins disabled | Quiet-period monitoring inside SQL | Server removal |

What the DBA signs at each gate

| Gate | DBA signature covers |
| --- | --- |
| Gate 1 | SQL summary reviewed; every SQL RED flag decided; migration path chosen (section 5) |
| Gate 2 | Instance built to standard; logins, jobs, linked servers scripted; backup and restore proven on the target |
| Gate 3 | Data validated (row counts, CHECKDB, key reports); jobs running; first backup and restore on the target |
| Gate 4 | Databases offline then final backup kept; instance stopped; SQL licence released |

———   ◆   ———

## 3. Hand-offs with the sysadmin

Three hand-off points (governance §2.2):

- After Discovery (Gate 1): OS path and SQL path agreed together.

- OS hand-off: the sysadmin finishes the OS in-place upgrade and hardening, then hands the server over. From then on, the DBA is responsible up to Gate 3.

- Before decommissioning: the DBA confirms the databases are offline and backed up; then the sysadmin removes the server.

Most delays happen between the two roles. Ask early, using this list.

| DBA needs from the sysadmin | Sysadmin needs from the DBA |
| --- | --- |
| Target server built, with disk layout for SQL: data, log, tempdb and backup volumes, 64 KB allocation unit | SQL port(s) and Browser need, for the firewall rules |
| Service accounts or gMSAs created, passwords in the vault, with instant file initialization and lock pages in memory rights | AV exclusions for data, log and backup files and sqlservr.exe |
| Backup agent installed; backup share reachable | Backup schedule and retention for the agent |
| Firewall rules for 1433 / named instance ports | Which apps and servers connect to SQL (from the capture), for the dependency list |
| DNS alias switch at the agreed time in cut-over | Go / no-go on the SQL side before the DNS switch |
| TLS certificate for SQL encryption | TLS level needed by SQL clients (legacy 2005 clients need TLS 1.0) |
| Server kept powered on during the quiet period | Confirmation that databases are offline before power-off |

———   ◆   ———

## 4. SQL Server on Windows Server

| SQL \ Windows | 2003 | 2008 | 2008 R2 | 2012 | 2012 R2 | 2016 | 2019 | 2022 | 2025 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SQL 2000 | Yes · SP3 | unsupported | unsupported | unsupported | unsupported | unsupported | unsupported | unsupported | unsupported |
| SQL 2005 | Yes · RTM | Yes · SP2 | Yes · SP3 | unsupported | LAB OK | unsupported | unsupported | unsupported | LAB OK |
| SQL 2008 | Yes · RTM | Yes · RTM | Yes · SP1 | Yes · SP4 | Yes · SP4 | unsupported | unsupported | unsupported | unsupported |
| SQL 2008 R2 | Yes · RTM | Yes · RTM | Yes · RTM | Yes · SP3 | Yes · SP3 | unsupported | unsupported | unsupported | unsupported |
| SQL 2012 | not possible | Yes · RTM | Yes · RTM | Yes · SP4 | Yes · SP4 | Yes · SP4 | Yes · SP4 | unsupported | unsupported |
| SQL 2014 | not possible | Yes · RTM | Yes · RTM | Yes · SP3 | Yes · SP3 | Yes · SP3 | Yes · SP3 | unsupported | unsupported |
| SQL 2016 | not possible | not possible | not possible | Yes · SP3 | Yes · SP3 | Yes · SP3 | Yes · SP3 | unsupported | unsupported |
| SQL 2017 | not possible | not possible | not possible | Yes · RTM | Yes · RTM | Yes · RTM | Yes · RTM | Yes · RTM | unsupported |
| SQL 2019 | not possible | not possible | not possible | not possible | not possible | Yes · RTM | Yes · RTM | Yes · RTM | Yes · RTM |
| SQL 2022 | not possible | not possible | not possible | not possible | not possible | Yes · RTM | Yes · RTM | Yes · RTM | Yes · RTM |
| SQL 2025 | not possible | not possible | not possible | not possible | not possible | not possible | Yes · RTM | Yes · RTM | Yes · RTM |

|  | Supported by Microsoft (minimum SQL service pack) |  | Unsupported, proven in our lab |
| --- | --- | --- | --- |
|  | Unsupported, not tested |  | Not possible (setup requires a newer OS) |

How to read it

- Yes · SP4 = supported by Microsoft, with at least that SQL service pack. Source: Microsoft, SQL Server and Windows compatibility matrix (KB 2681562, updated 2026-08-05). Windows 2003, 2008 and 2008 R2 aren't in that article any more. Those cells come from each SQL version's archived hardware and software requirements; check the exact minimum service pack there before relying on it.

- LAB OK = not supported, but proven in our lab: SQL 2005 SP4 kept running through in-place OS upgrades 2008 R2 → 2012 R2 → 2025. See section 5.3.

- unsupported = Microsoft doesn't support it and we haven't tested it. Don't plan on it.

- not possible = the SQL version needs a newer Windows; setup won't install it there.

Note Every SQL version up to 2016 is already out of support itself, wherever it runs (governance §1). A "supported" cell for those means the combination was supported, not that the product still gets updates.

Targets to choose for a new build

| Target Windows | Supported SQL to install | Recommended |
| --- | --- | --- |
| Windows Server 2025 | SQL 2019, 2022, 2025 | SQL 2022 or 2025 |
| Windows Server 2022 | SQL 2017, 2019, 2022, 2025 | SQL 2022 or 2025 |
| Windows Server 2019 | SQL 2012 SP4 to 2025 | Only if the OS is imposed; SQL 2022 |

———   ◆   ———

## 5. Migration paths

### 5.1 From each source version to SQL 2022 / 2025

| SQL 2000 compat 80 | → | ▸ restore: Hop instance SQL 2008 R2 (lab / temporary) |
| --- | --- | --- |
| Hop instance SQL 2008 R2 (lab / temporary) | → | ▸ set compat 100, back up, restore: SQL 2022 / 2025 on Windows 2022 / 2025 |
| SQL 2022 / 2025 on Windows 2022 / 2025 | → | end |
| SQL 2005 compat 90 | → | ▸ restore (auto compat 100): SQL 2022 / 2025 on Windows 2022 / 2025 |
| SQL 2008 / 2008 R2 | → | ▸ restore or log shipping: SQL 2022 / 2025 on Windows 2022 / 2025 |
| SQL 2012 SP4 | → | ▸ restore (in-place only to 2022): SQL 2022 / 2025 on Windows 2022 / 2025 |
| SQL 2014 – 2019 | → | ▸ restore or in-place upgrade: SQL 2022 / 2025 on Windows 2022 / 2025 |

| Source | Supported path to SQL 2022 / 2025 | Minimal-downtime option | Watch out for |
| --- | --- | --- | --- |
| SQL 2000 (compat 80) | Two hops. Restore on a temporary SQL 2008 R2 instance, raise to compat 100, back up, restore on 2022 / 2025 | None: plan a full outage | DTS packages need a rewrite to SSIS. No direct path exists |
| SQL 2005 (compat 90) | Direct backup / restore on 2022 or 2025, which raises the database to compat 100 | Differential + log backups restored before cut-over | No log shipping from 2005 to 2022/2025. Old clients may need TLS 1.0 on the source until cut-over |
| SQL 2008 SP3+ / 2008 R2 SP2+ | Direct backup / restore | Log shipping to 2022 / 2025 is supported | Once the new server is primary, the old one can't receive changes back. Rollback = the untouched source |
| SQL 2012 SP4 | Backup / restore to 2022 or 2025. In-place upgrade only to 2022, and only if the OS supports SQL 2022 | Log shipping, or AG (Enterprise) | In-place: the OS must be Windows 2016+, and SQL 2012 often sits on 2012 R2 |
| SQL 2014 SP3 / 2016 SP3 | Backup / restore, or in-place upgrade to 2022 / 2025 | Log shipping, AG | In-place to 2025 needs Windows 2019+ under it |
| SQL 2017 / 2019 | Backup / restore, or in-place upgrade to 2022 / 2025 | Log shipping, AG, distributed AG | SQL 2017 isn't supported on Windows 2025 |

Sources: Microsoft, Supported version and edition upgrades for SQL Server 2022 and SQL Server 2025: direct migration from compatibility level 90+; in-place upgrade from 2012 SP4 (to 2022) or 2014 SP3 (to 2025); log shipping from 2008 SP3 / 2008 R2 SP2.

Warning A restore upgrades the database one way. A backup taken on SQL 2022 can't be restored on the old version. The rollback is always the untouched source instance, kept read-only and available until Gate 3.

### 5.2 Choosing the method

In-place first, whenever a supported path exists. Side-by-side second (governance §3.1). Clone first only when the path is uncertain (when to clone).

| Situation | Method |
| --- | --- |
| A supported in-place SQL path exists (to 2022 from 2012 SP4+, to 2025 from 2014 SP3+) and the OS supports the target SQL | 1st choice: in-place SQL upgrade (supported, so normally no clone). Rollback = the VM snapshot |
| The OS is upgraded in place, but the SQL version can't be upgraded in place (SQL 2005, 2008, 2008 R2) | Keep the server, change the instance: install a new SQL 2022 / 2025 instance on the upgraded server, then restore the databases into it (5.1). Clone first |
| 2nd choice: side-by-side, small or medium database, outage window of a few hours | Full backup → restore, then a final differential or log backup at cut-over |
| Large database, short window, source 2008 SP3+ | Log shipping, then a final log backup and recovery at cut-over |
| Many databases, logins and jobs on one instance | dbatools from the admin workstation: Copy-DbaLogin, Copy-DbaAgentJob, Copy-DbaLinkedServer, Copy-DbaDatabase |
| SQL 2000 | Hop instance (5.1) and a full outage |
| The app can't move yet, but the OS must leave 2008 R2 | Interim step: the lab path in 5.3. The sysadmin does the OS part; the DBA takes over at the OS hand-off |

### 5.3 Lab-proven interim path: keep SQL, upgrade the OS under it

NOT SUPPORTED. Proven in our lab. A step on the way to a newer SQL version. Because it's lab-proven, a clone is needed only if Discovery found something unusual on the server (when to clone).

In the lab, a SQL Server 2005 SP4 instance with a live application stayed in place while the sysadmin upgraded Windows 2008 R2 SP1 → 2012 R2 → 2025 in place. Nothing was reinstalled or restored. The OS upgrade itself is the sysadmin's runbook (Sysadmin guide §5).

| Lab check (on Windows 2025) | Result |
| --- | --- |
| SQL services, logins, databases after each OS hop | Kept, untouched. @@VERSION shows the wrong Windows name (cosmetic) |
| Service stop / start | Stopped in about 3 s, restarted cleanly; app reconnected |
| Hard kill of sqlservr.exe | Crash recovery in about 1 s; DBCC CHECKDB clean |
| Disk full | Reads fine; writes failed with the correct errors (9002, 3202); full recovery |
| Memory pressure (to about 900 MB free) | Kept answering; full recovery |
| Weakness found | No service recovery actions: after a crash, SQL stayed down. Fixed with sc failure (below), and re-tested: back in 13.5 s with no manual action |

Full details: lab runbook and stability showcase.

Conditions for using it in production

☐  Clone first if this server is uncertain (when to clone); otherwise a snapshot before each OS step. Steps and timings recorded on the server page

☐  Server LAN-only and firewalled; no internet access

☐  Service recovery set on every SQL service:

sc failure MSSQLSERVER reset= 86400 actions= restart/5000/restart/10000/restart/30000 sc failure SQLBrowser reset= 86400 actions= restart/5000/restart/10000/restart/30000

☐  TLS 1.0 exception for the SQL clients, if any client still needs it

☐  Exit plan with a date: restore the databases on a supported SQL version (2005 → 2022/2025 is direct, 5.1). This can be a new SQL 2022 or 2025 instance on the same upgraded server, or a new server.

Note Moving the databases to a new SQL 2022 instance on the same upgraded server hasn't been tested in the lab yet. It's the next lab test before the end-state step is offered as a standard path.

———   ◆   ———

## 6. Options after Discovery

Discovery ends with one of three options for each server or database, decided at Gate 1 (governance §1.10):

| Discovery results | → | ▸ Is the database still used? |
| --- | --- | --- |
| Is the database still used? | → | ▸ no: Retire 6.2 ▸ yes: In-place path exists? |
| Retire 6.2 | → | end |
| In-place path exists? | → | ▸ yes: 1st: in-place 6.1 · clone if uncertain ▸ no: 2nd: side-by-side restore on a new server |
| 1st: in-place 6.1 · clone if uncertain | → | ▸ clone test fails: 2nd: side-by-side restore on a new server |
| 2nd: side-by-side restore on a new server | → | end |

### 6.1 In-place upgrade, step by step

Important The OS in-place upgrade is done by the sysadmin (Sysadmin §6.1). The DBA's part during the OS work is small: full backups before the first hop, and a quick SQL check after each hop. When the sysadmin hands the server over (the OS hand-off), the DBA becomes responsible for the rest: SQL to a newer version, data validation, and the app test with the app owner, up to Gate 3.

"In-place" means the server stays. For the DBA it takes one of three forms, depending on the SQL version:

| Form | When | What the DBA does |
| --- | --- | --- |
| A. OS upgraded under SQL | The sysadmin upgrades Windows in place (Sysadmin §6.1) | Backups before, a quick SQL check after each hop; take over at the OS hand-off |
| B. SQL upgraded in place | A supported SQL upgrade path exists: to 2022 from 2012 SP4, 2014 SP3, 2016 SP3, 2017, 2019; to 2025 from 2014 SP3 onwards. And the OS supports the target SQL | Run SQL setup in upgrade mode |
| C. New instance on the same server | SQL can't be upgraded in place (SQL 2005, 2008, 2008 R2), but the server stays | Install a new SQL 2022 / 2025 instance next to the old one; restore the databases into it (5.1) |

Usual combination for old servers: A, then C. The OS goes 2008 R2 → 2012 R2 → 2025 with SQL 2005 kept running (A, lab-proven), then the databases move to a new SQL 2022 instance on the same server (C), and the SQL 2005 instance is removed.

Steps for each form (on a clone first only if the path is uncertain):

| # | A. OS upgraded under SQL | B. SQL upgraded in place | C. New instance on the same server |
| --- | --- | --- | --- |
| 1 | Full backups of all databases, system databases included; script logins and jobs | Full backups; check the prerequisites: no pending restart, Agent account in sysadmin, supported edition path | Full backups; script logins (with SIDs), jobs, linked servers |
| 2 | Note the baseline: version, databases, logins, jobs, row counts of key tables | Run Data Migration Assistant from the admin workstation for breaking changes | Install the new instance (named, or default after the old one is removed); standard configuration |
| 3 | The sysadmin runs the OS hop | Run SQL setup in upgrade mode | Restore the databases; recreate logins, jobs and linked servers (dbatools) |
| 4 | After each hop: quick check (services up, connection works). After the OS hand-off: error log, DBCC CHECKDB, app test | After setup: error log, DBCC CHECKDB, UPDATE STATISTICS, app test | DBCC CHECKDB, orphaned users fixed, app connection string or alias pointed to the new instance, app test |
| 5 | Set service recovery actions (sc failure, lab finding) | Compatibility levels unchanged; raise them later, after validation, with Query Store on | Old instance stopped and kept as the rollback until Gate 3, then uninstalled |
| Rollback | VM snapshot before the hop | VM snapshot; an in-place SQL upgrade can't be undone otherwise | The old instance, untouched |

Note Form C hasn't been tested in our lab yet (see the note in 5.3), so it's uncertain: run it on a clone first until it has worked once.

### 6.2 Retire: when Discovery shows a database isn't used

If nobody and nothing uses a database or a whole instance any more, it isn't migrated. It goes straight to Phase 4 on the retire-only path (governance, retire-only path). A server can also be split: some databases migrate, the others retire.

Evidence the DBA brings to Gate 1:

| Check | "Not used" looks like |
| --- | --- |
| Connection capture during the Discovery week | No user connections to the database, apart from maintenance and backup |
| sys.dm_db_index_usage_stats (2005+) | No reads or writes since the last restart, and the instance has been up for a long time (the stats reset on restart) |
| Login auditing / error log | No successful logins by application accounts |
| Agent jobs | Only maintenance jobs touch it; no business jobs, or their output isn't used |
| Linked servers and cross-database queries | No other instance or database reads from it (check the other instances' linked servers) |
| SSRS / SSIS | No reports or packages use it as a data source |
| Size and last write | Data and log files not growing; last full backup the same size for months |

Important The DBA brings the evidence; the app owner decides. Retention rules may still require the data: retire doesn't mean delete. The app owner, or the data owner, decides whether the database is archived, handed over or deleted.

DBA tasks on the retire-only path:

☐  Final full backup of each database, kept per retention, with a restore test

☐  Set the database offline (not dropped), so it can come back in minutes

☐  During the scream test (at least 4 weeks, including a month-end): watch the error log for failed logins to the offline database. Any attempt is a missed dependency

☐  If someone is affected: bring it back online, record the dependency, and go back to Gate 1

☐  If nobody is affected: carry out the data decision (archive copy kept, or drop under the retention policy), then stop and uninstall the instance if nothing else is on it, and release the SQL licence

☐  Confirm to the sysadmin that the server can be powered off

———   ◆   ———

## 7. Audit logging

### 7.1 What an audit log is

An audit log is a record of who did what, when, and from where on the instance, kept so it can be checked later. For SQL Server it covers four kinds of events:

| Kind | Examples | Why it matters |
| --- | --- | --- |
| Logins | Successful and failed logins: login name, client host, application, time | Who uses the instance; brute-force attempts; dependency discovery during migration |
| Security changes | Logins created or dropped, role membership, GRANT / DENY / REVOKE, password changes | Privilege escalation; Cyber and audit requirements |
| Schema changes (DDL) | CREATE / ALTER / DROP of tables, procedures, databases | Unplanned changes; troubleshooting after a release |
| Data access (DML) | SELECT / INSERT / UPDATE / DELETE on sensitive tables | Compliance for personal or financial data. Costly: only on the tables that need it |

An audit log is not the transaction log (that's for recovery), and not the error log, although the error log can hold login events (7.3).

### 7.2 What each version supports

| Version | Native SQL Server Audit | Other built-in options |
| --- | --- | --- |
| SQL 2000 | None | SQL Trace (server-side), C2 audit mode, login auditing to the error log, DML triggers |
| SQL 2005 | None | Same as 2000, plus the default trace, DDL triggers, logon triggers (SP2+), event notifications, Common Criteria compliance (SP2, Enterprise) |
| SQL 2008 / 2008 R2 | Enterprise only (server and database level) | Standard edition: the 2005 options, plus Extended Events |
| SQL 2012 / 2014 | Server level: all editions. Database level: Enterprise only | Audit filtering, user-defined audit events, Extended Events |
| SQL 2016 SP1 – 2025 | Server and database level: all editions | Extended Events; temporal tables (data history, 2016+); ledger (tamper-evident tables, 2022+) |

Important On the target (SQL 2022 / 2025), use SQL Server Audit. It's built in, cheap, and covers all four kinds. The workarounds in 7.3 are for the source servers until they're migrated, and for discovery.

### 7.3 Options on versions without SQL Server Audit

Use several light options together. None of them alone covers everything, and none is as complete as SQL Server Audit.

| Option | Versions | Covers | Cost and risks |
| --- | --- | --- | --- |
| 1. Login auditing to the error log | 2000+ | Successful and failed logins | Very low. The error log grows: recycle it daily and keep 30 files |
| 2. Default trace | 2005+ | Object created, altered, dropped; logins and users added; some permission changes; DBCC; server config changes | On by default, almost free. Only 5 files × 20 MB that roll over: copy them off regularly |
| 3. Server-side SQL Trace (audit events only) | 2000+ | Logins, failed logins, security changes, DDL. DML on chosen tables possible | Low when filtered to audit events. Never use the Profiler GUI for this. Must be restarted after a SQL restart (startup procedure) |
| 4. DDL triggers | 2005+ | All DDL, with the full statement (EVENTDATA()) into an audit table | Low. A broken trigger blocks all DDL: test on the clone |
| 5. Logon trigger | 2005 SP2+ | Logins, with host and application | A broken logon trigger locks everyone out. Recovery needs the DAC. Use only if 1 and 3 aren't enough |
| 6. DML triggers on sensitive tables | 2000+ | Data changes on those tables | Adds cost to every write; not for SELECT |
| 7. C2 audit mode / Common Criteria | 2000+ / 2005 SP2 Ent. | Everything | Heavy. The instance stops if the audit disk fills. Last resort only |
| 8. Network and OS side (sysadmin) | Any | Who connects to the SQL port, from where | Windows Security log, firewall logs; no SQL detail |

Recommended set for a legacy source server: 1 + 2 + 3, with the files copied off the server every day (to the log server or SIEM), so they survive a disk failure and are harder to tamper with. Add 4 where schema changes matter.

Warning None of these is tamper-proof. A sysadmin on the instance can stop a trace, disable a trigger or delete files. That's why the files are copied off the server daily, and why the target uses SQL Server Audit. On the decision log, record what the legacy server has as a compensating control, not as a full audit.

▾ Scripts: login auditing, error-log retention, default trace (2005+)

-- 1. Login auditing: both failed and successful logins (3 = both). Takes effect after a SQL restart. EXEC xp_instance_regwrite N'HKEY_LOCAL_MACHINE', N'Software\Microsoft\MSSQLServer\MSSQLServer', N'AuditLevel', REG_DWORD, 3; -- Keep 30 error logs, and recycle daily (add sp_cycle_errorlog to a daily Agent job) EXEC xp_instance_regwrite N'HKEY_LOCAL_MACHINE', N'Software\Microsoft\MSSQLServer\MSSQLServer', N'NumErrorLogs', REG_DWORD, 30; EXEC sp_cycle_errorlog;

-- 2. Read the default trace (2005+) DECLARE @path nvarchar(260); SELECT @path = REVERSE(SUBSTRING(REVERSE(path), CHARINDEX('\', REVERSE(path)), 260)) + N'log.trc' FROM sys.traces WHERE is_default = 1; SELECT t.StartTime, e.name AS event, t.LoginName, t.HostName, t.ApplicationName, t.DatabaseName, t.ObjectName FROM fn_trace_gettable(@path, DEFAULT) AS t JOIN sys.trace_events AS e ON e.trace_event_id = t.EventClass ORDER BY t.StartTime DESC;

▾ Script: server-side audit trace that restarts with SQL (2000 and 2005)

USE master; GO -- Starts a rollover trace of audit events only. Marked as a startup procedure below. CREATE PROCEDURE dbo.usp_StartAuditTrace AS BEGIN DECLARE @id int, @on bit, @file nvarchar(245), @size bigint; SET @on = 1; SET @size = 100; -- MB per file SET @file = N'D:\SQLAudit\audit_' + CONVERT(nvarchar(8), GETDATE(), 112) + N'_' + REPLACE(CONVERT(nvarchar(8), GETDATE(), 108), ':', ''); -- 2 = TRACE_FILE_ROLLOVER. On SQL 2005+ you can add @filecount = 50 to cap the number of files. EXEC sp_trace_create @id OUTPUT, 2, @file, @size, NULL; -- Events: 14 Login, 20 Login failed, 102 DB scope GDR, 103 Object GDR, -- 104 Add login, 105 Login GDR, 106 Login change property, 107 Login change password, -- 108 Add login to server role, 109 Add DB user, 110 Add member to DB role, -- 46 Object created, 47 Object deleted, 164 Object altered DECLARE @events TABLE (e int); INSERT @events SELECT 14 UNION ALL SELECT 20 UNION ALL SELECT 102 UNION ALL SELECT 103 UNION ALL SELECT 104 UNION ALL SELECT 105 UNION ALL SELECT 106 UNION ALL SELECT 107 UNION ALL SELECT 108 UNION ALL SELECT 109 UNION ALL SELECT 110 UNION ALL SELECT 46 UNION ALL SELECT 47 UNION ALL SELECT 164; -- Columns: 1 TextData, 6 NTUserName, 8 HostName, 10 ApplicationName, 11 LoginName, -- 12 SPID, 14 StartTime, 21 EventSubClass, 34 ObjectName, 35 DatabaseName DECLARE @cols TABLE (c int); INSERT @cols SELECT 1 UNION ALL SELECT 6 UNION ALL SELECT 8 UNION ALL SELECT 10 UNION ALL SELECT 11 UNION ALL SELECT 12 UNION ALL SELECT 14 UNION ALL SELECT 21 UNION ALL SELECT 34 UNION ALL SELECT 35; DECLARE @e int, @c int; DECLARE ec CURSOR LOCAL FAST_FORWARD FOR SELECT e, c FROM @events CROSS JOIN @cols; OPEN ec; FETCH NEXT FROM ec INTO @e, @c; WHILE @@FETCH_STATUS = 0 BEGIN EXEC sp_trace_setevent @id, @e, @c, @on; FETCH NEXT FROM ec INTO @e, @c; END CLOSE ec; DEALLOCATE ec; EXEC sp_trace_setstatus @id, 1; -- start END GO EXEC sp_procoption N'dbo.usp_StartAuditTrace', 'startup', 'true'; EXEC dbo.usp_StartAuditTrace;

Create D:\SQLAudit first, writable by the SQL service account, on a volume that isn't the data or log volume. A daily Agent job or scheduled task copies the closed .trc files to the log server. Read them with fn_trace_gettable. Test on the clone first.

▾ Target: SQL Server Audit on SQL 2022 / 2025

USE master; CREATE SERVER AUDIT MigrationAudit TO FILE (FILEPATH = N'D:\SQLAudit\', MAXSIZE = 256 MB, MAX_ROLLOVER_FILES = 50) WITH (ON_FAILURE = CONTINUE); ALTER SERVER AUDIT MigrationAudit WITH (STATE = ON); CREATE SERVER AUDIT SPECIFICATION MigrationAuditSpec FOR SERVER AUDIT MigrationAudit ADD (FAILED_LOGIN_GROUP), ADD (SUCCESSFUL_LOGIN_GROUP), ADD (SERVER_ROLE_MEMBER_CHANGE_GROUP), ADD (DATABASE_ROLE_MEMBER_CHANGE_GROUP), ADD (SERVER_PERMISSION_CHANGE_GROUP), ADD (DATABASE_PERMISSION_CHANGE_GROUP), ADD (SERVER_PRINCIPAL_CHANGE_GROUP), ADD (DATABASE_PRINCIPAL_CHANGE_GROUP), ADD (SCHEMA_OBJECT_CHANGE_GROUP), ADD (DATABASE_OBJECT_CHANGE_GROUP), ADD (AUDIT_CHANGE_GROUP) WITH (STATE = ON); -- Read it SELECT event_time, action_id, succeeded, server_principal_name, client_ip, application_name, database_name, object_name, statement FROM sys.fn_get_audit_file(N'D:\SQLAudit\*.sqlaudit', DEFAULT, DEFAULT) ORDER BY event_time DESC;

Add a database audit specification for SELECT / UPDATE on sensitive tables only where compliance requires it.

———   ◆   ———

## 8. Tasks by phase

### Phase 1 · Discovery

Details and queries per version: governance §1.6 – 1.8.

☐  Run the SQL discovery script (yours or the reference one) from the admin workstation, using dbatools where possible

☐  Instance: version, edition, SP, collation, service accounts, port, configuration, trace flags

☐  Databases: size, compat level, recovery model, page verify, last CHECKDB, last backup

☐  Logins, orphaned users, jobs and their owners, linked servers, DTS / SSIS / SSRS, Database Mail, encryption keys

☐  Monthly and quarterly Agent jobs listed, each with an owner

☐  Connection capture inside SQL for the Discovery week, plus login auditing

☐  Migration path chosen per database (section 5), with supported or works, not supported, and proven or uncertain (clone), written next to it

☐  SQL flags written to the summary file; sign the Gate 1 part

### Phase 2 · Install & configure

☐  Supported SQL version on the target OS (section 4), at the latest CU

☐  Collation matches the source, or the change is documented

☐  Memory, MAXDOP, cost threshold for parallelism, tempdb files to standard

☐  Service accounts, SPNs, static port; service recovery actions set (lab finding)

☐  Backups, integrity checks and index maintenance jobs from the standard solution

☐  Logins scripted with their SIDs and password hashes (Copy-DbaLogin or sp_help_revlogin), disabled until cut-over

☐  Linked servers with non-personal credentials; Database Mail; operators and alerts

☐  Backup → restore tested on the target

### Phase 3 · Migration

☐  Take over at the OS hand-off (in-place) and record it on the server page. From here the DBA is responsible up to Gate 3

☐  Rehearsal, timed: on a clone if the path is uncertain (when to clone), otherwise on a test instance. Record the duration on the server page

☐  Source set read-only (or app stopped) before the final backup

☐  Restore; fix orphaned users (ALTER USER … WITH LOGIN = …); enable logins; enable jobs

☐  DBCC CHECKDB, then UPDATE STATISTICS with FULLSCAN on key tables

☐  Page verify set to CHECKSUM

☐  Row counts and key reports compared with the source

☐  Compatibility level raised only after validation, one database at a time. Enable Query Store first, so plan regressions are visible

☐  First backup on the target and a restore test

☐  Go / no-go for the DNS switch, given to the sysadmin

### Phase 4 · Decommissioning

☐  Source databases set offline (not dropped) for the quiet period

☐  Watch for login attempts on the old instance during the quiet period; any attempt is a missed dependency

☐  Final full backup of every database, kept per retention, with a restore test

☐  Instance stopped and services disabled; SQL licence released

☐  Confirm to the sysadmin that the server can be powered off

———   ◆   ———

DBA guide · part of the migration governance · lab evidence in legacy-migration

MIGRATION GOVERNANCE · CONTRIBUTOR GUIDE # Scripts & VS Code Bring your own script · one repository · Copilot ● PULL — ● WRITE & TEST — ● COMMIT — ● PUSH TO DEVELOP

Companion to the migration governance guide · for sysadmins and DBAs who write or run discovery and migration scripts

Important Use the script you know. Share it in the team repository. Your own script is welcome, as long as it follows the five rules in section 1 and is pushed to the repository before it runs on a production server.

———   ◆   ———

## 1. Bring your own script

Many of us already have discovery scripts that work. There's no need to rewrite them. What the migration needs is comparable output, safe execution and a record of what ran where.

### The five rules

| # | Rule | Why |
| --- | --- | --- |
| 1 | Standard output. Produce the standard file names, CSV columns and flag summary (governance guide §3.2–3.3) | Results can be compared across servers and bundles, and the summary is what gets reviewed |
| 2 | Checklist coverage. Collect the Discovery checklist items for your role, whatever the tool | Nothing is missed (SMBv1, FTP, monthly jobs, …) |
| 3 | Read-only. Discovery scripts never change anything on the server | Safety on production |
| 4 | No secrets. No passwords in scripts, config files or output. Credentials come from the vault or Get-Credential at run time | Security requirement |
| 5 | In the repository first. The version that runs on production is in the repository, and its version or commit is recorded in the summary | Answers "what ran on this server, with admin rights?" |

How a script is written (style, structure, language, tool) is up to its author. This is the starting point. The wanted path is a few standard scripts owned by the teams (section 7).

Tip Already have a script? Usually it only needs an export step at the end that writes the standard CSV names and the flag summary. That's often a short job, and Copilot can help (section 5). Don't have one? Use the reference script in discovery/reference/. It's optional; it covers 2003 to 2019, and runs on PowerShell 2.0 with the newer cmdlets used only where they exist.

### Script header

Every script starts with a short comment-based help block, so anyone can see what it does, what it needs and who to ask:

<# .SYNOPSIS Server discovery: services, tasks, shares, SMBv1, FTP. .DESCRIPTION Read-only. Writes <SERVER>_<area>_<yyyyMMdd>.csv and <SERVER>_SUMMARY_<yyyyMMdd>.csv to the output folder given in -OutputPath. .PARAMETER ComputerName Server to discover. Defaults to the local computer. .PARAMETER OutputPath Folder for the CSV files. .NOTES Author : <name> Version : 1.3.0 Requires : PowerShell 2.0+ (runs on 2008 R2); remote WMI for 2003 Changes : 1.3.0 - added SMBv1 client check .EXAMPLE .\Get-ServerDiscovery.ps1 -ComputerName APP01 -OutputPath D:\Discovery #>

———   ◆   ———

## 2. Repository layout

One repository for the whole team. Each author keeps their own folder, so nobody's work is overwritten and credit stays visible.

migration-scripts/ ├── README.md what's here, link to this guide ├── COPILOT-CONTEXT.md team context to paste into Microsoft 365 Copilot (see 5.2) ├── .github/ │ └── copilot-instructions.md team rules for GitHub Copilot, when licensed (see 5.6) ├── .gitignore keeps output and secrets out of Git ├── discovery/ │ ├── reference/ optional reference script (2003–2019) │ ├── <author>/ each person's own scripts │ │ ├── Get-ServerDiscovery.ps1 │ │ └── README.md one paragraph: what it covers, how to run it │ └── sql/ │ └── <author>/ DBA scripts (T-SQL, dbatools) ├── common/ │ └── Export-StandardOutput.ps1 shared export step for the standard CSVs └── checks/ └── Test-DiscoveryOutput.ps1 checks a SharePoint folder for missing files or columns

.gitignore: discovery output and credentials never go to Git.

# Discovery output belongs in SharePoint, not Git *.csv *.xlsx output/ # Credentials and local settings *.cred *.secret .env .vscode/settings.json

———   ◆   ———

## 3. Set up VS Code

You install it once, and it takes about 15 minutes. VS Code runs on your admin workstation, not on the legacy servers.

### 3.1 Install

You need two programs: VS Code (the editor) and Git for Windows (the version control that VS Code uses). VS Code doesn't include Git. Without Git, the Source Control view stays empty.

Important Install so that updates work without admin rights. VS Code ships an update every month, and Git for Windows a few times a year. Choose an install method that lets them update themselves, so nobody stays on an old version. If the company software portal (Company Portal / Software Center) has them, use that first: IT then handles the updates.

#### Visual Studio Code

| Method | Updates | Admin rights | Use it? |
| --- | --- | --- | --- |
| Microsoft Store | Automatic, through the Store | No | Recommended, if the Store is allowed on your PC |
| User Installer from the web | VS Code updates itself (it asks to restart) | No | Recommended if the Store is blocked |
| System Installer from the web | Each update needs an admin | Yes | Avoid: updates get stuck |

From the Microsoft Store

- Open the Microsoft Store app, search for Visual Studio Code, and check that the publisher is Microsoft Corporation.

- Click Get / Install.

- Updates arrive through the Store. To check: Store → Library → Get updates.

With the User Installer, if the Store is blocked

- Go to https://code.visualstudio.com/download.

- Under Windows, click User Installer, x64. Don't pick the System Installer.

- Run it. It installs to %LOCALAPPDATA%\Programs\Microsoft VS Code without asking for admin rights.

- On the Select Additional Tasks screen, tick:

  - Add "Open with Code" action to Windows Explorer file context menu

  - Add "Open with Code" action to Windows Explorer directory context menu

  - Add to PATH (already ticked)

- Updates: VS Code checks by itself, and shows a blue dot on the gear icon (bottom left) when one is ready. Click Restart to Update.

#### Git for Windows

Requirements: Windows 10 or 11, 64-bit. Admin rights aren't required: if you're not an administrator, the installer installs for your user only.

| Method | How |
| --- | --- |
| winget (simplest) | In PowerShell: winget install --id Git.Git -e --source winget. Later updates: winget upgrade --id Git.Git |
| From the web | https://git-scm.com/download/win → 64-bit Git for Windows Setup |

Microsoft doesn't publish Git for Windows in the Store; winget is its equivalent.

Installer options that matter. Accept the defaults, except where marked:

| Installer screen | Choose | Why |
| --- | --- | --- |
| Choosing the default editor | Use Visual Studio Code as Git's default editor ⬅ change | Commit messages open in VS Code, not Vim |
| Adjusting the name of the initial branch | Let Git decide (default) | The team branch comes from the repo anyway |
| Adjusting your PATH environment | Git from the command line and also from 3rd-party software (default) | Required: VS Code finds Git through the PATH |
| Choosing the HTTPS transport backend | Use the native Windows Secure Channel library ⬅ change | Uses the company's certificates. Avoids SSL errors behind the corporate proxy |
| Configuring line ending conversions | Checkout Windows-style, commit Unix-style (default) |  |
| Configure extra options / credential helper | Git Credential Manager (default; keep it) | Signs you in to Azure DevOps with your work account (3.2) |

Check that it worked. Close and reopen VS Code. Then in the terminal (` Ctrl+ ``):

git --version # e.g. git version 2.4x.x.windows.1 git credential-manager --version # shows a version, so the Azure DevOps sign-in will work

Keep Git up to date: run winget upgrade --id Git.Git, or git update-git-for-windows if you installed from the web. Once a quarter is enough.

#### Extensions

Open VS Code, go to Extensions (Ctrl+Shift+X) and install:

| Extension | What it does |
| --- | --- |
| PowerShell (Microsoft) | Syntax, IntelliSense, debugging, and PSScriptAnalyzer warnings as you type |
| GitHub Copilot (later) | Only once GitHub Copilot Business is licensed (5.6). Microsoft 365 Copilot doesn't need an extension |
| SQL Server (mssql) (Microsoft) | For DBAs: run T-SQL against an instance from VS Code |
| GitLens (optional) | Shows who changed each line and when |

Extensions update themselves.

#### Tell Git who you are

Do this once. In the terminal (` Ctrl+ ``):

git config --global user.name "First Last" git config --global user.email "first.last@company.com"

### 3.2 Connect to Azure DevOps and get the repository

You don't need an extension, a password or a token. Git for Windows includes the Git Credential Manager, which signs you in to Azure DevOps with your work account, the same one as Outlook and Teams.

| Azure DevOps Repos → Clone | → | Clone in VS Code (or copy the HTTPS URL) | → | Choose a local folder C:\Repos | → | Sign in once with your work account | → | Switch to develop |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Step by step

- In the browser, open Azure DevOps → your project → Repos → Files, and select the scripts repository at the top.

- Click Clone (top right). Then either:

  - click Clone in VS Code, and allow the browser to open VS Code; or

  - copy the HTTPS URL. In VS Code, press Ctrl+Shift+P, type Git: Clone, and paste the URL.

- Choose a local folder, for example C:\Repos.

- A Microsoft sign-in window appears the first time. Sign in with your work account. Git remembers it, and you won't be asked again.

- When VS Code asks "Would you like to open the cloned repository?", click Open.

- Switch to the team branch: click the branch name in the bottom-left corner of VS Code (it probably shows main), then choose origin/develop. The status bar now shows develop.

Caution Don't clone into OneDrive (Desktop or Documents are often synced). OneDrive and Git both manage the same files and cause conflicts. Use a plain local folder such as C:\Repos.

Note Use HTTPS, not SSH, and don't use Generate Git Credentials in Azure DevOps unless the tech lead asks you to. The Credential Manager sign-in is enough.

### 3.3 Where things are

| Shortcut | Opens |
| --- | --- |
| Ctrl+Shift+E | Explorer (files) |
| Ctrl+Shift+G | Source Control: changes, commit, push |
| ` Ctrl+ `` | Terminal (PowerShell) |
| Ctrl+Shift+P | Command palette (every command) |
| F5 / F8 | Run the script / run the selected lines |

Note PowerShell 2.0 targets. VS Code runs your script with the workstation's PowerShell 5.1 or 7. That's fine for editing and syntax checks, but test on a real 2008 / 2008 R2 server, or a lab copy, before running it in a bundle. A cmdlet that works on your workstation may not exist there.

———   ◆   ———

## 4. Daily workflow on develop

For now, the team works on one branch: develop. Everyone pulls from it and pushes to it. That keeps things simple, as long as everyone pulls before starting and pushes small changes often.

| main | ● reference script | ── | ── | ── | ── |
| --- | --- | --- | --- | --- | --- |
| develop | ── | ● alice: SMBv1 check | ● bob: SQL jobs export | ● alice: FTP scripts scan | ● carol: standard CSV export |

### 4.1 Words you'll see

| Word | Meaning |
| --- | --- |
| Repository (repo) | The shared folder of scripts, with its full history, stored in Azure DevOps |
| Clone | Your local copy of the repo, made once (3.2) |
| Branch | A line of work. The team uses develop |
| Pull | Bring your colleagues' latest changes from Azure DevOps to your PC |
| Stage | Choose which changed files go into the next commit |
| Commit | Save a snapshot of your staged changes on your PC, with a message. Nobody else sees it yet |
| Push | Send your commits to Azure DevOps, so the team gets them |
| Sync | VS Code's button that does a pull and then a push |
| origin | Git's name for the Azure DevOps copy of the repo |

| Azure DevOps develop | → | ▸ Pull: Your PC C:\Repos\... |
| --- | --- | --- |
| Your PC C:\Repos\... | → | ▸ Stage + Commit (local snapshot): Your PC C:\Repos\... ▸ Push: Azure DevOps develop |

### 4.2 Your first commit and push, step by step

An example: adding your existing discovery script to the repo.

1. Get the latest version. Open Source Control (Ctrl+Shift+G), click ... at the top, then Pull. You can also click the circular arrows next to develop in the status bar.

2. Add your script. In Explorer (Ctrl+Shift+E), right-click discovery → New Folder → your name (for example jdoe). Drag your .ps1 file from Windows Explorer into that folder, or create it with New File. Add a short README.md next to it.

3. See what changed. Back in Source Control, your files are listed under Changes, each with a letter:

| Letter | Meaning |
| --- | --- |
| U | Untracked: a new file Git hasn't seen before |
| M | Modified |
| D | Deleted |

Click a file to see a side-by-side comparison: the old version on the left, yours on the right.

4. Stage. Hover over a file and click + (Stage Changes). It moves to Staged Changes. To stage everything, click the + on the Changes heading.

5. Commit. Type a message in the box at the top, for example discovery: add jdoe server discovery script. Then click Commit (or press Ctrl+Enter). The commit is saved on your PC only.

6. Push. The button now says Sync Changes ↑1, meaning one commit is waiting to go up. Click it. The first time, VS Code explains that it will pull and push: click OK.

7. Check in Azure DevOps. In the browser, go to Repos → Commits, choose the develop branch, and your commit is at the top. Under Repos → Files, your folder and script are visible to the whole team.

Tip If you click Commit with nothing staged, VS Code offers to stage all changes and commit them directly. That's fine when you've checked every file in the list.

### 4.3 The daily loop

| Step | In VS Code | Equivalent command |
| --- | --- | --- |
| 1. Pull before you start | Source Control → ... → Pull, or the arrows next to develop in the status bar | git pull |
| 2. Write and test | Edit; run with F5 against a test server |  |
| 3. Review your changes | Source Control: click each file to see the side-by-side comparison | git diff |
| 4. Stage and commit | + on the files, type a message, Commit (Ctrl+Enter) | git add <file> then git commit -m "..." |
| 5. Push | Sync Changes (pull, then push) | git pull then git push |

Push at least once a day when you've changed something. Commits that stay on your PC aren't backed up, and nobody else can see them.

### 4.4 Commit messages

Short, in the form <area>: what changed, so the history reads like a changelog:

discovery: add SMBv1 client check for 2012+ sql: export Agent jobs with monthly schedules common: summary file now includes the script version fix: Get-ServerDiscovery failed on 2003 without PowerShell

Tip Microsoft 365 Copilot can draft a commit message: copy the diff from Source Control into the chat and ask for one in the <area>: what changed form (see 5.4).

### 4.5 If two people changed the same lines

VS Code shows a merge conflict when you pull, and the file appears under Merge Changes with a !. Open the file. Each conflict shows your version (Current) and the other version (Incoming). For each one, choose Accept Current Change, Accept Incoming Change or Accept Both Changes. Then save, stage, commit and push.

If you're not sure which version is right, find out who made the other change: hover over the line with GitLens, or see Repos → Commits in Azure DevOps. Then ask them.

Separate folders per author make conflicts rare.

### 4.6 Undo and fix mistakes

| Situation | What to do |
| --- | --- |
| Changed a file and want the original back (not committed) | Source Control → hover over the file → ↶ Discard Changes. Uncommitted changes are gone for good, so be sure. |
| Staged a file by mistake | Hover over it under Staged Changes → − (Unstage) |
| Committed, but not pushed yet | Source Control → ... → Commit → Undo Last Commit. Your changes come back as uncommitted edits |
| Already pushed something wrong | Don't try to rewrite history. Fix the file and push a new commit. If it's more serious, ask the tech lead |
| Pushed a password or secret | Tell the tech lead right away and have the password changed. Removing it from the repo isn't enough, because it stays in the history |

### 4.7 Troubleshooting

| Message or symptom | Cause and fix |
| --- | --- |
| Please tell me who you are | Git doesn't know your name yet. Run the two git config commands in 3.1 |
| Git not found / no Source Control view | Git for Windows isn't installed. Install it, then restart VS Code |
| Asked for a password in the terminal | The Credential Manager isn't being used. Reinstall Git for Windows with the default options, and sign in with your work account when the window appears |
| Sign-in keeps failing | In Windows Credential Manager → Windows Credentials, remove the entries starting with git:https://dev.azure.com, then pull again and sign in |
| Updates were rejected because the remote contains work that you do not have | Someone pushed before you. Pull first, then push (or use Sync Changes, which does both) |
| TF402455: Pushes to this branch are not permitted | develop has a branch policy. Contact the tech lead |
| A .csv file doesn't appear in Changes | That's intended: .gitignore keeps discovery output out of Git |
| Status bar shows main instead of develop | Click the branch name and choose develop (3.2, step 6) |

### 4.8 Later: feature branches and pull requests

When the team is comfortable with develop, the next step is short-lived branches merged through a pull request. One colleague reviews before the change reaches develop, and main holds the approved versions that run in bundles:

| main | ● approved v1.2 | ── | ── | ── | ── | ⬑ approved v1.3 |
| --- | --- | --- | --- | --- | --- | --- |
| develop | ── | ● integration | ── | ── | ⬑ PR approved | ── |
| feature/smb1-audit | ── | ── | ● SMBv1 audit 2016+ | ● review fixes | ── | ── |

This isn't required yet. It's listed here so the team knows where things are heading.

———   ◆   ———

## 5. Copilot

| Today: Microsoft 365 Copilot | Target: GitHub Copilot Business |
| --- | --- |
| - Approved and available now - Runs next to VS Code: browser, Teams or the Copilot app - You paste code in and copy answers back - No access to your files or the repository | - Needs a licence request (5.6) - Runs inside VS Code - Suggestions as you type; edits files directly - Reads the repository and the team's rules automatically |

Note These are two different products with separate licences. A Microsoft 365 Copilot licence doesn't enable Copilot inside VS Code.

### 5.1 Open Microsoft 365 Copilot Chat

- Open Microsoft 365 Copilot: the Copilot app, Copilot in Teams, or https://m365.cloud.microsoft/chat in the browser.

- Make sure you're signed in with your work account. The shield icon shows that enterprise data protection applies.

- Put the browser window or Teams next to VS Code. Use Win+← and Win+→ to snap them side by side.

### 5.2 Start each chat with the team context

Copilot Chat doesn't know our rules unless you tell it. Paste this block at the start of every new chat about scripts. The same text is in the repository as COPILOT-CONTEXT.md, so you can copy it from VS Code.

Context for this chat: - I write PowerShell scripts for Windows Server 2003 to 2019. Unless I say otherwise, code must be PowerShell 2.0 compatible: Get-WmiObject (not CIM), Export-Csv (not ConvertTo-Json), New-Object PSObject (not [PSCustomObject]). Newer cmdlets only behind: if ($PSVersionTable.PSVersion.Major -ge 3). - Discovery scripts are read-only. Never write to the registry, services, files outside -OutputPath, or SQL. - Never put credentials in code. Use Get-Credential or the vault. - Output: <SERVER>_<area>_<yyyyMMdd>.csv and <SERVER>_SUMMARY_<yyyyMMdd>.csv with columns Server, Area, Item, Flag, Detail, Owner, Decision, DecidedBy, Date. - Every script starts with comment-based help (.SYNOPSIS, .DESCRIPTION, .PARAMETER, .NOTES with Author, Version, Requires, Changes, .EXAMPLE). - T-SQL must say which SQL Server versions it supports (2000 has no DMVs). Answer with complete code blocks I can paste back into VS Code.

Tip Shortcut, if your tenant allows agents: in Microsoft 365 Copilot, create an agent (for example "Migration scripts") with the context above as its instructions, then share it with the team. Everyone starts from the same rules without pasting anything.

### 5.3 The workflow

| Step | Where | What you do |
| --- | --- | --- |
| 1. Select | VS Code | Select the function or section you want help with (Ctrl+A for the whole script). Small sections give better answers. |
| 2. Copy and ask | Copilot Chat | After the team context, paste the code and ask your question (see 5.4) |
| 3. Paste back | VS Code | Copy Copilot's code block and paste it in place of the selection |
| 4. Review the diff | VS Code, Source Control (Ctrl+Shift+G) | Click the file to see exactly what changed. Undo with Ctrl+Z if it's wrong |
| 5. Test | Test server | Run it, and on PowerShell 2.0 if it targets legacy servers |

### 5.4 Prompts that work well for this project

Explain what this script does, step by step, and list anything it changes on the server. (use on a colleague's script before you run it) Make this script compatible with PowerShell 2.0. Keep it read-only. Add an export step that writes the results to <SERVER>_services_<yyyyMMdd>.csv with columns Name, DisplayName, StartName, StartMode, State. Add a check: if a service runs as a named account, add an AMBER row to the flag summary with Area = "Identity". Write comment-based help for this script using our header format. This error appears on Windows Server 2008 R2: <paste the error>. Why, and what's the PowerShell 2.0 compatible fix? Convert this T-SQL to also work on SQL Server 2000 (sysprocesses, no DMVs). Write a commit message in the form "<area>: what changed" for this change: <paste the diff from Source Control>

### 5.5 Rules for using Copilot

Warning You're responsible for every line you commit, whether Copilot wrote it or not. - Read and test every answer before you commit. Copilot doesn't know which cmdlets exist on a 2008 server, and it can write code that looks right but isn't. - Don't paste secrets: no passwords, connection strings with credentials, or keys. - Don't paste real discovery data (server lists, IPs, user names, file listings) unless the company Copilot policy allows it. Use made-up examples such as APP01 or 10.0.0.10. - Use your work account only. Never use a personal Copilot or ChatGPT account for company code. - Follow the company's Copilot policy. The tech lead has the link.

### 5.6 Target: GitHub Copilot Business

The recommended path is to add GitHub Copilot Business licences for the people who write scripts. Microsoft 365 Copilot is designed for documents, mail and meetings; GitHub Copilot is designed for code.

What it would change for the team

| Today, with Microsoft 365 Copilot | With GitHub Copilot Business |
| --- | --- |
| Copy code to the chat and paste answers back | Suggestions and edits directly in VS Code |
| Paste the team context into every chat | The rules in .github/copilot-instructions.md are read automatically |
| Copilot sees only what you paste | Copilot sees the open files and the repository |
| One script at a time | Agent mode: one change across several scripts, each edit shown for approval |
| Write commit messages by hand, or paste the diff | Commit message generated from the changes, in Source Control |
| Errors analysed after copying them out | /fix and /explain on the code in place |

Points for the business case

- Productivity where the work is. The migration depends on many scripts being adapted to the standard output, the five rules and PowerShell 2.0. That's repetitive editing, which is what GitHub Copilot speeds up most.

- Governance built in. The team rules live in the repository and apply to every suggestion, not only when someone remembers to paste them.

- Enterprise controls. Copilot Business is managed by the company's GitHub organisation: seat assignment, policies, sign-in with the company identity (Entra ID), and settings such as the public-code filter. Microsoft's terms for Copilot Business say business code isn't used to train the models. Security and procurement should confirm this against the current terms.

- Works with the current repository. GitHub Copilot works with any Git repository opened in VS Code, including Azure DevOps. The licence comes through a GitHub organisation, but the code doesn't need to move.

- Small, measurable start. Begin with a pilot: a few seats for script authors over one or two bundles, then compare time per script adaptation before and after.

What to request (through the tech lead or manager, to the team that approved Microsoft 365 Copilot):

- GitHub Copilot Business seats for script authors (pilot size).

- A GitHub organisation linked to the company identity, if one doesn't exist yet.

- Confirmation of the data and usage policy from Security.

▾ Ready for when it's approved: .github/copilot-instructions.md

GitHub Copilot in VS Code reads this file from the repository automatically. It has the same content as the team context in 5.2:

# Copilot instructions for migration-scripts - Scripts run on Windows Server 2003 to 2019. Unless a script says otherwise, write PowerShell 2.0 compatible code: Get-WmiObject (not CIM), Export-Csv (not ConvertTo-Json), New-Object PSObject (not [PSCustomObject]). Newer cmdlets only behind: if ($PSVersionTable.PSVersion.Major -ge 3). - Discovery scripts are read-only. Never write to the registry, services, files outside -OutputPath, or SQL. - Never put credentials in code. Use Get-Credential or the vault. - Output: <SERVER>_<area>_<yyyyMMdd>.csv and <SERVER>_SUMMARY_<yyyyMMdd>.csv with columns Server, Area, Item, Flag, Detail, Owner, Decision, DecidedBy, Date. - Every script starts with comment-based help (.SYNOPSIS, .DESCRIPTION, .PARAMETER, .NOTES with Author, Version, Requires, Changes, .EXAMPLE). - T-SQL must say which SQL Server versions it supports (2000 has no DMVs).

———   ◆   ———

## 6. Checklist before you push

☐  Pulled develop first

☐  Script header filled in, and the version number bumped if the behaviour changed

☐  Still read-only; no secrets anywhere

☐  Produces the standard output (checked with checks/Test-DiscoveryOutput.ps1 on a test run)

☐  Tested on the oldest OS or SQL version it claims to support

☐  No warnings from PSScriptAnalyzer (shown in VS Code's Problems panel, Ctrl+Shift+M), or each one understood

☐  No output files or credentials staged (check the Source Control list)

☐  Clear commit message: <area>: what changed

———   ◆   ———

## 7. Target: fewer scripts, owned by the enterprise

Bring your own script is the starting point, not the end state. The wanted path is a small set of standard scripts, owned by the teams rather than by individuals, built from the best parts of everyone's work.

### 7.1 Why

| Today: many personal scripts | Target: a few enterprise-owned scripts |
| --- | --- |
| Each script depends on its author; if that person moves on, nobody maintains it | Owned by a team, with at least two maintainers per script |
| Same checks written several times, slightly differently | One implementation per check, improved by everyone |
| Results differ slightly from one script to another | Identical output for every server, so comparisons are easy |
| Hard to tell what ran on production | Released, versioned and signed scripts: the version is in every summary |
| Each new bundle needs several scripts adapted | One change, made once, applies to every bundle |

### 7.2 The path

| 1 · Collect everyone's scripts in the repository | → | 2 · Compare catalogue: who covers what, on which versions | → | 3 · Converge a few standard scripts, best parts merged in | → | 4 · Enterprise-owned team ownership, releases, signing, central feed |
| --- | --- | --- | --- | --- | --- | --- |

| Stage | What happens | Done when |
| --- | --- | --- |
| 1 · Collect (now) | Everyone pushes the scripts they use to develop, following the five rules (section 1) | Every script that ran in a bundle is in the repository |
| 2 · Compare | Build a catalogue: script, author, what it covers, OS and SQL versions supported, standard output yes or no. Review the overlaps in the tech discussion | Each Discovery checklist item has a "best current implementation" |
| 3 · Converge | Build the standard set (7.3) from the best parts. Authors are credited in the script header and the changelog, and invited to become maintainers. A personal script moves to archive/ only once the standard set covers everything it did | Bundles run on the standard set |
| 4 · Enterprise-owned | Team ownership (7.4), pull requests, released versions on main, code signing, and a central package feed | Production runs only released, signed versions |

### 7.3 The standard set

Around four maintained scripts or modules instead of one per person:

| Script / module | Owning team | Covers |
| --- | --- | --- |
| Server discovery | Windows team | Platform, identity, software, tasks, network, certificates, legacy protocols, FTP flows, files and shares |
| SQL discovery | DBA team | Instance, databases, jobs, security, activity capture and audit options for each SQL version |
| Common | Both teams | Standard CSV output, flag summary, scheduled connection capture, logging |
| Output check | Both teams | Checks a SharePoint folder for missing files or columns before Gate 1 |

Specific needs that don't fit the standard set can stay as extensions in the repository, using the common module for their output.

### 7.4 Who owns what

| Role | Who | Responsibility |
| --- | --- | --- |
| Owning team | Windows team (server script), DBA team (SQL script) | Decides what the script does; accountable for its quality |
| Maintainers | Two per script: a primary and a backup | Review and merge changes, publish releases, keep the changelog |
| Contributors | Anyone | Propose changes through a pull request |
| Tech lead |  | Approves the catalogue decisions (stage 2) and the move to stage 4 |

### 7.5 Rules once the scripts are enterprise-owned

- Changes go through a pull request to develop, approved by one maintainer. In Azure DevOps, a branch policy with required reviewers on each script's folder enforces this.

- Releases go to main with a version tag (for example v1.4.0) and a changelog entry (4.8).

- Scripts are signed with the company code-signing certificate, so the PowerShell execution policy can require signed scripts.

- Published as a PowerShell module to an internal feed (for example Azure Artifacts), so every admin workstation installs the same released version.

- Bundles run released versions only; develop is for work in progress.

- Every flag summary records the released version used.

### 7.6 How we'll know it's working

| Measure | Target |
| --- | --- |
| Discovery scripts in active use | 4 or fewer |
| Servers discovered with the standard set | 100% of a bundle |
| Maintainers per script | 2 or more |
| Time to adapt the scripts for a new bundle | Going down from bundle to bundle |

Note Nobody's work is thrown away. The standard set is built from the scripts the team already wrote, and their authors are credited. Personal scripts stay usable until the standard set covers what they do.

———   ◆   ———

Scripts & VS Code · companion to the migration governance guide · improve this page the same way as the scripts: change it and push to develop

MIGRATION GOVERNANCE · TEMPLATE # Server page template [SERVER NAME] · Migration page

How to use this template. Make one page per server, in the bundle's Loop workspace. Replace everything in [brackets] and delete the examples in italics. The rules behind each section are in the migration governance guide. Status values: Not started · In progress · Blocked · Done · N/A

———   ◆   ———

## At a glance

| Server | [name] |
| --- | --- |
| Bundle | [e.g. B03-Finance] |
| What it does | [one or two sentences: the application or service, and who uses it] |
| OS / SQL | [e.g. Windows Server 2008 R2 · SQL Server 2008 R2 Standard] |
| Out of support since | [date] |
| Disposition (decided at Gate 1) | [Migrate · Consolidate · Retire] |
| Current phase | [Discovery · Install & test · Migration · Decommissioning · Done] |
| Target | [new server name, OS, SQL version · or "retire"] |
| Planned cut-over | [date] |
| Last updated | [date, name] |

### Phase status

| Phase | Status | Gate signed (by · date) | Owner | Link |
| --- | --- | --- | --- | --- |
| 1 · Discovery | Not started |  | [sysadmin / DBA] | [ADO story] |
| 2 · Install & test | Not started |  | [sysadmin / DBA] | [ADO story] |
| 3 · Migration | Not started |  | [tech lead] | [ADO story] |
| 4 · Decommissioning | Not started |  | [sysadmin] | [ADO story] |

———   ◆   ———

## People

| Role | Name | Responsible for |
| --- | --- | --- |
| App owner (business) |  | Dependencies, UAT, acceptance (Gate 3), decisions about data |
| SME |  | How the application works, its interfaces and its schedules |
| Sysadmin |  | Server discovery, build, cut-over, decommissioning |
| DBA |  | SQL discovery, build, data migration and validation |
| Tech lead |  | Plan, decision log, gates 1, 2 and 4 |
| PM |  | Planning, the blockers meeting, stakeholder updates |
| Security / Cyber |  | Exceptions, cyber review |
| Other stakeholders |  | [teams or partners to keep informed] |

———   ◆   ———

## Links

| What | Link |
| --- | --- |
| ADO epic / feature | [link] |
| SharePoint folder | [Migration/<BUNDLE>/<SERVER>/] |
| Discovery summary (flags) | [<SERVER>_SUMMARY_<yyyyMMdd>.csv] |
| ServiceNow: server request | [link] |
| ServiceNow: change (CAB) | [link] |
| ServiceNow: decommission request | [link] |
| Architecture document | [link] |

———   ◆   ———

## 1 · Discovery

ADO story: [link] · Scripts version: [version or commit] · Capture week: [from – to]

### Key findings

[Three to five lines a non-technical reader can follow: what the server does, who connects to it, what's unusual.]

### Dependencies (confirmed by the app owner)

| Direction | System / partner / device | Protocol / port | Purpose | Confirmed by |
| --- | --- | --- | --- | --- |
| Inbound | Partner X | FTP 21 | Daily invoice drop in \\APP01\Inbound |  |
| Outbound | SQL02 | 1433 | Linked server for reporting |  |

### Monthly, quarterly and yearly jobs

The one-week capture doesn't see these, so each one needs an owner who confirms what it touches.

| Task / job | Schedule | What it touches | Owner confirmed |
| --- | --- | --- | --- |

### Gate 1 checklist

☐  Scripts ran from the approved version; output is in the SharePoint folder

☐  Summary reviewed by the sysadmin and the DBA

☐  Every RED flag has an owner and a decision (see Flags and blockers)

☐  App owner confirmed the dependencies and the unused data

☐  Disposition recorded: Migrate · Consolidate · Retire

☐  Signed: [tech lead, date]

———   ◆   ———

## Flags and blockers

RED blocks progress until it's decided. AMBER needs a plan. Every decision also goes into the decision log.

| # | Finding | Flag | Plan / decision | Owner | Due | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | FTP flows (port 21 / SFTP 22) to partners | AMBER | Move to Kiteworks (MFT) |  |  | Not started |
| 2 | Clear-text passwords in scripts and config files | RED | Move to the vault; rotate the passwords |  |  | Not started |
| 3 | SMBv1 used by scanners | AMBER | Firmware update before cut-over |  |  | Not started |

### Exceptions

Only for items that can't be fixed during the migration. Each one needs an end date.

| # | Item | Reason | Compensating control | Owner | End date | Approved by (Cyber) |
| --- | --- | --- | --- | --- | --- | --- |

———   ◆   ———

## Migration strategy

| Method | [In-place (1st choice) · side-by-side (2nd) · consolidation] |
| --- | --- |
| Path certainty | [Proven (lab or earlier server) · Uncertain → clone first] |
| Path | [e.g. SQL 2005 → 2016 (hop) → 2022 · Windows 2008 R2 → new 2022 server] |
| File transfers | [FTP flows → Kiteworks (MFT): list the flows] |
| Credentials | [Passwords found in files → vault; service accounts → gMSA where possible] |
| Legacy protocols | [SMBv1 / TLS 1.0 / NTLMv1: how each one is fixed on the target] |
| Data not migrated | [Archive, hand over or delete: the data owner's decision] |
| Rollback | [The source server stays untouched until Gate 3] |

### Summary of steps

- [e.g. Build the target server (ServiceNow request)]

- [e.g. Onboard the FTP flows on Kiteworks and test them with each partner]

- [e.g. Rehearse the migration on a copy and time it]

- [e.g. Cut over, validate, and get the app owner's sign-off]

———   ◆   ———

## 2 · Install & test

ServiceNow server request: [link] · ADO task: [link]

| Step | Status | Owner | Notes |
| --- | --- | --- | --- |
| In-place: clone run, only if the path is uncertain | Not started · N/A | Sysadmin | [proven or uncertain, and why] |
| In-place: OS upgrade and hardening | Not started | Sysadmin | [OS hops, snapshots] |
| In-place: OS hand-off to the DBA | Not started | Sysadmin → DBA | [date] · from here the DBA is responsible |
| Side-by-side: server built to the standard (OS, patches, OU, agents) | Not started | Sysadmin |  |
| SQL installed and configured to the standard | Not started |  |  |
| Firewall rules and certificates | Not started |  |  |
| Kiteworks (MFT) flows set up | Not started |  |  |
| Credentials stored in the vault | Not started |  |  |
| Smoke test (the app starts and connects) | Not started |  |  |
| UAT on test data | Not started |  |  |

### Gate 2 checklist

☐  Build complete; deviations logged

☐  Backup and restore tested on the target

☐  Monitoring green

☐  Signed: [tech lead, date]

———   ◆   ———

## 3 · Migration

### Approvals

| Approval | Status | Owner | Approver | Date | Evidence (link) |
| --- | --- | --- | --- | --- | --- |
| Architecture | Not started |  |  |  |  |
| Cyber | Not started |  |  |  |  |
| CAB (change) | Not started |  |  |  | [ServiceNow change] |
| UAT sign-off | Not started | App owner |  |  | [approval record] |
| Go / no-go for cut-over | Not started | Tech lead |  |  |  |

UAT sign-off: use a record that can be audited and linked here. Two options: - an approval on the ServiceNow change, assigned to the app owner; - a Teams Approvals request sent to the app owner. An email or a chat message isn't enough evidence.

### Rehearsal

| Date | Duration measured | Issues found | Done by |
| --- | --- | --- | --- |

### Delta and cut-over

| Delta steps | [final data sync, last files, last job runs: what moves at cut-over and in what order] |
| --- | --- |
| Freeze starts | [date and time; source read-only or services stopped] |
| Cut-over window | [date, start – end] |
| Point of no return | [time, and who decides] |
| Rollback plan | [link] |

### Validation

☐  Data validated (row counts, CHECKDB, key reports)

☐  Every dependency tested, including the Kiteworks flows with partners

☐  Legacy-protocol flags closed, or covered by an exception

☐  First backup on the target, and a restore tested

☐  Gate 3, signed by the app owner: [name, date, link to the approval]

———   ◆   ———

## 4 · Decommissioning

ServiceNow decommission request: [link]

| Step | Status | Owner | Date |
| --- | --- | --- | --- |
| Quiet period, or scream test for a retire (includes a month-end) | Not started |  |  |
| Data decision carried out (archive, hand over, delete) | Not started |  |  |
| SQL databases offline; final backup with a restore test | Not started |  |  |
| Server powered off (not deleted) | Not started |  |  |
| Removed from AD, DNS, DHCP, firewall | Not started |  |  |
| Removed from monitoring, backup, AV/EDR, patching | Not started |  |  |
| CMDB updated; licences reclaimed | Not started |  |  |
| Service accounts disabled; certificates revoked | Not started |  |  |
| VM deleted or hardware disposed of (disks wiped) | Not started |  |  |

☐  Gate 4 signed: [tech lead, date]

———   ◆   ———

## Decision log

| ID | Date | Decision | Why | Decided by |
| --- | --- | --- | --- | --- |

## Change history

| Date | Who | What changed on this page |
| --- | --- | --- |